## FS Elec
Stand Number | Section | Meter Serial | Parent Meter | Manufacturer | Meter Model | Connection size | Phase connected | Kiosk Number | Opening reading [kWh] | Meter Commission Date | AMR Installed | BO Board serial | EB Port | WBHO Subsection | Snag Date 1 | Snag Date 2 | Snag Date 3 | Snag Date 4 | Handover Date | Closing Reading
046 | A3 | 14558068871 | 82929684 | Hexing | HXP100DII | 1x80A | R | 10EVE2 | 0 | 2026-07-03 | TRUE | 2cf7f12072902fd1 | 6 | Section 13 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04
047 | B3 | 14558066198 | 82929684 | Hexing | HXP100DII | 1x80A | R | 10EVE2 | 0 | 2026-07-03 | TRUE | 2cf7f12072902fd1 | 3 | Section 10 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22
048 | A3 | 14558066255 | 82929684 | Hexing | HXP100DII | 1x80A | W | 10EVE2 | 0 | 2026-07-03 | TRUE | 2cf7f12072902fd1 | 5 | Section 13 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04
049 | B3 | 14558066115 | 82929684 | Hexing | HXP100DII | 1x80A | W | 10EVE2 | 0 | 2026-07-03 | TRUE | 2cf7f12072902fd1 | 2 | Section 10 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22
050 | A3 | 14558068913 | 82929684 | Hexing | HXP100DII | 1x80A | B | 10EVE2 | 0 | 2026-07-03 | TRUE | 2cf7f12072902fd1 | 4 | Section 13 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04
051 | B3 | 14558069010 | 82929684 | Hexing | HXP100DII | 1x80A | B | 10EVE2 | 0 | 2026-07-03 | TRUE | 2cf7f12072902fd1 | 1 | Section 10 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22
140 | B3 | 14558069556 | 71205556 | Hexing | HXP100DII | 1x80A | W | 10EVE3 | 0 | 2026-07-21 | FALSE | 2cf7f12072901e3a | 5 | Section 25 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
141 | A3 | 14558069721 | 71205556 | Hexing | HXP100DII | 1x80A | R | 10EVE3 | 0 | 2026-07-21 | FALSE | 2cf7f12072901e3a | 1 | Section 24 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
142 | B3 | 14558068038 | 71205556 | Hexing | HXP100DII | 1x80A | B | 10EVE3 | 0 | 2026-07-21 | FALSE | 2cf7f12072901e3a | 6 | Section 25 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
143 | A3 | 14558069135 | 71205556 | Hexing | HXP100DII | 1x80A | W | 10EVE3 | 0 | 2026-07-21 | FALSE | 2cf7f12072901e3a | 2 | Section 24 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
144 | B3 | 14558068103 | 71205556 | Hexing | HXP100DII | 1x80A | R | 10EVE3 | 0 | 2026-07-21 | FALSE | 2cf7f12072901e3a | 7 | Section 25 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
145 | A3 | 14558066354 | 71205556 | Hexing | HXP100DII | 1x80A | B | 10EVE3 | 0 | 2026-07-16 | FALSE | 2cf7f12072901e3a | 3 | Section 24 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
147 | A3 | 14558069838 | 71205556 | Hexing | HXP100DII | 1x80A | R | 10EVE3 | 0 | 2026-07-21 | FALSE | 2cf7f12072901e3a | 4 | Section 24 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
146 | B3 | 14558069812 | 71205556 | Hexing | HXP100DII | 1x80A | W | 11EVE3 | 0 | 2026-07-21 | FALSE | 2cf7f12072901d88 | 5 | Section 25 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
148 | B3 | 14558069754 | 71205556 | Hexing | HXP100DII | 1x80A | B | 11EVE3 | 0 | 2026-07-21 | FALSE | 2cf7f12072901d88 | 6 | Section 25 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
149 | A3 | 14558067931 | 71205556 | Hexing | HXP100DII | 1x80A | R | 11EVE3 | 0 | 2026-07-21 | FALSE | 2cf7f12072901d88 | 1 | Section 24 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
150 | B3 | 14558069788 | 71205556 | Hexing | HXP100DII | 1x80A | R | 11EVE3 | 0 | 2026-07-21 | FALSE | 2cf7f12072901d88 | 7 | Section 25 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
151 | A3 | 14558067956 | 71205556 | Hexing | HXP100DII | 1x80A | W | 11EVE3 | 0 | 2026-07-21 | FALSE | 2cf7f12072901d88 | 2 | Section 24 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
152 | B3 | 14558069747 | 71205556 | Hexing | HXP100DII | 1x80A | W | 11EVE3 | 0 | 2026-07-21 | FALSE | 2cf7f12072901d88 | 8 | Section 25 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
153 | A3 | 14558069879 | 71205556 | Hexing | HXP100DII | 1x80A | B | 11EVE3 | 0 | 2026-07-21 | FALSE | 2cf7f12072901d88 | 3 | Section 24 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
154 | A3 | 14558069861 | 71205556 | Hexing | HXP100DII | 1x80A | R | 11EVE3 | 0 | 2026-07-21 | FALSE | 2cf7f12072901d88 | 4 | Section 24 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
155 | A3 | 14558068920 | 82929702 | Hexing | HXP100DII | 1x80A | R | 1EVE1 | 0 | 2026-07-17 | FALSE | 2cf7f12072902d12 | 1 | Section 16 | 2026-07-23 | 2026-07-30 | 2026-08-14 | 2026-08-20
156 | A3 | 14558069598 | 82929702 | Hexing | HXP100DII | 1x80A | B | 1EVE1 | 0 | 2026-07-17 | FALSE | 2cf7f12072902d12 | 7 | Section 16 | 2026-07-23 | 2026-07-30 | 2026-08-14 | 2026-08-20
157 | A3 | 14558069770 | 82929702 | Hexing | HXP100DII | 1x80A | R | 1EVE1 | 0 | 2026-07-17 | FALSE | 2cf7f12072902d12 | 2 | Section 16 | 2026-07-23 | 2026-07-30 | 2026-08-14 | 2026-08-20
158 | A3 | 14558067923 | 82929702 | Hexing | HXP100DII | 1x80A | R | 1EVE1 | 0 | 2026-07-17 | FALSE | 2cf7f12072902d12 | 3 | Section 16 | 2026-07-23 | 2026-07-30 | 2026-08-14 | 2026-08-20
159 | A3 | 14558068137 | 82929702 | Hexing | HXP100DII | 1x80A | B | 1EVE1 | 0 | 2026-07-17 | FALSE | 2cf7f12072902d12 | 8 | Section 16 | 2026-07-23 | 2026-07-30 | 2026-08-14 | 2026-08-20
160 | A3 | 14558067865 | 82929702 | Hexing | HXP100DII | 1x80A | W | 1EVE1 | 0 | 2026-07-17 | FALSE | 2cf7f12072902d12 | 4 | Section 16 | 2026-07-23 | 2026-07-30 | 2026-08-14 | 2026-08-20
161 | A3 | 14558066081 | 82929702 | Hexing | HXP100DII | 1x80A | W | 1EVE1 | 0 | 2026-07-17 | FALSE | 2cf7f12072902d12 | 5 | Section 16 | 2026-07-23 | 2026-07-30 | 2026-08-14 | 2026-08-20
162 | A3 | 14558068012 | 82929702 | Hexing | HXP100DII | 1x80A | W | 1EVE1 | 0 | 2026-07-17 | FALSE | 2cf7f12072902d12 | 6 | Section 16 | 2026-07-23 | 2026-07-30 | 2026-08-14 | 2026-08-20
182 | A2 | 14558068855 | 82929684 | Hexing | HXP100DII | 1x80A | R | 1EVE2 | 0 | 2026-07-07 | FALSE | 2cf7f1207290340e | 1 | Section 7 | 2026-07-21 | 2026-07-28 | 2026-08-12 | 2026-08-18
183 | A2 | 14558066271 | 82929684 | Hexing | HXP100DII | 1x80A | W | 1EVE2 | 0 | 2026-07-07 | TRUE | 2cf7f1207290340e | 2 | Section 6 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04
184 | A2 | 14558066230 | 82929684 | Hexing | HXP100DII | 1x80A | B | 1EVE2 | 0 | 2026-07-07 | TRUE | 2cf7f1207290340e | 3 | Section 6 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04
185 | A2 | 14558066073 | 82929684 | Hexing | HXP100DII | 1x80A | R | 1EVE2 | 0 | 2026-07-07 | TRUE | 2cf7f1207290340e | 4 | Section 6 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04
186 | A2 | 14558066172 | 82929684 | Hexing | HXP100DII | 1x80A | W | 1EVE2 | 0 | 2026-07-07 | TRUE | 2cf7f1207290340e | 5 | Section 6 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04
187 | A2 | 14558068830 | 82929684 | Hexing | HXP100DII | 1x80A | B | 1EVE2 | 0 | 2026-07-07 | TRUE | 2cf7f1207290340e | 6 | Section 6 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04
122 | B3 | 14558069432 | 71205556 | Hexing | HXP100DII | 1x80A | W | 1EVE3 | 0 | 2026-06-20 | FALSE | 2cf7f12073100e80 | 9 | Section 22 | 2026-07-24 | 2026-07-31 | 2026-08-15 | 2026-08-21
124 | B3 | 14558068020 | 71205556 | Hexing | HXP100DII | 1x80A | B | 1EVE3 | 0 | 2026-06-20 | FALSE | 2cf7f12073100e80 | 6 | Section 22 | 2026-07-24 | 2026-07-31 | 2026-08-15 | 2026-08-21
125 | A1 | 14558068111 | 71205556 | Hexing | HXP100DII | 1x80A | B | 1EVE3 | 0 | 2026-06-20 | TRUE | 2cf7f12073100e80 | 8 | Section 1 | 2026-04-13 | 2026-04-20 | 2026-05-06 | 2026-05-12 | 2026-07-01 15:39 | 36.7
126 | B3 | 14558069846 | 71205556 | Hexing | HXP100DII | 1x80A | W | 1EVE3 | 0 | 2026-06-20 | FALSE | 2cf7f12073100e80 | 5 | Section 22 | 2026-07-24 | 2026-07-31 | 2026-08-15 | 2026-08-21
127 | A1 | 14558068152 | 71205556 | Hexing | HXP100DII | 1x80A | R | 1EVE3 | 0 | 2026-06-20 | TRUE | 2cf7f12073100e80 | 7 | Section 1 | 2026-04-13 | 2026-04-20 | 2026-05-06 | 2026-05-12 | 2026-07-01 17:09 | 11.591
128 | B3 | 14558069804 | 71205556 | Hexing | HXP100DII | 1x80A | R | 1EVE3 | 0 | 2026-06-20 | FALSE | 2cf7f12073100e80 | 4 | Section 22 | 2026-07-24 | 2026-07-31 | 2026-08-15 | 2026-08-21
129 | B3 | 14558069671 | 71205556 | Hexing | HXP100DII | 1x80A | B | 1EVE3 | 0 | 2026-06-20 | FALSE | 2cf7f12073100e80 | 3 | Section 22 | 2026-07-24 | 2026-07-31 | 2026-08-15 | 2026-08-21
130 | B3 | 14558067949 | 71205556 | Hexing | HXP100DII | 1x80A | W | 1EVE3 | 0 | 2026-06-20 | FALSE | 2cf7f12073100e80 | 2 | Section 22 | 2026-07-24 | 2026-07-31 | 2026-08-15 | 2026-08-21
131 | B3 | 14558068335 | 71205556 | Hexing | HXP100DII | 1x80A | R | 1EVE3 | 0 | 2026-06-20 | TRUE | 2cf7f12073100e80 | 1 | Section 22 | 2026-07-24 | 2026-07-31 | 2026-08-15 | 2026-08-21
163 | A3 | 14558069101 | 82929702 | Hexing | HXP100DII | 1x80A | B | 2EVE1 | 0 | 2026-07-17 | TRUE | 2cf7f12072903411 | 6 | Section 15 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04
164 | A3 | 14558067980 | 82929702 | Hexing | HXP100DII | 1x80A | R | 2EVE1 | 0 | 2026-07-17 | FALSE | 2cf7f12072903411 | 3 | Section 15 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04
165 | A3 | 14558067998 | 82929702 | Hexing | HXP100DII | 1x80A | R | 2EVE1 | 0 | 2026-07-17 | FALSE | 2cf7f12072903411 | 2 | Section 15 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04
166 | A3 | 14558068350 | 82929702 | Hexing | HXP100DII | 1x80A | R | 2EVE1 | 0 | 2026-07-17 | FALSE | 2cf7f12072903411 | 1 | Section 15 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04
167 | A3 | 14558069564 | 82929702 | Hexing | HXP100DII | 1x80A | W | 2EVE1 | 0 | 2026-07-17 | FALSE | 2cf7f12072903411 | 5 | Section 15 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04
168 | A3 | 14558068129 | 82929702 | Hexing | HXP100DII | 1x80A | B | 2EVE1 | 0 | 2026-07-17 | FALSE | 2cf7f12072903411 | 7 | Section 15 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04
169 | A3 | 14558068087 | 82929702 | Hexing | HXP100DII | 1x80A | W | 2EVE1 | 0 | 2026-07-17 | FALSE | 2cf7f12072903411 | 4 | Section 15 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04
076 | A2 | 14558068954 | 82929684 | Hexing | HXP100DII | 1x80A | R | 2EVE2 | 0 | 2026-06-25 | TRUE | 2cf7f12072901cf5 | 3 | Section 5 | 2026-06-17 | 2026-06-24 | 2026-07-08 | 2026-07-14 | 2026-07-31 | TBC
077 | A2 | 14558068764 | 82929684 | Hexing | HXP100DII | 1x80A | W | 2EVE2 | 0 | 2026-06-25 | TRUE | 2cf7f12072901cf5 | 4 | Section 5 | 2026-06-17 | 2026-06-24 | 2026-07-08 | 2026-07-14 | 2026-07-31 | TBC
078 | A2 | 14558068822 | 82929684 | Hexing | HXP100DII | 1x80A | B | 2EVE2 | 0 | 2026-06-25 | TRUE | 2cf7f12072901cf5 | 5 | Section 5 | 2026-06-17 | 2026-06-24 | 2026-07-08 | 2026-07-14 | 2026-07-31 | TBC
079 | A2 | 14558068848 | 82929684 | Hexing | HXP100DII | 1x80A | R | 2EVE2 | 0 | 2026-06-25 | TRUE | 2cf7f12072901cf5 | 1 | Section 5 | 2026-06-17 | 2026-06-24 | 2026-07-08 | 2026-07-14 | 2026-07-31 | TBC
080 | A2 | 14558068806 | 71205556 | Hexing | HXP100DII | 1x80A | B | 2EVE2 | 0 | 2026-06-25 | TRUE | 2cf7f12072901cf5 | 8 | Section 4 | 2026-06-02 | 2026-06-09 | 2026-06-24 | 2026-06-30 | 2026-07-31 | TBC
188 | A2 | 14558069291 | 82929684 | Hexing | HXP100DII | 1x80A | R | 2EVE2 | 0 | 2026-06-25 | TRUE | 2cf7f12072901cf5 | 6 | Section 6 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04
189 | A2 | 14558069036 | 82929684 | Hexing | HXP100DII | 1x80A | W | 2EVE2 | 0 | 2026-06-25 | TRUE | 2cf7f12072901cf5 | 7 | Section 6 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04
190 | A2 | 14558068897 | 82929684 | Hexing | HXP100DII | 1x80A | B | 2EVE2 | 0 | 2026-06-25 | TRUE | 2cf7f12072901cf5 | 2 | Section 6 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04
112 | B3 | 14558068053 | 71205556 | Hexing | HXP100DII | 1x80A | B | 2EVE3 | 0 | 2026-06-20 | FALSE | 2cf7f12073100ebc | 9 | Section 21 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06
114 | B3 | 14558068004 | 71205556 | Hexing | HXP100DII | 1x80A | W | 2EVE3 | 0.16 | 2026-06-20 | FALSE | 2cf7f12073100ebc | 8 | Section 21 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06
116 | B3 | 14558068079 | 71205556 | Hexing | HXP100DII | 1x80A | R | 2EVE3 | 0 | 2026-06-20 | TRUE | 2cf7f12073100ebc | 7 | Section 21 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06
117 | A1 | 14558069713 | 71205556 | Hexing | HXP100DII | 1x80A | R | 2EVE3 | 0 | 2026-06-20 | TRUE | 2cf7f12073100ebc | 4 | Section 1 | 2026-04-13 | 2026-04-20 | 2026-05-06 | 2026-05-12 | 2026-07-01 10:12 | 19.7
118 | B3 | 14558068095 | 71205556 | Hexing | HXP100DII | 1x80A | B | 2EVE3 | 0 | 2026-06-20 | FALSE | 2cf7f12073100ebc | 6 | Section 21 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06
119 | A1 | 14558069705 | 71205556 | Hexing | HXP100DII | 1x80A | B | 2EVE3 | 0 | 2026-06-20 | TRUE | 2cf7f12073100ebc | 3 | Section 1 | 2026-04-13 | 2026-04-20 | 2026-05-06 | 2026-05-12 | 2026-07-01 16:55 | 39.33
120 | B3 | 14558069663 | 71205556 | Hexing | HXP100DII | 1x80A | W | 2EVE3 | 0 | 2026-06-20 | FALSE | 2cf7f12073100ebc | 5 | Section 22 | 2026-07-24 | 2026-07-31 | 2026-08-15 | 2026-08-21
121 | A1 | 14558069762 | 71205556 | Hexing | HXP100DII | 1x80A | W | 2EVE3 | 0 | 2026-06-20 | TRUE | 2cf7f12073100ebc | 2 | Section 1 | 2026-04-13 | 2026-04-20 | 2026-05-06 | 2026-05-12 | 2026-07-01 10:11 | 35.67
123 | A1 | 14558069887 | 71205556 | Hexing | HXP100DII | 1x80A | R | 2EVE3 | 0 | 2026-06-20 | TRUE | 2cf7f12073100ebc | 1 | Section 1 | 2026-04-13 | 2026-04-20 | 2026-05-06 | 2026-05-12 | 2026-07-01 15:47 | 37.428
001 | A3 | 14558066321 | 82929702 | Hexing | HXP100DII | 1x80A | R | 3EVE1 | 0 | 2026-07-16 | FALSE | 2cf7f12073100145 | 1 | Section 20 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
002 | A3 | 14558069515 | 82929702 | Hexing | HXP100DII | 1x80A | R | 3EVE1 | 0 | 2026-07-16 | TRUE | 2cf7f12073100145 | 2 | Section 20 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
003 | B3 | 14558069051 | 82929702 | Hexing | HXP100DII | 1x80A | W | 3EVE1 | 0 | 2026-07-16 | FALSE | 2cf7f12073100145 | 6 | Section 18 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06
004 | A3 | 14558069440 | 82929702 | Hexing | HXP100DII | 1x80A | R | 3EVE1 | 0 | 2026-07-16 | FALSE | 2cf7f12073100145 | 3 | Section 20 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
005 | B3 | 14558068418 | 82929702 | Hexing | HXP100DII | 1x80A | B | 3EVE1 | 0 | 2026-07-16 | FALSE | 2cf7f12073100145 | 7 | Section 18 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06
006 | A3 | 14558068459 | 82929702 | Hexing | HXP100DII | 1x80A | W | 3EVE1 | 0 | 2026-07-16 | FALSE | 2cf7f12073100145 | 4 | Section 20 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
007 | B3 | 14558069572 | 82929702 | Hexing | HXP100DII | 1x80A | W | 3EVE1 | 0 | 2026-07-16 | FALSE | 2cf7f12073100145 | 5 | Section 18 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06
008 | A3 | 14558069408 | 82929702 | Hexing | HXP100DII | 1x80A | B | 3EVE1 | 0 | 2026-07-16 | FALSE | 2cf7f12073100145 | 9 | Section 20 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
009 | B3 | 14558069523 | 82929702 | Hexing | HXP100DII | 1x80A | B | 3EVE1 | 0 | 2026-07-16 | FALSE | 2cf7f12073100145 | 8 | Section 18 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06
068 | A3 | 14558068244 | 82929684 | Hexing | HXP100DII | 1x80A | R | 3EVE2 | 0 | 2026-06-24 | TRUE | 2cf7f120729029f5 | 6 | Section 12 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22
069 | B3 | 14558070026 | 82929684 | Hexing | HXP100DII | 1x80A | W | 3EVE2 | 0 | 2026-06-24 | TRUE | 2cf7f120729029f5 | 5 | Section 9 | 2026-05-11 | 2026-05-18 | 2026-06-01 | 2026-06-06
070 | A3 | 14558068228 | 82929684 | Hexing | HXP100DII | 1x80A | R | 3EVE2 | 0 | 2026-06-24 | TRUE | 2cf7f120729029f5 | 7 | Section 12 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22
071 | B3 | 14558069176 | 82929684 | Hexing | HXP100DII | 1x80A | B | 3EVE2 | 0 | 2026-06-24 | TRUE | 2cf7f120729029f5 | 1 | Section 9 | 2026-05-11 | 2026-05-18 | 2026-06-01 | 2026-06-06
072 | A3 | 14558068442 | 82929684 | Hexing | HXP100DII | 1x80A | R | 3EVE2 | 0 | 2026-06-24 | TRUE | 2cf7f120729029f5 | 8 | Section 12 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22
073 | B3 | 14558070000 | 82929684 | Hexing | HXP100DII | 1x80A | B | 3EVE2 | 0 | 2026-06-24 | TRUE | 2cf7f120729029f5 | 2 | Section 9 | 2026-05-11 | 2026-05-18 | 2026-06-01 | 2026-06-06
074 | A3 | 14558069317 | 82929684 | Hexing | HXP100DII | 1x80A | W | 3EVE2 | 0 | 2026-06-24 | TRUE | 2cf7f120729029f5 | 4 | Section 12 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22
075 | B3 | 14558070109 | 82929684 | Hexing | HXP100DII | 1x80A | B | 3EVE2 | 0 | 2026-06-24 | TRUE | 2cf7f120729029f5 | 3 | Section 9 | 2026-05-11 | 2026-05-18 | 2026-06-01 | 2026-06-06
104 | B3 | 14558068376 | 71205556 | Hexing | HXP100DII | 1x80A | B | 3EVE3 | 0 | 2026-06-20 | FALSE | 2cf7f12073100d7c | 9 | Section 21 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06
106 | B3 | 14558068293 | 71205556 | Hexing | HXP100DII | 1x80A | W | 3EVE3 | 0 | 2026-06-20 | FALSE | 2cf7f12073100d7c | 8 | Section 21 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06
107 | A1 | 14558067899 | 71205556 | Hexing | HXP100DII | 1x80A | W | 3EVE3 | 0.02 | 2026-06-20 | TRUE | 2cf7f12073100d7c | 5 | Section 2 | 2026-04-22 | 2026-04-30 | 2026-05-15 | 2026-05-21 | 2026-07-01 16:54 | 102.95
108 | B3 | 14558068277 | 71205556 | Hexing | HXP100DII | 1x80A | R | 3EVE3 | 0 | 2026-06-20 | FALSE | 2cf7f12073100d7c | 7 | Section 21 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06
109 | A1 | 14558067873 | 71205556 | Hexing | HXP100DII | 1x80A | R | 3EVE3 | 0.04 | 2026-06-20 | TRUE | 2cf7f12073100d7c | 4 | Section 2 | 2026-04-22 | 2026-04-30 | 2026-05-15 | 2026-05-21 | 2026-07-01 15:47 | 70.277
110 | B3 | 14558068202 | 71205556 | Hexing | HXP100DII | 1x80A | B | 3EVE3 | 0 | 2026-06-20 | TRUE | 2cf7f12073100d7c | 6 | Section 21 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06
111 | A1 | 14558067881 | 71205556 | Hexing | HXP100DII | 1x80A | B | 3EVE3 | 0.55 | 2026-06-20 | TRUE | 2cf7f12073100d7c | 3 | Section 2 | 2026-04-22 | 2026-04-30 | 2026-05-15 | 2026-05-21 | 2026-07-01 09:55 | 77.23
113 | A1 | 14558067907 | 71205556 | Hexing | HXP100DII | 1x80A | W | 3EVE3 | 0.53 | 2026-06-20 | TRUE | 2cf7f12073100d7c | 2 | Section 1 | 2026-04-13 | 2026-04-20 | 2026-05-06 | 2026-05-12 | 2026-07-01 10:14 | 25.35
115 | A1 | 14558067964 | 71205556 | Hexing | HXP100DII | 1x80A | R | 3EVE3 | 0 | 2026-06-20 | TRUE | 2cf7f12073100d7c | 1 | Section 1 | 2026-04-13 | 2026-04-20 | 2026-05-06 | 2026-05-12 | 2026-07-01 15:47 | 45.285
010 | A3 | 14558066248 | 82929702 | Hexing | HXP100DII | 1x80A | R | 4EVE1 | 0 | 2026-07-15 | FALSE | 2cf7f120731005ba | 3 | Section 20 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
011 | B3 | 14558069416 | 82929702 | Hexing | HXP100DII | 1x80A | W | 4EVE1 | 0 | 2026-07-15 | FALSE | 2cf7f120731005ba | 5 | Section 18 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06
012 | A3 | 14558069465 | 82929702 | Hexing | HXP100DII | 1x80A | R | 4EVE1 | 0 | 2026-07-15 | FALSE | 2cf7f120731005ba | 2 | Section 20 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
013 | B3 | 14558068988 | 82929702 | Hexing | HXP100DII | 1x80A | B | 4EVE1 | 0 | 2026-07-16 | FALSE | 2cf7f120731005ba | 9 | Section 18 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06
014 | A3 | 14558066305 | 82929702 | Hexing | HXP100DII | 1x80A | R | 4EVE1 | 0 | 2026-07-15 | FALSE | 2cf7f120731005ba | 1 | Section 20 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
015 | B3 | 14558068962 | 82929702 | Hexing | HXP100DII | 1x80A | B | 4EVE1 | 0 | 2026-07-16 | FALSE | 2cf7f120731005ba | 8 | Section 18 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06
016 | A3 | 14558068939 | 82929702 | Hexing | HXP100DII | 1x80A | W | 4EVE1 | 0 | 2026-07-15 | FALSE | 2cf7f120731005ba | 6 | Section 20 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
017 | B3 | 14558069549 | 82929702 | Hexing | HXP100DII | 1x80A | B | 4EVE1 | 0 | 2026-07-16 | FALSE | 2cf7f120731005ba | 7 | Section 17 | 2026-06-24 | 2026-07-01 | 2026-07-15 | 2026-07-21
018 | A3 | 14558066099 | 82929702 | Hexing | HXP100DII | 1x80A | W | 4EVE1 | 0 | 2026-07-15 | FALSE | 2cf7f120731005ba | 4 | Section 20 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
058 | A3 | 14558069093 | 82929684 | Hexing | HXP100DII | 1x80A | R | 4EVE2 | 0 | 2026-06-24 | TRUE | 2cf7f120731008bf | 9 | Section 13 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04
060 | A3 | 14558069242 | 82929684 | Hexing | HXP100DII | 1x80A | W | 4EVE2 | 0 | 2026-06-24 | TRUE | 2cf7f120731008bf | 8 | Section 13 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04
061 | B3 | 14558070083 | 82929684 | Hexing | HXP100DII | 1x80A | B | 4EVE2 | 0 | 2026-06-24 | TRUE | 2cf7f120731008bf | 1 | Section 9 | 2026-05-11 | 2026-05-18 | 2026-06-01 | 2026-06-06
062 | A3 | 14558069341 | 82929684 | Hexing | HXP100DII | 1x80A | B | 4EVE2 | 0 | 2026-06-24 | TRUE | 2cf7f120731008bf | 7 | Section 12 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22
063 | B3 | 14558068384 | 82929684 | Hexing | HXP100DII | 1x80A | W | 4EVE2 | 0 | 2026-06-24 | FALSE | 2cf7f120731008bf | 2 | Section 9 | 2026-05-11 | 2026-05-18 | 2026-06-01 | 2026-06-06
064 | A3 | 14558069200 | 82929684 | Hexing | HXP100DII | 1x80A | R | 4EVE2 | 0 | 2026-06-24 | TRUE | 2cf7f120731008bf | 6 | Section 12 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22
065 | B3 | 14558067972 | 82929684 | Hexing | HXP100DII | 1x80A | R | 4EVE2 | 0 | 2026-06-24 | TRUE | 2cf7f120731008bf | 3 | Section 9 | 2026-05-11 | 2026-05-18 | 2026-06-01 | 2026-06-06
066 | A3 | 14558069168 | 82929684 | Hexing | HXP100DII | 1x80A | W | 4EVE2 | 0 | 2026-06-24 | TRUE | 2cf7f120731008bf | 5 | Section 12 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22
067 | B3 | 14558069267 | 82929684 | Hexing | HXP100DII | 1x80A | B | 4EVE2 | 0 | 2026-06-24 | TRUE | 2cf7f120731008bf | 4 | Section 9 | 2026-05-11 | 2026-05-18 | 2026-06-01 | 2026-06-06
097 | A1 | 14558068194 | 71205556 | Hexing | HXP100DII | 1x80A | W | 4EVE3 | 1.09 | 2026-06-22 | TRUE | 2cf7f12072903342 | 5 | Section 2 | 2026-04-22 | 2026-04-30 | 2026-05-15 | 2026-05-21 | 2026-07-01 15:45 | 47.1
098 | B2 | 14558068236 | 71205556 | Hexing | HXP100DII | 1x80A | B | 4EVE3 | 4.23 | 2026-06-22 | TRUE | 2cf7f12072903342 | 8 | Section 5 | 2026-04-28 | 2026-05-06 | 2026-05-20 | 2026-05-26 | 2026-07-01 22:03 | 38.9
099 | A1 | 14558068178 | 71205556 | Hexing | HXP100DII | 1x80A | R | 4EVE3 | 1.11 | 2026-06-22 | TRUE | 2cf7f12072903342 | 4 | Section 2 | 2026-04-22 | 2026-04-30 | 2026-05-15 | 2026-05-21 | 2026-07-01 21:00 | 53.9
100 | B2 | 14558068368 | 71205556 | Hexing | HXP100DII | 1x80A | W | 4EVE3 | 5.23 | 2026-06-22 | TRUE | 2cf7f12072903342 | 7 | Section 5 | 2026-04-28 | 2026-05-06 | 2026-05-20 | 2026-05-26 | 2026-07-01 15:47 | 61.852
101 | A1 | 14558068160 | 71205556 | Hexing | HXP100DII | 1x80A | B | 4EVE3 | 0.38 | 2026-06-22 | TRUE | 2cf7f12072903342 | 3 | Section 2 | 2026-04-22 | 2026-04-30 | 2026-05-15 | 2026-05-21 | 2026-07-01 15:45 | 47.4
102 | B2 | 14558068392 | 71205556 | Hexing | HXP100DII | 1x80A | R | 4EVE3 | 2.74 | 2026-06-22 | TRUE | 2cf7f12072903342 | 6 | Section 5 | 2026-04-28 | 2026-05-06 | 2026-05-20 | 2026-05-26 | 2026-07-01 22:03 | 43.3
103 | A1 | 14558068285 | 71205556 | Hexing | HXP100DII | 1x80A | W | 4EVE3 | 1.37 | 2026-06-22 | TRUE | 2cf7f12072903342 | 2 | Section 2 | 2026-04-22 | 2026-04-30 | 2026-05-15 | 2026-05-21 | 2026-07-01 15:45 | 47.1
105 | A1 | 14558068301 | 71205556 | Hexing | HXP100DII | 1x80A | R | 4EVE3 | 1.63 | 2026-06-22 | TRUE | 2cf7f12072903342 | 1 | Section 2 | 2026-04-22 | 2026-04-30 | 2026-05-15 | 2026-05-21 | 2026-07-01 15:45 | 56.3
019 | B3 | 14558069481 | 82929702 | Hexing | HXP100DII | 1x80A | W | 5EVE1 | 0 | 2026-07-15 | TRUE | 2cf7f12072902d37 | 4 | Section 17 | 2026-06-24 | 2026-07-01 | 2026-07-15 | 2026-07-21
020 | A3 | 14558068434 | 82929702 | Hexing | HXP100DII | 1x80A | R | 5EVE1 | 0 | 2026-07-15 | TRUE | 2cf7f12072902d37 | 1 | Section 19 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
021 | B3 | 14558068798 | 82929702 | Hexing | HXP100DII | 1x80A | W | 5EVE1 | 0 | 2026-07-15 | FALSE | 2cf7f12072902d37 | 3 | Section 17 | 2026-06-24 | 2026-07-01 | 2026-07-15 | 2026-07-21
022 | A3 | 14558069002 | 82929702 | Hexing | HXP100DII | 1x80A | R | 5EVE1 | 0 | 2026-07-15 | TRUE | 2cf7f12072902d37 | 2 | Section 19 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
023 | B3 | 14558068921 | 82929702 | Hexing | HXP100DII | 1x80A | B | 5EVE1 | 0 | 2026-07-15 | FALSE | 2cf7f12072902d37 | 5 | Section 17 | 2026-06-24 | 2026-07-01 | 2026-07-15 | 2026-07-21
024 | A3 | 14558069374 | 82929702 | Hexing | HXP100DII | 1x80A | B | 5EVE1 | 0 | 2026-07-15 | FALSE | 2cf7f12072902d37 | 6 | Section 19 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
052 | A3 | 14558069895 | 82929684 | Hexing | HXP100DII | 1x80A | W | 5EVE2 | 0 | 2026-07-03 | TRUE | 2cf7f12072903b79 | 6 | Section 13 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04
053 | B3 | 14558069192 | 82929684 | Hexing | HXP100DII | 1x80A | R | 5EVE2 | 0 | 2026-07-03 | TRUE | 2cf7f12072903b79 | 4 | Section 10 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22
054 | A3 | 14558068269 | 82929684 | Hexing | HXP100DII | 1x80A | R | 5EVE2 | 0 | 2026-07-03 | TRUE | 2cf7f12072903b79 | 7 | Section 13 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04
055 | B3 | 14558068426 | 82929684 | Hexing | HXP100DII | 1x80A | W | 5EVE2 | 0 | 2026-07-03 | TRUE | 2cf7f12072903b79 | 3 | Section 10 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22
056 | A3 | 14558069358 | 82929684 | Hexing | HXP100DII | 1x80A | B | 5EVE2 | 0 | 2026-07-03 | TRUE | 2cf7f12072903b79 | 5 | Section 13 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04
057 | B3 | 14558068327 | 82929684 | Hexing | HXP100DII | 1x80A | B | 5EVE2 | 0 | 2026-07-03 | TRUE | 2cf7f12072903b79 | 2 | Section 10 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22
059 | B3 | 14558069531 | 82929684 | Hexing | HXP100DII | 1x80A | R | 5EVE2 | 0 | 2026-07-03 | TRUE | 2cf7f12072903b79 | 1 | Section 10 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22
092 | B2 | 14558068186 | 71205556 | Hexing | HXP100DII | 1x80A | W | 5EVE3 | 0.04 | 2026-06-22 | TRUE | 2cf7f12072902ba2 | 5 | Section 5 | 2026-04-28 | 2026-05-06 | 2026-05-20 | 2026-05-26 | 2026-07-01 22:04 | 76.2
093 | A1 | 14558069796 | 71205556 | Hexing | HXP100DII | 1x80A | W | 5EVE3 | 0.01 | 2026-06-22 | TRUE | 2cf7f12072902ba2 | 2 | Section 2 | 2026-04-22 | 2026-04-30 | 2026-05-15 | 2026-05-21 | 2026-07-01 15:47 | 31.8
094 | B2 | 14558068319 | 71205556 | Hexing | HXP100DII | 1x80A | R | 5EVE3 | 1.56 | 2026-06-22 | TRUE | 2cf7f12072902ba2 | 4 | Section 5 | 2026-04-28 | 2026-05-06 | 2026-05-20 | 2026-05-26 | 2026-07-01 22:04 | 100.4
095 | A1 | 14558069945 | 71205556 | Hexing | HXP100DII | 1x80A | R | 5EVE3 | 0 | 2026-06-22 | TRUE | 2cf7f12072902ba2 | 1 | Section 2 | 2026-04-22 | 2026-04-30 | 2026-05-15 | 2026-05-21 | 2026-07-01 22:04 | 73
096 | B2 | 14558069952 | 71205556 | Hexing | HXP100DII | 1x80A | B | 5EVE3 | 0.01 | 2026-06-22 | TRUE | 2cf7f12072902ba2 | 3 | Section 5 | 2026-04-28 | 2026-05-06 | 2026-05-20 | 2026-05-26 | 2026-07-01 22:04 | 55.5
025 | B3 | 14558066313 | 82929702 | Hexing | HXP100DII | 1x80A | W | 6EVE1 | 0 | 2026-07-15 | FALSE | 2cf7f12073100f68 | 5 | Section 17 | 2026-06-24 | 2026-07-01 | 2026-07-15 | 2026-07-21
026 | A3 | 14558069382 | 82929702 | Hexing | HXP100DII | 1x80A | B | 6EVE1 | 0 | 2026-07-15 | FALSE | 2cf7f12073100f68 | 7 | Section 19 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
027 | B3 | 14558069424 | 82929702 | Hexing | HXP100DII | 1x80A | B | 6EVE1 | 0 | 2026-07-15 | FALSE | 2cf7f12073100f68 | 9 | Section 17 | 2026-06-24 | 2026-07-01 | 2026-07-15 | 2026-07-21
028 | A3 | 14558069606 | 82929702 | Hexing | HXP100DII | 1x80A | R | 6EVE1 | 0 | 2026-07-15 | FALSE | 2cf7f12073100f68 | 3 | Section 19 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
029 | B3 | 14558068947 | 82929702 | Hexing | HXP100DII | 1x80A | R | 6EVE1 | 0 | 2026-07-15 | FALSE | 2cf7f12073100f68 | 1 | Section 17 | 2026-06-24 | 2026-07-01 | 2026-07-15 | 2026-07-21
030 | A3 | 14558069580 | 82929702 | Hexing | HXP100DII | 1x80A | R | 6EVE1 | 0 | 2026-07-15 | FALSE | 2cf7f12073100f68 | 2 | Section 19 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
031 | B3 | 14558068772 | 82929702 | Hexing | HXP100DII | 1x80A | B | 6EVE1 | 0 | 2026-07-15 | FALSE | 2cf7f12073100f68 | 8 | Section 17 | 2026-06-24 | 2026-07-01 | 2026-07-15 | 2026-07-21
032 | A3 | 14558069390 | 82929702 | Hexing | HXP100DII | 1x80A | W | 6EVE1 | 0 | 2026-07-15 | FALSE | 2cf7f12073100f68 | 4 | Section 19 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
033 | A3 | 14558069499 | 82929702 | Hexing | HXP100DII | 1x80A | W | 6EVE1 | 0 | 2026-07-15 | FALSE | 2cf7f12073100f68 | 6 | Section 19 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
176 | A2 | 14558068889 | 82929684 | Hexing | HXP100DII | 1x80A | R | 6EVE2 | 0 | 2026-07-07 | TRUE | 2cf7f12072903334 | 1 | Section 7 | 2026-07-21 | 2026-07-28 | 2026-08-12 | 2026-08-18
177 | A2 | 14558068780 | 82929684 | Hexing | HXP100DII | 1x80A | W | 6EVE2 | 0 | 2026-07-07 | TRUE | 2cf7f12072903334 | 2 | Section 7 | 2026-07-21 | 2026-07-28 | 2026-08-12 | 2026-08-18
178 | A2 | 14558066206 | 82929684 | Hexing | HXP100DII | 1x80A | B | 6EVE2 | 0 | 2026-07-07 | TRUE | 2cf7f12072903334 | 3 | Section 7 | 2026-07-21 | 2026-07-28 | 2026-08-12 | 2026-08-18
179 | A2 | 14558069143 | 82929684 | Hexing | HXP100DII | 1x80A | R | 6EVE2 | 0 | 2026-07-07 | TRUE | 2cf7f12072903334 | 4 | Section 7 | 2026-07-21 | 2026-07-28 | 2026-08-12 | 2026-08-18
180 | A2 | 14558069119 | 82929684 | Hexing | HXP100DII | 1x80A | W | 6EVE2 | 0 | 2026-07-07 | TRUE | 2cf7f12072903334 | 5 | Section 7 | 2026-07-21 | 2026-07-28 | 2026-08-12 | 2026-08-18
181 | A2 | 14558069234 | 82929684 | Hexing | HXP100DII | 1x80A | B | 6EVE2 | 0 | 2026-07-07 | TRUE | 2cf7f12072903334 | 6 | Section 7 | 2026-07-21 | 2026-07-28 | 2026-08-12 | 2026-08-18
170 | A3 | 14558070034 | 82929684 | Hexing | HXP100DII | 1x80A | R | 7EVE2 | 0 | 2026-07-07 | TRUE | 2cf7f12072902d3a | 1 | Section 8 | 2026-08-04 | 2026-08-12 | 2026-08-26 | 2026-09-01
171 | A2 | 14558069259 | 82929684 | Hexing | HXP100DII | 1x80A | W | 7EVE2 | 0 | 2026-07-07 | FALSE | 2cf7f12072902d3a | 2 | Section 8 | 2026-08-04 | 2026-08-12 | 2026-08-26 | 2026-09-01
172 | A2 | 14558069226 | 82929684 | Hexing | HXP100DII | 1x80A | B | 7EVE2 | 0 | 2026-07-07 | TRUE | 2cf7f12072902d3a | 3 | Section 8 | 2026-08-04 | 2026-08-12 | 2026-08-26 | 2026-09-01
173 | A2 | 14558069903 | 82929684 | Hexing | HXP100DII | 1x80A | R | 7EVE2 | 0 | 2026-07-07 | FALSE | 2cf7f12072902d3a | 4 | Section 8 | 2026-08-04 | 2026-08-12 | 2026-08-26 | 2026-09-01
174 | A2 | 14558069697 | 82929684 | Hexing | HXP100DII | 1x80A | W | 7EVE2 | 0 | 2026-07-07 | TRUE | 2cf7f12072902d3a | 5 | Section 8 | 2026-08-04 | 2026-08-12 | 2026-08-26 | 2026-09-01
175 | A2 | 14558069929 | 82929684 | Hexing | HXP100DII | 1x80A | B | 7EVE2 | 0 | 2026-07-07 | FALSE | 2cf7f12072902d3a | 6 | Section 7 | 2026-07-21 | 2026-07-28 | 2026-08-12 | 2026-08-18
089 | B2 | 14558069937 | 71205556 | Hexing | HXP100DII | 1x80A | R | 7EVE3 | 0 | 2026-06-23 | TRUE | 2cf7f120729020d2 | 1 | Section 3 | 2026-05-13 | 2026-05-20 | 2026-06-03 | 2026-06-09 | 2026-07-31 | TBC
090 | B2 | 14558070059 | 71205556 | Hexing | HXP100DII | 1x80A | W | 7EVE3 | 0 | 2026-06-23 | TRUE | 2cf7f120729020d2 | 2 | Section 3 | 2026-05-13 | 2026-05-20 | 2026-06-03 | 2026-06-09 | 2026-07-31 | TBC
091 | B2 | 14558068343 | 71205556 | Hexing | HXP100DII | 1x80A | B | 7EVE3 | 0 | 2026-06-23 | TRUE | 2cf7f120729020d2 | 3 | Section 3 | 2026-05-13 | 2026-05-20 | 2026-06-03 | 2026-06-09 | 2026-07-31 | TBC
034 | A3 | 14558069275 | 82929684 | Hexing | HXP100DII | 1x80A | R | 8EVE2 | 0 | 2026-07-03 | FALSE | 2cf7f12072903bab | 1 | Section 14 | 2026-06-22 | 2026-06-29 | 2026-07-18 | 2026-07-18
035 | B3 | 14558069325 | 82929684 | Hexing | HXP100DII | 1x80A | B | 8EVE2 | 0 | 2026-07-03 | FALSE | 2cf7f12072903bab | 3 | Section 11 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04
036 | A3 | 14558069978 | 82929684 | Hexing | HXP100DII | 1x80A | W | 8EVE2 | 0 | 2026-07-03 | FALSE | 2cf7f12072903bab | 2 | Section 14 | 2026-06-22 | 2026-06-29 | 2026-07-18 | 2026-07-18
037 | B3 | 14558069283 | 82929684 | Hexing | HXP100DII | 1x80A | R | 8EVE2 | 0 | 2026-07-03 | FALSE | 2cf7f12072903bab | 4 | Section 11 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04
081 | A2 | 14558069127 | 71205556 | Hexing | HXP100DII | 1x80A | W | 8EVE3 | 0 | 2026-06-23 | TRUE | 2cf7f12072901fa5 | 1 | Section 4 | 2026-06-02 | 2026-06-09 | 2026-06-24 | 2026-06-30 | 2026-07-31 | TBC
082 | A2 | 14558069077 | 71205556 | Hexing | HXP100DII | 1x80A | R | 8EVE3 | 0 | 2026-06-23 | TRUE | 2cf7f12072901fa5 | 2 | Section 4 | 2026-06-02 | 2026-06-09 | 2026-06-24 | 2026-06-30 | 2026-07-31 | TBC
083 | A2 | 14558068251 | 71205556 | Hexing | HXP100DII | 1x80A | B | 8EVE3 | 0 | 2026-06-23 | TRUE | 2cf7f12072901fa5 | 3 | Section 4 | 2026-06-02 | 2026-06-09 | 2026-06-24 | 2026-06-30 | 2026-07-31 | TBC
084 | A2 | 14558068210 | 71205556 | Hexing | HXP100DII | 1x80A | W | 8EVE3 | 0 | 2026-06-23 | TRUE | 2cf7f12072901fa5 | 4 | Section 4 | 2026-06-02 | 2026-06-09 | 2026-06-24 | 2026-06-30 | 2026-07-31 | TBC
085 | A2 | 14558069853 | 71205556 | Hexing | HXP100DII | 1x80A | R | 8EVE3 | 0 | 2026-06-23 | TRUE | 2cf7f12072901fa5 | 5 | Section 4 | 2026-06-02 | 2026-06-09 | 2026-06-24 | 2026-06-30 | 2026-07-31 | TBC
086 | A2 | 14558069911 | 71205556 | Hexing | HXP100DII | 1x80A | B | 8EVE3 | 0 | 2026-06-23 | TRUE | 2cf7f12072901fa5 | 6 | Section 4 | 2026-06-02 | 2026-06-09 | 2026-06-24 | 2026-06-30 | 2026-07-31 | TBC
087 | B2 | 14558069069 | 71205556 | Hexing | HXP100DII | 1x80A | R | 8EVE3 | 0 | 2026-06-23 | TRUE | 2cf7f12072901fa5 | 7 | Section 3 | 2026-05-13 | 2026-05-20 | 2026-06-03 | 2026-06-09 | 2026-07-31 | TBC
088 | B2 | 14558069333 | 71205556 | Hexing | HXP100DII | 1x80A | W | 8EVE3 | 0 | 2026-06-23 | TRUE | 2cf7f12072901fa5 | 8 | Section 3 | 2026-05-13 | 2026-05-20 | 2026-06-03 | 2026-06-09 | 2026-07-31 | TBC
038 | A3 | 14558069473 | 82929684 | Hexing | HXP100DII | 1x80A | R | 9EVE2 | 0 | 2026-07-03 | FALSE | 2cf7f120729018c1 | 8 | Section 14 | 2026-06-22 | 2026-06-29 | 2026-07-18 | 2026-07-18
039 | B3 | 14558069366 | 82929684 | Hexing | HXP100DII | 1x80A | W | 9EVE2 | 0 | 2026-07-03 | FALSE | 2cf7f120729018c1 | 4 | Section 11 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04
040 | A3 | 14558069614 | 82929684 | Hexing | HXP100DII | 1x80A | W | 9EVE2 | 0 | 2026-07-03 | FALSE | 2cf7f120729018c1 | 7 | Section 14 | 2026-06-22 | 2026-06-29 | 2026-07-18 | 2026-07-18
041 | B3 | 14558068905 | 82929684 | Hexing | HXP100DII | 1x80A | B | 9EVE2 | 0 | 2026-07-03 | FALSE | 2cf7f120729018c1 | 3 | Section 11 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04
042 | A3 | 14558069630 | 82929684 | Hexing | HXP100DII | 1x80A | B | 9EVE2 | 0 | 2026-07-03 | FALSE | 2cf7f120729018c1 | 6 | Section 14 | 2026-06-22 | 2026-06-29 | 2026-07-18 | 2026-07-18
043 | B3 | 14558068863 | 82929684 | Hexing | HXP100DII | 1x80A | R | 9EVE2 | 0 | 2026-07-03 | TRUE | 2cf7f120729018c1 | 1 | Section 11 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04
044 | A3 | 14558069655 | 82929684 | Hexing | HXP100DII | 1x80A | R | 9EVE2 | 0 | 2026-07-03 | TRUE | 2cf7f120729018c1 | 5 | Section 14 | 2026-06-22 | 2026-06-29 | 2026-07-18 | 2026-07-18
045 | B3 | 14558069622 | 82929684 | Hexing | HXP100DII | 1x80A | W | 9EVE2 | 0 | 2026-07-03 | FALSE | 2cf7f120729018c1 | 2 | Section 10 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22
132 | B3 | 14558069994 | 71205556 | Hexing | HXP100DII | 1x80A | R | 9EVE3 | 0 | 2026-07-22 | FALSE |  |  | Section 23 | 2026-08-08 | 2026-08-17 | 2026-08-31 | 2026-09-05
133 | B3 | 14558070117 | 71205556 | Hexing | HXP100DII | 1x80A | W | 9EVE3 | 0 | 2026-07-22 | FALSE |  |  | Section 23 | 2026-08-08 | 2026-08-17 | 2026-08-31 | 2026-09-05
134 | B3 | 14558068814 | 71205556 | Hexing | HXP100DII | 1x80A | B | 9EVE3 | 0 | 2026-07-22 | FALSE |  |  | Section 23 | 2026-08-08 | 2026-08-17 | 2026-08-31 | 2026-09-05
135 | B3 | 14558068996 | 71205556 | Hexing | HXP100DII | 1x80A | R | 9EVE3 | 0 | 2026-07-22 | FALSE |  |  | Section 23 | 2026-08-08 | 2026-08-17 | 2026-08-31 | 2026-09-05
136 | B3 | 14558069457 | 71205556 | Hexing | HXP100DII | 1x80A | W | 9EVE3 | 0 | 2026-07-22 | FALSE |  |  | Section 23 | 2026-08-08 | 2026-08-17 | 2026-08-31 | 2026-09-05
137 | B3 | 14558069028 | 71205556 | Hexing | HXP100DII | 1x80A | B | 9EVE3 | 0 | 2026-07-22 | FALSE |  |  | Section 23 | 2026-08-08 | 2026-08-17 | 2026-08-31 | 2026-09-05
138 | B3 | 14558069218 | 71205556 | Hexing | HXP100DII | 1x80A | R | 9EVE3 | 0 | 2026-07-22 | FALSE |  |  | Section 23 | 2026-08-08 | 2026-08-17 | 2026-08-31 | 2026-09-05
139 | B3 | 14558069648 | 71205556 | Hexing | HXP100DII | 1x80A | W | 9EVE3 | 0 | 2026-07-22 | FALSE |  |  | Section 23 | 2026-08-08 | 2026-08-17 | 2026-08-31 | 2026-09-05
Clubhouse | A1 | 98819618 | 82929684 | Iskra | MT174D | 3x100A | RWB | MS2 | 0 | 2026-06-09 | TRUE | 2cf7f1207310074f | 10 | Section 1 | 2026-04-13 | 2026-04-20 | 2026-05-06 | 2026-05-12

## FS Water
Stand Number | Section | Meter serial number | Manufacturer | Meter Model | Connection size | Opening readings | Meter Commissioning Date | AMR Commissioned | WBHO Subsection | Snag Date 1 | Snag Date 2 | Snag Date 3 | Snag Date 4 | Faulty Meter | Faulty Replaced | Replacement Date | Handover Date | Closing Reading
001 | A3 | 10596212 | Precision | Axioma | 20mm | 0.085 | 2026-08-20 | TRUE | Section 20 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06 | FALSE | FALSE
002 | A3 | 10596210 | Precision | Axioma | 20mm | 0.077 | 2026-08-20 | TRUE | Section 20 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06 | FALSE | FALSE
003 | B3 | 10596190 | Precision | Axioma | 20mm | 0.092 | 2026-08-24 | FALSE | Section 18 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06 | FALSE | FALSE
004 | A3 | 10596206 | Precision | Axioma | 20mm | 0.092 | 2026-08-20 | TRUE | Section 20 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06 | FALSE | FALSE
005 | B3 | 10596304 | Precision | Axioma | 20mm | 0.093 | 2026-08-21 | TRUE | Section 18 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06 | FALSE | FALSE
006 | A3 | 10596211 | Precision | Axioma | 20mm | 0.085 | 2026-08-20 | TRUE | Section 20 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06 | FALSE | FALSE
007 | B3 | 10596231 | Precision | Axioma | 20mm | 0.104 | 2026-08-21 | TRUE | Section 18 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06 | FALSE | FALSE
008 | A3 | 10596282 | Precision | Axioma | 20mm | 0.085 | 2026-08-20 | TRUE | Section 20 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06 | FALSE | FALSE
009 | B3 | 10596214 | Precision | Axioma | 20mm | 0.077 | 2026-08-20 | TRUE | Section 18 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06 | FALSE | FALSE
010 | A3 | 10596126 | Precision | Axioma | 20mm | 0.091 | 2026-08-20 | TRUE | Section 20 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06 | FALSE | FALSE
011 | B3 | 10596200 | Precision | Axioma | 20mm | 0.091 | 2026-08-20 | TRUE | Section 18 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06 | FALSE | FALSE
012 | A3 | 10596380 | Precision | Axioma | 20mm | 0.083 | 2026-08-20 | TRUE | Section 20 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06 | FALSE | FALSE
013 | B3 | 10596275 | Precision | Axioma | 20mm | 0.084 | 2026-08-20 | TRUE | Section 18 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06 | FALSE | FALSE
014 | A3 | 10596276 | Precision | Axioma | 20mm | 0.076 | 2026-08-20 | TRUE | Section 20 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06 | FALSE | FALSE
015 | B3 | 10596269 | Precision | Axioma | 20mm | 0.087 | 2026-08-20 | TRUE | Section 18 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06 | FALSE | FALSE
016 | A3 | 10596239 | Precision | Axioma | 20mm | 0.083 | 2026-08-20 | TRUE | Section 20 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06 | FALSE | FALSE
017 | B3 | 10596182 | Precision | Axioma | 20mm | 0.098 | 2026-08-20 | TRUE | Section 17 | 2026-06-24 | 2026-07-01 | 2026-07-15 | 2026-07-21 | FALSE | FALSE
018 | A3 | 10596185 | Precision | Axioma | 20mm | 0.099 | 2026-08-20 | TRUE | Section 20 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06 | FALSE | FALSE
019 | B3 | 10596196 | Precision | Axioma | 20mm | 0.091 | 2026-08-20 | TRUE | Section 17 | 2026-06-24 | 2026-07-01 | 2026-07-15 | 2026-07-21 | FALSE | FALSE
020 | A3 | 10596201 | Precision | Axioma | 20mm | 0.093 | 2026-08-20 | TRUE | Section 19 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21 | FALSE | FALSE
021 | B3 | 54789074 | Kamstrup | FlowIQ2200 | 20mm | 0.118 | 2026-08-14 | TRUE | Section 17 | 2026-06-24 | 2026-07-01 | 2026-07-15 | 2026-07-21 | FALSE | FALSE
022 | A3 | 10596118 | Precision | Axioma | 20mm | 0.092 | 2026-08-20 | TRUE | Section 19 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21 | FALSE | FALSE
023 | B3 | 54789043 | Kamstrup | FlowIQ2200 | 20mm | 0.151 | 2026-08-14 | TRUE | Section 17 | 2026-06-24 | 2026-07-01 | 2026-07-15 | 2026-07-21 | FALSE | FALSE
024 | A3 | 10596208 | Precision | Axioma | 20mm | 0.09 | 2026-08-20 | TRUE | Section 19 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21 | FALSE | FALSE
025 | B3 | 54789075 | Kamstrup | FlowIQ2200 | 20mm | 0.117 | 2026-08-18 | TRUE | Section 17 | 2026-06-24 | 2026-07-01 | 2026-07-15 | 2026-07-21 | FALSE | FALSE
026 | A3 | 54789076 | Kamstrup | FlowIQ2200 | 20mm | 0.117 | 2026-08-18 | TRUE | Section 19 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21 | FALSE | FALSE
027 | B3 | 54789078 | Kamstrup | FlowIQ2200 | 20mm | 0.117 | 2026-08-18 | TRUE | Section 17 | 2026-06-24 | 2026-07-01 | 2026-07-15 | 2026-07-21 | FALSE | FALSE
028 | A3 | 10596193 | Precision | Axioma | 20mm | 0.09 | 2026-08-20 | TRUE | Section 19 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21 | FALSE | FALSE
029 | B3 | 10596114 | Precision | Axioma | 20mm | 0.092 | 2026-08-20 | TRUE | Section 17 | 2026-06-24 | 2026-07-01 | 2026-07-15 | 2026-07-21 | FALSE | FALSE
030 | A3 | 10596225 | Precision | Axioma | 20mm | 0.086 | 2026-08-20 | TRUE | Section 19 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21 | FALSE | FALSE
031 | B3 | 10596198 | Precision | Axioma | 20mm | 0.12 | 2026-08-14 | FALSE | Section 17 | 2026-06-24 | 2026-07-01 | 2026-07-15 | 2026-07-21 | FALSE | FALSE
032 | A3 | 54789039 | Kamstrup | FlowIQ2200 | 20mm | 0.151 | 2026-08-14 | TRUE | Section 19 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21 | FALSE | FALSE
033 | A3 | 54789048 | Kamstrup | FlowIQ2200 | 20mm | 0.12 | 2026-08-14 | TRUE | Section 19 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21 | FALSE | FALSE
034 | A3 | 9993262 | Precision | Axioma | 20mm | 0.082 | 2026-07-02 | TRUE | Section 14 | 2026-06-22 | 2026-06-29 | 2026-07-18 | 2026-07-18 | FALSE | FALSE
035 | B3 | 10192065 | Precision | Axioma | 20mm | 0.091 | 2026-07-02 | TRUE | Section 11 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04 | FALSE | FALSE
036 | A3 | 10192049 | Precision | Axioma | 20mm | 0.091 | 2026-07-02 | TRUE | Section 14 | 2026-06-22 | 2026-06-29 | 2026-07-18 | 2026-07-18 | FALSE | FALSE
037 | B3 | 10192051 | Precision | Axioma | 20mm | 0.089 | 2026-07-02 | TRUE | Section 11 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04 | FALSE | FALSE
038 | A3 | 10192048 | Precision | Axioma | 20mm | 0.091 | 2026-07-02 | TRUE | Section 14 | 2026-06-22 | 2026-06-29 | 2026-07-18 | 2026-07-18 | FALSE | FALSE
039 | B3 | 10596179 | Precision | Axioma | 20mm | 0.12 | 2026-07-02 | FALSE | Section 11 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04 | TRUE | TRUE | 2026-09-08
040 | A3 | 10192061 | Precision | Axioma | 20mm | 0.089 | 2026-07-02 | TRUE | Section 14 | 2026-06-22 | 2026-06-29 | 2026-07-18 | 2026-07-18 | FALSE | FALSE
041 | B3 | 9993241 | Precision | Axioma | 20mm | 0.076 | 2026-07-02 | TRUE | Section 11 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04 | FALSE | FALSE
042 | A3 | 10216100 | Precision | Axioma | 20mm | 0.155 | 2026-07-02 | TRUE | Section 14 | 2026-06-22 | 2026-06-29 | 2026-07-18 | 2026-07-18 | FALSE | FALSE
043 | B3 | 9993239 | Precision | Axioma | 20mm | 0.076 | 2026-07-02 | TRUE | Section 11 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04 | FALSE | FALSE
044 | A3 | 9993254 | Precision | Axioma | 20mm | 0.081 | 2026-07-02 | TRUE | Section 14 | 2026-06-22 | 2026-06-29 | 2026-07-18 | 2026-07-18 | FALSE | FALSE
045 | B3 | 10596203 | Precision | Axioma | 20mm | 0.095 | 2026-07-02 | FALSE | Section 10 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22 | TRUE | TRUE | 2026-09-14
046 | A3 | 10192058 | Precision | Axioma | 20mm | 0.086 | 2026-07-02 | TRUE | Section 13 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04 | FALSE | FALSE
047 | B3 | 10216099 | Precision | Axioma | 20mm | 0.154 | 2026-07-01 | TRUE | Section 10 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22 | FALSE | FALSE
048 | A3 | 9993267 | Precision | Axioma | 20mm | 0.081 | 2026-07-02 | TRUE | Section 13 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04 | FALSE | FALSE
049 | B3 | 10596183 | Precision | Axioma | 20mm | 0.111 | 2026-07-01 | FALSE | Section 10 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22 | TRUE | TRUE | 2026-09-08
050 | A3 | 10192026 | Precision | Axioma | 20mm | 0.066 | 2026-07-02 | TRUE | Section 13 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04 | FALSE | FALSE
051 | B3 | 10192066 | Precision | Axioma | 20mm | 0.089 | 2026-07-01 | TRUE | Section 10 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22 | FALSE | FALSE
052 | A3 | 9993263 | Precision | Axioma | 20mm | 0.076 | 2026-07-02 | TRUE | Section 13 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04 | FALSE | FALSE
053 | B3 | 10192023 | Precision | Axioma | 20mm | 0.067 | 2026-07-01 | TRUE | Section 10 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22 | FALSE | FALSE
054 | A3 | 9993269 | Precision | Axioma | 20mm | 0.074 | 2026-07-02 | TRUE | Section 13 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04 | FALSE | FALSE
055 | B3 | 10192060 | Precision | Axioma | 20mm | 0.091 | 2026-07-01 | TRUE | Section 10 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22 | FALSE | FALSE
056 | A3 | 10192024 | Precision | Axioma | 20mm | 0.061 | 2026-07-02 | TRUE | Section 13 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04 | FALSE | FALSE
057 | B3 | 9907505 | Precision | Axioma | 20mm | 0.076 | 2026-07-01 | TRUE | Section 10 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22 | FALSE | FALSE
058 | A3 | 9993264 | Precision | Axioma | 20mm | 0.082 | 2026-07-02 | TRUE | Section 13 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04 | FALSE | FALSE
059 | B3 | 54789019 | Kamstrup | FlowIQ2200 | 20mm | 0.175 | 2026-07-01 | TRUE | Section 10 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22 | TRUE | TRUE | 2026-09-08
060 | A3 | 9993270 | Precision | Axioma | 20mm | 0.081 | 2026-07-02 | TRUE | Section 13 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04 | FALSE | FALSE
061 | B3 | 10192017 | Precision | Axioma | 20mm | 0.067 | 2026-06-13 | TRUE | Section 9 | 2026-05-11 | 2026-05-18 | 2026-06-01 | 2026-06-06 | FALSE | FALSE
062 | A3 | 10596300 | Precision | Axioma | 20mm | 0.104 | 2026-06-13 | TRUE | Section 12 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22 | TRUE | TRUE | 2026-08-20
063 | B3 | 10192021 | Precision | Axioma | 20mm | 0.066 | 2026-06-13 | TRUE | Section 9 | 2026-05-11 | 2026-05-18 | 2026-06-01 | 2026-06-06 | FALSE | FALSE
064 | A3 | 9993250 | Precision | Axioma | 20mm | 0.081 | 2026-06-13 | TRUE | Section 12 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22 | FALSE | FALSE
065 | B3 | 10192022 | Precision | Axioma | 20mm | 0.067 | 2026-06-13 | TRUE | Section 9 | 2026-05-11 | 2026-05-18 | 2026-06-01 | 2026-06-06 | FALSE | FALSE
066 | A3 | 9993255 | Precision | Axioma | 20mm | 0.082 | 2026-07-01 | TRUE | Section 12 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22 | FALSE | FALSE
067 | B3 | 10596245 | Precision | Axioma | 20mm | 0.113 | 2026-06-13 | TRUE | Section 9 | 2026-05-11 | 2026-05-18 | 2026-06-01 | 2026-06-06 | TRUE | TRUE | 2026-08-20
068 | A3 | 10192012 | Precision | Axioma | 20mm | 0.069 | 2026-07-01 | TRUE | Section 12 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22 | FALSE | FALSE
069 | B3 | 10192007 | Precision | Axioma | 20mm | 0.066 | 2026-06-13 | TRUE | Section 9 | 2026-05-11 | 2026-05-18 | 2026-06-01 | 2026-06-06 | FALSE | FALSE
070 | A3 | 9897925 | Precision | Axioma | 20mm | 0.072 | 2026-06-13 | TRUE | Section 12 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22 | FALSE | FALSE
071 | B3 | 10172133 | Precision | Axioma | 20mm | 0.083 | 2026-06-09 | TRUE | Section 9 | 2026-05-11 | 2026-05-18 | 2026-06-01 | 2026-06-06 | FALSE | FALSE
072 | A3 | 10596189 | Precision | Axioma | 20mm | 0.101 | 2026-06-09 | TRUE | Section 12 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22 | TRUE | TRUE | 2026-08-20
073 | B3 | 9897893 | Precision | Axioma | 20mm | 0.07 | 2026-06-09 | TRUE | Section 9 | 2026-05-11 | 2026-05-18 | 2026-06-01 | 2026-06-06 | FALSE | FALSE
074 | A3 | 9897897 | Precision | Axioma | 20mm | 0.07 | 2026-06-09 | TRUE | Section 12 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22 | FALSE | FALSE
075 | B3 | 9897987 | Precision | Axioma | 20mm | 0.072 | 2026-06-09 | TRUE | Section 9 | 2026-05-11 | 2026-05-18 | 2026-06-01 | 2026-06-06 | FALSE | FALSE
076 | A2 | 10192062 | Precision | Axioma | 20mm | 0.096 | 2026-06-04 | TRUE | Section 5 | 2026-06-17 | 2026-06-24 | 2026-07-08 | 2026-07-14 | TRUE | TRUE | 2026-07-13 | 2026-07-31 | 3.47
077 | A2 | 10172251 | Precision | Axioma | 20mm | 0.103 | 2026-06-04 | TRUE | Section 5 | 2026-06-17 | 2026-06-24 | 2026-07-08 | 2026-07-14 | FALSE | FALSE |  | 2026-07-31 | 3.19
078 | A2 | 10172260 | Precision | Axioma | 20mm | 0.103 | 2026-05-29 | TRUE | Section 5 | 2026-06-17 | 2026-06-24 | 2026-07-08 | 2026-07-14 | FALSE | FALSE |  | 2026-07-31 | 11.05
079 | A2 | 10172246 | Precision | Axioma | 20mm | 0.097 | 2026-06-04 | TRUE | Section 5 | 2026-06-17 | 2026-06-24 | 2026-07-08 | 2026-07-14 | FALSE | FALSE |  | 2026-07-31 | 4.42
080 | A2 | 10172248 | Precision | Axioma | 20mm | 0.096 | 2026-05-29 | TRUE | Section 4 | 2026-06-02 | 2026-06-09 | 2026-06-24 | 2026-06-30 | FALSE | FALSE |  | 2026-07-31 | 8.92
081 | A2 | 10596241 | Precision | Axioma | 20mm | 0.102 | 2026-05-29 | FALSE | Section 4 | 2026-06-02 | 2026-06-09 | 2026-06-24 | 2026-06-30 | TRUE | TRUE | 2026-08-24 | 2026-07-31 | 7.78
082 | A2 | 10172256 | Precision | Axioma | 20mm | 0.102 | 2026-05-29 | TRUE | Section 4 | 2026-06-02 | 2026-06-09 | 2026-06-24 | 2026-06-30 | FALSE | FALSE |  | 2026-07-31 | 7.59
083 | A2 | 10172257 | Precision | Axioma | 20mm | 0.102 | 2026-05-29 | TRUE | Section 4 | 2026-06-02 | 2026-06-09 | 2026-06-24 | 2026-06-30 | FALSE | FALSE |  | 2026-07-31 | 14.26
084 | A2 | 10172262 | Precision | Axioma | 20mm | 0.102 | 2026-05-29 | TRUE | Section 4 | 2026-06-02 | 2026-06-09 | 2026-06-24 | 2026-06-30 | FALSE | FALSE |  | 2026-07-31 | 11.58
085 | A2 | 10172253 | Precision | Axioma | 20mm | 0.101 | 2026-05-29 | TRUE | Section 4 | 2026-06-02 | 2026-06-09 | 2026-06-24 | 2026-06-30 | FALSE | FALSE |  | 2026-07-31 | 8.42
086 | A2 | 10172135 | Precision | Axioma | 20mm | 0.088 | 2026-06-04 | TRUE | Section 4 | 2026-06-02 | 2026-06-09 | 2026-06-24 | 2026-06-30 | FALSE | FALSE |  | 2026-07-31 | 4.56
087 | B2 | 10192014 | Precision | Axioma | 20mm | 0.069 | 2026-07-01 | TRUE | Section 3 | 2026-05-13 | 2026-05-20 | 2026-06-03 | 2026-06-09 | FALSE | FALSE |  | 2026-07-31 | 4.73
088 | B2 | 10172138 | Precision | Axioma | 20mm | 0.085 | 2026-06-09 | TRUE | Section 3 | 2026-05-13 | 2026-05-20 | 2026-06-03 | 2026-06-09 | FALSE | FALSE |  | 2026-07-31 | 23.56
089 | B2 | 10172265 | Precision | Axioma | 20mm | 0.102 | 2026-05-21 | TRUE | Section 3 | 2026-05-13 | 2026-05-20 | 2026-06-03 | 2026-06-09 | FALSE | FALSE |  | 2026-07-31 | 4.43
090 | B2 | 10172247 | Precision | Axioma | 20mm | 0.097 | 2026-05-21 | TRUE | Section 3 | 2026-05-13 | 2026-05-20 | 2026-06-03 | 2026-06-09 | FALSE | FALSE |  | 2026-07-31 | 13.63
091 | B2 | 10172249 | Precision | Axioma | 20mm | 0.099 | 2026-05-21 | TRUE | Section 3 | 2026-05-13 | 2026-05-20 | 2026-06-03 | 2026-06-09 | FALSE | FALSE |  | 2026-07-31 | 10.17
092 | B2 | 10596175 | Precision | Axioma | 20mm | 0.142 | 2026-05-19 | FALSE | Section 5 | 2026-04-28 | 2026-05-06 | 2026-05-20 | 2026-05-26 | TRUE | TRUE | 2026-09-08 | 2026-07-01 05:47 | 3.81
093 | A1 | 9897995 | Precision | Axioma | 20mm | 0.095 | 2026-05-26 | TRUE | Section 2 | 2026-04-22 | 2026-04-30 | 2026-05-15 | 2026-05-21 | FALSE | FALSE |  | 2026-07-01 10:56 | 11.769
094 | B2 | 10596238 | Precision | Axioma | 20mm | 0.086 | 2026-05-19 | TRUE | Section 5 | 2026-04-28 | 2026-05-06 | 2026-05-20 | 2026-05-26 | TRUE | TRUE | 2026-07-13 | 2026-07-01 05:47 | 0.082 | Faulty replaced twice
095 | A1 | 10172258 | Precision | Axioma | 20mm | 0.104 | 2026-05-26 | TRUE | Section 2 | 2026-04-22 | 2026-04-30 | 2026-05-15 | 2026-05-21 | FALSE | FALSE |  | 2026-07-01 16:45 | 2.952
096 | B2 | 9993247 | Precision | Axioma | 20mm | 0.086 | 2026-05-19 | TRUE | Section 5 | 2026-04-28 | 2026-05-06 | 2026-05-20 | 2026-05-26 | TRUE | TRUE | 2026-07-13 | 2026-07-01 15:47 | 0.086
097 | A1 | 10172250 | Precision | Axioma | 20mm | 0.082 | 2026-05-26 | TRUE | Section 2 | 2026-04-22 | 2026-04-30 | 2026-05-15 | 2026-05-21 | FALSE | FALSE |  | 2026-07-01 16:47 | 32.674
098 | B2 | 10172259 | Precision | Axioma | 20mm | 0.102 | 2026-05-19 | TRUE | Section 5 | 2026-04-28 | 2026-05-06 | 2026-05-20 | 2026-05-26 | FALSE | FALSE |  | 2026-07-01 15:47 | 4.172
099 | A1 | 10172261 | Precision | Axioma | 20mm | 0.101 | 2026-05-26 | TRUE | Section 2 | 2026-04-22 | 2026-04-30 | 2026-05-15 | 2026-05-21 | FALSE | FALSE |  | 2026-07-01 11:01 | 4.336
100 | B2 | 10172254 | Precision | Axioma | 20mm | 0.102 | 2026-05-19 | TRUE | Section 5 | 2026-04-28 | 2026-05-06 | 2026-05-20 | 2026-05-26 | FALSE | FALSE |  | 2026-07-01 07:55 | 4.3209
101 | A1 | 9897994 | Precision | Axioma | 20mm | 0.091 | 2026-05-26 | TRUE | Section 2 | 2026-04-22 | 2026-04-30 | 2026-05-15 | 2026-05-21 | FALSE | FALSE |  | 2026-07-01 16:15 | 9.712
102 | B2 | 10172264 | Precision | Axioma | 20mm | 0.105 | 2026-05-19 | TRUE | Section 5 | 2026-04-28 | 2026-05-06 | 2026-05-20 | 2026-05-26 | FALSE | FALSE |  | 2026-07-01 07:56 | 4.1758
103 | A1 | 10192047 | Precision | Axioma | 20mm | 0.097 | 2026-05-26 | TRUE | Section 2 | 2026-04-22 | 2026-04-30 | 2026-05-15 | 2026-05-21 | TRUE | TRUE | 2026-07-13 | 2026-07-01 16:15 | 0.097
104 | B3 |  | Precision | Axioma | 20mm |  |  | FALSE | Section 21 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06 | FALSE | FALSE
105 | A1 | 10596306 | Precision | Axioma | 20mm | 0.104 | 2026-05-26 | TRUE | Section 2 | 2026-04-22 | 2026-04-30 | 2026-05-15 | 2026-05-21 | TRUE | TRUE | 2026-07-03 | 2026-07-01 16:15 | 0.075 | Faulty replaced twice
106 | B3 |  | Precision | Axioma | 20mm |  |  | FALSE | Section 21 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06 | FALSE | FALSE
107 | A1 | 9898044 | Precision | Axioma | 20mm | 0.081 | 2026-05-26 | TRUE | Section 2 | 2026-04-22 | 2026-04-30 | 2026-05-15 | 2026-05-21 | FALSE | FALSE |  | 2026-07-01 16:52 | 20.81
108 | B3 |  | Precision | Axioma | 20mm |  |  | FALSE | Section 21 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06 | FALSE | FALSE
109 | A1 | 10192016 | Precision | Axioma | 20mm | 0.068 | 2026-04-30 | TRUE | Section 2 | 2026-04-22 | 2026-04-30 | 2026-05-15 | 2026-05-21 | TRUE | TRUE | 2026-07-03 | 2026-07-01 16:52 | 0.068
110 | B3 |  | Precision | Axioma | 20mm |  |  | FALSE | Section 21 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06 | FALSE | FALSE
111 | A1 | 9897906 | Precision | Axioma | 20mm | 0.068 | 2026-04-30 | TRUE | Section 2 | 2026-04-22 | 2026-04-30 | 2026-05-15 | 2026-05-21 | FALSE | FALSE |  | 2026-07-01 11:06 | 8.855
112 | B3 |  | Precision | Axioma | 20mm |  |  | FALSE | Section 21 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06 | FALSE | FALSE
113 | A1 | 9897997 | Precision | Axioma | 20mm | 0.091 | 2026-04-30 | TRUE | Section 1 | 2026-04-13 | 2026-04-20 | 2026-05-06 | 2026-05-12 | FALSE | FALSE |  | 2026-07-01 10:46 | 6.451
114 | B3 |  | Precision | Axioma | 20mm |  |  | FALSE | Section 21 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06 | FALSE | FALSE
115 | A1 | 9898005 | Precision | Axioma | 20mm | 0.093 | 2026-04-30 | TRUE | Section 1 | 2026-04-13 | 2026-04-20 | 2026-05-06 | 2026-05-12 | FALSE | FALSE |  | 2026-07-01 10:46 | 4.733
116 | B3 |  | Precision | Axioma | 20mm |  |  | FALSE | Section 21 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06 | FALSE | FALSE
117 | A1 | 9897913 | Precision | Axioma | 20mm | 0.082 | 2026-04-24 | TRUE | Section 1 | 2026-04-13 | 2026-04-20 | 2026-05-06 | 2026-05-12 | FALSE | FALSE |  | 2026-07-01 10:46 | 20.442
118 | B3 |  | Precision | Axioma | 20mm |  |  | FALSE | Section 21 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06 | FALSE | FALSE
119 | A1 | 9897993 | Precision | Axioma | 20mm | 0.223 | 2026-04-24 | TRUE | Section 1 | 2026-04-13 | 2026-04-20 | 2026-05-06 | 2026-05-12 | FALSE | FALSE |  | 2026-07-01 10:46 | 0.223
120 | B3 |  | Precision | Axioma | 20mm |  |  | FALSE | Section 22 | 2026-07-24 | 2026-07-31 | 2026-08-15 | 2026-08-21 | FALSE | FALSE
121 | A1 | 9897907 | Precision | Axioma | 20mm | 0.08 | 2026-04-24 | TRUE | Section 1 | 2026-04-13 | 2026-04-20 | 2026-05-06 | 2026-05-12 | FALSE | FALSE |  | 2026-07-01 10:46 | 7.593
122 | B3 |  | Precision | Axioma | 20mm |  |  | FALSE | Section 22 | 2026-07-24 | 2026-07-31 | 2026-08-15 | 2026-08-21 | FALSE | FALSE
123 | A1 | 9897911 | Precision | Axioma | 20mm | 0.071 | 2026-05-26 | TRUE | Section 1 | 2026-04-13 | 2026-04-20 | 2026-05-06 | 2026-05-12 | FALSE | FALSE |  | 2026-07-01 10:46 | 3.893
124 | B3 |  | Precision | Axioma | 20mm |  |  | FALSE | Section 22 | 2026-07-24 | 2026-07-31 | 2026-08-15 | 2026-08-21 | FALSE | FALSE
125 | A1 | 9993259 | Precision | Axioma | 20mm | 0.091 | 2026-05-26 | TRUE | Section 1 | 2026-04-13 | 2026-04-20 | 2026-05-06 | 2026-05-12 | TRUE | TRUE | 2026-07-03 | 2026-07-01 10:46 | 1.163
126 | B3 |  | Precision | Axioma | 20mm |  |  | FALSE | Section 22 | 2026-07-24 | 2026-07-31 | 2026-08-15 | 2026-08-21 | FALSE | FALSE
127 | A1 | 9897908 | Precision | Axioma | 20mm | 0.076 | 2026-05-26 | TRUE | Section 1 | 2026-04-13 | 2026-04-20 | 2026-05-06 | 2026-05-12 | FALSE | FALSE |  | 2026-07-01 10:46 | 22.7
128 | B3 |  | Precision | Axioma | 20mm |  |  | FALSE | Section 22 | 2026-07-24 | 2026-07-31 | 2026-08-15 | 2026-08-21 | FALSE | FALSE
129 | B3 |  | Precision | Axioma | 20mm |  |  | FALSE | Section 22 | 2026-07-24 | 2026-07-31 | 2026-08-15 | 2026-08-21 | FALSE | FALSE
130 | B3 |  | Precision | Axioma | 20mm |  |  | FALSE | Section 22 | 2026-07-24 | 2026-07-31 | 2026-08-15 | 2026-08-21 | FALSE | FALSE
131 | B3 |  | Precision | Axioma | 20mm |  |  | FALSE | Section 22 | 2026-07-24 | 2026-07-31 | 2026-08-15 | 2026-08-21 | FALSE | FALSE
132 | B3 |  | Precision | Axioma | 20mm |  |  | FALSE | Section 23 | 2026-08-08 | 2026-08-17 | 2026-08-31 | 2026-09-05 | FALSE | FALSE
133 | B3 |  | Precision | Axioma | 20mm |  |  | FALSE | Section 23 | 2026-08-08 | 2026-08-17 | 2026-08-31 | 2026-09-05 | FALSE | FALSE
134 | B3 |  | Precision | Axioma | 20mm |  |  | FALSE | Section 23 | 2026-08-08 | 2026-08-17 | 2026-08-31 | 2026-09-05 | FALSE | FALSE
135 | B3 |  | Precision | Axioma | 20mm |  |  | FALSE | Section 23 | 2026-08-08 | 2026-08-17 | 2026-08-31 | 2026-09-05 | FALSE | FALSE
136 | B3 |  | Precision | Axioma | 20mm |  |  | FALSE | Section 23 | 2026-08-08 | 2026-08-17 | 2026-08-31 | 2026-09-05 | FALSE | FALSE
137 | B3 |  | Precision | Axioma | 20mm |  |  | FALSE | Section 23 | 2026-08-08 | 2026-08-17 | 2026-08-31 | 2026-09-05 | FALSE | FALSE
138 | B3 |  | Precision | Axioma | 20mm |  |  | FALSE | Section 23 | 2026-08-08 | 2026-08-17 | 2026-08-31 | 2026-09-05 | FALSE | FALSE
139 | B3 |  | Precision | Axioma | 20mm |  |  | FALSE | Section 23 | 2026-08-08 | 2026-08-17 | 2026-08-31 | 2026-09-05 | FALSE | FALSE
140 | B3 |  | Precision | Axioma | 20mm |  |  | FALSE | Section 25 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06 | FALSE | FALSE
141 | A3 | 10596292 | Precision | Axioma | 20mm | 0.104 | 2026-08-24 | FALSE | Section 24 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21 | FALSE | FALSE
142 | B3 | [6 empty] | FALSE | Section 25 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06 | FALSE | FALSE
143 | A3 | 10596297 | Precision | Axioma | 20mm | 0.102 | 2026-08-24 | FALSE | Section 24 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21 | FALSE | FALSE
144 | B3 | [6 empty] | FALSE | Section 25 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06 | FALSE | FALSE
145 | A3 | 10596307 | Precision | Axioma | 20mm | 0.099 | 2026-08-24 | FALSE | Section 24 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21 | FALSE | FALSE
146 | B3 | 10596218 | Precision | Axioma | 20mm | 0.086 | 2026-08-24 | FALSE | Section 25 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06 | FALSE | FALSE
147 | A3 |  | Precision | Axioma | 20mm |  |  | FALSE | Section 24 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21 | FALSE | FALSE
148 | B3 | 10596272 | Precision | Axioma | 20mm | 0.084 | 2026-08-24 | FALSE | Section 25 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06 | FALSE | FALSE
149 | A3 |  | Precision | Axioma | 20mm |  |  | FALSE | Section 24 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21 | FALSE | FALSE
150 | B3 | 10596233 | Precision | Axioma | 20mm | 0.103 | 2026-08-24 | FALSE | Section 25 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06 | FALSE | FALSE
151 | A3 |  | Precision | Axioma | 20mm |  |  | FALSE | Section 24 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21 | FALSE | FALSE
152 | B3 | 10596254 | Precision | Axioma | 20mm | 0.091 | 2026-08-24 | FALSE | Section 25 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06 | FALSE | FALSE
153 | A3 |  | Precision | Axioma | 20mm |  |  | FALSE | Section 24 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21 | FALSE | FALSE
154 | A3 |  | Precision | Axioma | 20mm |  |  | FALSE | Section 24 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21 | FALSE | FALSE
155 | A3 | 10596377 | Precision | Axioma | 20mm | 0.079 | 2026-08-21 | TRUE | Section 16 | 2026-07-23 | 2026-07-30 | 2026-08-14 | 2026-08-20 | FALSE | FALSE
156 | A3 | 10596237 | Precision | Axioma | 20mm | 0.084 | 2026-08-21 | TRUE | Section 16 | 2026-07-23 | 2026-07-30 | 2026-08-14 | 2026-08-20 | FALSE | FALSE
157 | A3 | 10596229 | Precision | Axioma | 20mm | 0.104 | 2026-08-21 | TRUE | Section 16 | 2026-07-23 | 2026-07-30 | 2026-08-14 | 2026-08-20 | FALSE | FALSE
158 | A3 | 10596295 | Precision | Axioma | 20mm | 0.104 | 2026-08-21 | TRUE | Section 16 | 2026-07-23 | 2026-07-30 | 2026-08-14 | 2026-08-20 | FALSE | FALSE
159 | A3 | 10596246 | Precision | Axioma | 20mm | 0.083 | 2026-08-21 | TRUE | Section 16 | 2026-07-23 | 2026-07-30 | 2026-08-14 | 2026-08-20 | FALSE | FALSE
160 | A3 | 10596197 | Precision | Axioma | 20mm | 0.092 | 2026-08-21 | TRUE | Section 16 | 2026-07-23 | 2026-07-30 | 2026-08-14 | 2026-08-20 | FALSE | FALSE
161 | A3 | 10596299 | Precision | Axioma | 20mm | 0.104 | 2026-08-24 | TRUE | Section 16 | 2026-07-23 | 2026-07-30 | 2026-08-14 | 2026-08-20 | FALSE | FALSE
162 | A3 | 10596247 | Precision | Axioma | 20mm | 0.082 | 2026-08-24 | TRUE | Section 16 | 2026-07-23 | 2026-07-30 | 2026-08-14 | 2026-08-20 | FALSE | FALSE
163 | A3 | 54789034 | Kamstrup | FlowIQ2200 | 20mm | 0.153 | 2026-08-14 | TRUE | Section 15 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04 | FALSE | FALSE
164 | A3 | 54789038 | Kamstrup | FlowIQ2200 | 20mm | 0.152 | 2026-08-14 | TRUE | Section 15 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04 | FALSE | FALSE
165 | A3 | 54789042 | Kamstrup | FlowIQ2200 | 20mm | 0.152 | 2026-08-14 | TRUE | Section 15 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04 | FALSE | FALSE
166 | A3 | 54789045 | Kamstrup | FlowIQ2200 | 20mm | 0.12 | 2026-08-14 | TRUE | Section 15 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04 | FALSE | FALSE
167 | A3 | 54789077 | Kamstrup | FlowIQ2200 | 20mm | 0.117 | 2026-08-14 | TRUE | Section 15 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04 | FALSE | FALSE
168 | A3 | 54789040 | Kamstrup | FlowIQ2200 | 20mm | 0.151 | 2026-08-14 | TRUE | Section 15 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04 | FALSE | FALSE
169 | A3 |  | Precision | Axioma | 20mm |  |  | FALSE | Section 15 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04 | FALSE | FALSE
170 | A2 | 54789044 | Kamstrup | FlowIQ2200 | 20mm | 0.121 | 2026-08-14 | TRUE | Section 8 | 2026-08-04 | 2026-08-12 | 2026-08-26 | 2026-09-01 | FALSE | FALSE
171 | A2 | 54789037 | Kamstrup | FlowIQ2200 | 20mm | 0.152 | 2026-08-14 | TRUE | Section 8 | 2026-08-04 | 2026-08-12 | 2026-08-26 | 2026-09-01 | FALSE | FALSE
172 | A2 | 54789036 | Kamstrup | FlowIQ2200 | 20mm | 0.152 | 2026-08-14 | TRUE | Section 8 | 2026-08-04 | 2026-08-12 | 2026-08-26 | 2026-09-01 | FALSE | FALSE
173 | A2 | 54789041 | Kamstrup | FlowIQ2200 | 20mm | 0.152 | 2026-08-14 | TRUE | Section 8 | 2026-08-04 | 2026-08-12 | 2026-08-26 | 2026-09-01 | FALSE | FALSE
174 | A2 | 10191967 | Precision | Axioma | 20mm | 0.067 | 2026-07-16 | TRUE | Section 8 | 2026-08-04 | 2026-08-12 | 2026-08-26 | 2026-09-01 | FALSE | FALSE
175 | A2 | 54554431 | Kamstrup | FlowIQ2200 | 20mm | 0.161 | 2026-07-16 | TRUE | Section 7 | 2026-07-21 | 2026-07-28 | 2026-08-12 | 2026-08-18 | FALSE | FALSE
176 | A2 | 10192063 | Precision | Axioma | 20mm | 0.089 | 2026-07-16 | TRUE | Section 7 | 2026-07-21 | 2026-07-28 | 2026-08-12 | 2026-08-18 | FALSE | FALSE
177 | A2 | 10192057 | Precision | Axioma | 20mm | 0.092 | 2026-07-16 | TRUE | Section 7 | 2026-07-21 | 2026-07-28 | 2026-08-12 | 2026-08-18 | FALSE | FALSE
178 | A2 | 10192056 | Precision | Axioma | 20mm | 0.09 | 2026-07-16 | TRUE | Section 7 | 2026-07-21 | 2026-07-28 | 2026-08-12 | 2026-08-18 | FALSE | FALSE
179 | A2 | 10192055 | Precision | Axioma | 20mm | 0.089 | 2026-07-16 | TRUE | Section 7 | 2026-07-21 | 2026-07-28 | 2026-08-12 | 2026-08-18 | FALSE | FALSE
180 | A2 | 10191968 | Precision | Axioma | 20mm | 0.069 | 2026-07-16 | TRUE | Section 7 | 2026-07-21 | 2026-07-28 | 2026-08-12 | 2026-08-18 | FALSE | FALSE
181 | A2 | 54789047 | Kamstrup | FlowIQ2200 | 20mm | 0.12 | 2026-08-14 | TRUE | Section 7 | 2026-07-21 | 2026-07-28 | 2026-08-12 | 2026-08-18 | FALSE | FALSE
182 | A2 | 54789035 | Kamstrup | FlowIQ2200 | 20mm | 0.152 | 2026-08-14 | TRUE | Section 7 | 2026-07-21 | 2026-07-28 | 2026-08-12 | 2026-08-18 | FALSE | FALSE
183 | A2 | 10596188 | Precision | Axioma | 20mm | 0.075 | 2026-06-13 | FALSE | Section 6 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04 | TRUE | TRUE | 2026-09-08
184 | A2 | 10192025 | Precision | Axioma | 20mm | 0.067 | 2026-06-13 | TRUE | Section 6 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04 | FALSE | FALSE
185 | A2 | 10596176 | Precision | Axioma | 20mm | 0.067 | 2026-06-13 | FALSE | Section 6 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04 | TRUE | TRUE | 2026-09-14
186 | A2 | 10596240 | Precision | Axioma | 20mm | 0.106 | 2026-06-13 | TRUE | Section 6 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04 | TRUE | TRUE | 2026-08-20
187 | A2 | 10596298 | Precision | Axioma | 20mm | 0.104 | 2026-06-13 | TRUE | Section 6 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04 | TRUE | TRUE | 2026-08-20
188 | A2 | 10596305 | Precision | Axioma | 20mm | 0.141 | 2026-06-13 | TRUE | Section 6 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04 | TRUE | TRUE | 2026-09-08
189 | A2 | 10192205 | Precision | Axioma | 20mm | 0.087 | 2026-06-13 | TRUE | Section 6 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04 | FALSE | FALSE
190 | A2 | 10192011 | Precision | Axioma | 20mm | 0.069 | 2026-06-13 | TRUE | Section 6 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04 | FALSE | FALSE
Lifestyle Cetre Meter 1 | A1 | 10228692 | Precision | Axioma | 25mm | 0.094 | 2026-05-29 | TRUE | Section 2 | 2026-04-22 | 2026-04-30 | 2026-05-15 | 2026-05-21 | FALSE | FALSE
Lifestyle Cetre Meter 2 | A1 | 9279142 | Precision | Axioma | 32mm | 0.131 | 2026-04-24 | TRUE | Section 2 | 2026-04-22 | 2026-04-30 | 2026-05-15 | 2026-05-21 | FALSE | FALSE

## Aprt Elec
Apartment Block | Stand | Elect meter serial | Parent Meter | Parent DB | AMR installed
Block A | Aprt BL A/00/001 | 87819319 | 87818883 | DB-GA-1 | TRUE
Block A | Aprt BL A/00/002 | 87819358 | 87818883 | DB-GA-1 | TRUE
Block A | Aprt BL A/00/003 | 87819167 | 87818883 | DB-GA-1 | TRUE
Block A | Aprt BL A/00/004 | 87819318 | 87818883 | DB-GA-1 | TRUE
Block A | Aprt BL A/00/005 | 87819205 | 87818883 | DB-GA-1 | TRUE
Block A | Aprt BL A/00/006 | 87819238 | 87818883 | DB-GA-1 | TRUE
Block A | Aprt BL A/00/007 | 87819315 | 87818883 | DB-GA-1 | TRUE
Block A | Aprt BL A/00/008 | 87819411 | 87818883 | DB-GA-1 | TRUE
Block A | Aprt BL A/00/009 | 87819166 | 87818883 | DB-GA-1 | TRUE
Block A | Aprt BL A/00/010 | 87819142 | 87818883 | DB-GA-1 | TRUE
Block A | Aprt BL A/00/011 | 87819179 | 87818883 | DB-GA-1 | TRUE
Block A | Aprt BL A/00/012 | 87819139 | 87818883 | DB-GA-1 | TRUE
Block A | Aprt BL A/00/013 | 87819184 | 87818883 | DB-GA-1 | TRUE
Block A | Aprt BL A/00/014 | 87819310 | 87818883 | DB-GA-1 | TRUE
Block A | Aprt BL A/00/015 | 87819234 | 87818877 | DB-GA-2 | TRUE
Block A | Aprt BL A/00/016 | 87819161 | 87818877 | DB-GA-2 | TRUE
Block A | Aprt BL A/00/017 | 87819211 | 87818877 | DB-GA-2 | TRUE
Block A | Aprt BL A/00/018 | 87819181 | 87818877 | DB-GA-2 | TRUE
Block A | Aprt BL A/00/019 | 87819386 | 87818877 | DB-GA-2 | TRUE
Block A | Aprt BL A/00/020 | 87819204 | 87818877 | DB-GA-2 | TRUE
Block A | Aprt BL A/00/023 | 87819350 | 87818878 | DB-GA-3 | TRUE
Block A | Aprt BL A/00/024 | 87819087 | 87818878 | DB-GA-3 | TRUE
Block A | Aprt BL A/00/025 | 87819144 | 87818878 | DB-GA-3 | TRUE
Block A | Aprt BL A/00/026 | 87819412 | 87818878 | DB-GA-3 | TRUE
Block A | Aprt BL A/00/027 | 87819221 | 87818878 | DB-GA-3 | TRUE
Block A | Aprt BL A/00/028 | 87819226 | 87818878 | DB-GA-3 | TRUE
Block A | Aprt BL A/00/029 | 87819292 | 87819009 | DB-GA-4 | TRUE
Block A | Aprt BL A/00/030 | 87819437 | 87819009 | DB-GA-4 | TRUE
Block A | Aprt BL A/00/031 | 87819109 | 87819009 | DB-GA-4 | TRUE
Block A | Aprt BL A/00/032 | 87819061 | 87819009 | DB-GA-4 | TRUE
Block A | Aprt BL A/00/033 | 87819274 | 87819009 | DB-GA-4 | TRUE
Block A | Aprt BL A/00/034 | 87819197 | 87819009 | DB-GA-4 | TRUE
Block A | Aprt BL A/00/035 | 87819106 | 87819009 | DB-GA-4 | TRUE
Block A | Aprt BL A/00/036 | 87819402 | 87819009 | DB-GA-4 | TRUE
Block A | Aprt BL A/00/037 | 87819083 | 87819009 | DB-GA-4 | TRUE
Block A | Aprt BL A/00/038 | 87819200 | 87819009 | DB-GA-4 | TRUE
Block A | Aprt BL A/00/039 | 87819217 | 87819009 | DB-GA-4 | TRUE
Block A | Aprt BL A/00/040 | 87819092 | 87819009 | DB-GA-4 | TRUE
Block A | Aprt BL A/00/041 | 87819149 | 87819009 | DB-GA-4 | TRUE
Block A | Aprt BL A/00/042 | 87819138 | 87819009 | DB-GA-4 | TRUE
Block A | Aprt BL A/01/101 | 87819117 | 87819003 | DB-1A-1 | TRUE
Block A | Aprt BL A/01/102 | 87819141 | 87819003 | DB-1A-1 | TRUE
Block A | Aprt BL A/01/103 | 87819185 | 87819003 | DB-1A-1 | TRUE
Block A | Aprt BL A/01/104 | 87819180 | 87819003 | DB-1A-1 | TRUE
Block A | Aprt BL A/01/105 | 87819224 | 87819003 | DB-1A-1 | TRUE
Block A | Aprt BL A/01/106 | 87819190 | 87819003 | DB-1A-1 | TRUE
Block A | Aprt BL A/01/107 | 87819173 | 87819003 | DB-1A-1 | TRUE
Block A | Aprt BL A/01/108 | 87819084 | 87819003 | DB-1A-1 | TRUE
Block A | Aprt BL A/01/109 | 87819354 | 87819003 | DB-1A-1 | TRUE
Block A | Aprt BL A/01/110 | 87819193 | 87819003 | DB-1A-1 | TRUE
Block A | Aprt BL A/01/111 | 87819330 | 87819003 | DB-1A-1 | TRUE
Block A | Aprt BL A/01/112 | 87819202 | 87819003 | DB-1A-1 | TRUE
Block A | Aprt BL A/01/113 | 87819215 | 87819003 | DB-1A-1 | TRUE
Block A | Aprt BL A/01/114 | 87819145 | 87819003 | DB-1A-1 | TRUE
Block A | Aprt BL A/01/115 | 87819262 | 87819002 | DB-1A-2 | TRUE
Block A | Aprt BL A/01/116 | 87819291 | 87819002 | DB-1A-2 | TRUE
Block A | Aprt BL A/01/117 | 87819267 | 87819002 | DB-1A-2 | TRUE
Block A | Aprt BL A/01/118 | 87819366 | 87819002 | DB-1A-2 | TRUE
Block A | Aprt BL A/01/119 | 87819058 | 87819002 | DB-1A-2 | TRUE
Block A | Aprt BL A/01/120 | 87819208 | 87819002 | DB-1A-2 | TRUE
Block A | Aprt BL A/01/121 | 87819163 | 87819002 | DB-1A-2 | TRUE
Block A | Aprt BL A/01/122 | 87819107 | 87819002 | DB-1A-2 | TRUE
Block A | Aprt BL A/01/123 | 87819121 | 87818863 | DB-1A-3 | TRUE
Block A | Aprt BL A/01/124 | 87819220 | 87818863 | DB-1A-3 | TRUE
Block A | Aprt BL A/01/125 | 87819459 | 87818863 | DB-1A-3 | TRUE
Block A | Aprt BL A/01/126 | 87819191 | 87818863 | DB-1A-3 | TRUE
Block A | Aprt BL A/01/127 | 87819339 | 87818863 | DB-1A-3 | TRUE
Block A | Aprt BL A/01/128 | 87819239 | 87818863 | DB-1A-3 | TRUE
Block A | Aprt BL A/01/129 | 87819230 | 87819008 | DB-1A-4 | TRUE
Block A | Aprt BL A/01/130 | 87819116 | 87819008 | DB-1A-4 | TRUE
Block A | Aprt BL A/01/131 | 87819406 | 87819008 | DB-1A-4 | TRUE
Block A | Aprt BL A/01/132 | 87819271 | 87819008 | DB-1A-4 | TRUE
Block A | Aprt BL A/01/133 | 87819465 | 87819008 | DB-1A-4 | TRUE
Block A | Aprt BL A/01/134 | 87819414 | 87819008 | DB-1A-4 | TRUE
Block A | Aprt BL A/01/135 | 87819246 | 87819008 | DB-1A-4 | TRUE
Block A | Aprt BL A/01/136 | 87819407 | 87819008 | DB-1A-4 | TRUE
Block A | Aprt BL A/01/137 | 87819225 | 87819008 | DB-1A-4 | TRUE
Block A | Aprt BL A/01/138 | 87778565 | 87819008 | DB-1A-4 | TRUE
Block A | Aprt BL A/01/139 | 87819334 | 87819008 | DB-1A-4 | TRUE
Block A | Aprt BL A/01/140 | 87819064 | 87819008 | DB-1A-4 | TRUE
Block A | Aprt BL A/01/141 | 87819110 | 87819008 | DB-1A-4 | TRUE
Block A | Aprt BL A/01/142 | 87819470 | 87819008 | DB-1A-4 | TRUE
Block A | Aprt BL A/02/201 | 87819210 | 87818879 | DB-2A-1 | TRUE
Block A | Aprt BL A/02/202 | 87819265 | 87818879 | DB-2A-1 | TRUE
Block A | Aprt BL A/02/203 | 87819212 | 87818879 | DB-2A-1 | TRUE
Block A | Aprt BL A/02/204 | 87819155 | 87818879 | DB-2A-1 | TRUE
Block A | Aprt BL A/02/205 | 87819137 | 87818879 | DB-2A-1 | TRUE
Block A | Aprt BL A/02/206 | 87819158 | 87818879 | DB-2A-1 | TRUE
Block A | Aprt BL A/02/207 | 87819088 | 87818879 | DB-2A-1 | TRUE
Block A | Aprt BL A/02/208 | 87819156 | 87818879 | DB-2A-1 | TRUE
Block A | Aprt BL A/02/209 | 87819258 | 87818879 | DB-2A-1 | TRUE
Block A | Aprt BL A/02/210 | 87819135 | 87818879 | DB-2A-1 | TRUE
Block A | Aprt BL A/02/211 | 87819207 | 87818879 | DB-2A-1 | TRUE
Block A | Aprt BL A/02/212 | 87819344 | 87818879 | DB-2A-1 | TRUE
Block A | Aprt BL A/02/213 | 87819157 | 87818879 | DB-2A-1 | TRUE
Block A | Aprt BL A/02/214 | 87819206 | 87818879 | DB-2A-1 | TRUE
Block A | Aprt BL A/02/215 | 87819182 | 87819007 | DB-2A-2 | TRUE
Block A | Aprt BL A/02/216 | 87819183 | 87819007 | DB-2A-2 | TRUE
Block A | Aprt BL A/02/217 | 87819203 | 87819007 | DB-2A-2 | TRUE
Block A | Aprt BL A/02/218 | 87819085 | 87819007 | DB-2A-2 | TRUE
Block A | Aprt BL A/02/219 | 87819209 | 87819007 | DB-2A-2 | TRUE
Block A | Aprt BL A/02/220 | 87819454 | 87819007 | DB-2A-2 | TRUE
Block A | Aprt BL A/02/221 | 87819362 | 87819007 | DB-2A-2 | TRUE
Block A | Aprt BL A/02/222 | 87819115 | 87819007 | DB-2A-2 | TRUE
Block A | Aprt BL A/02/223 | 87819382 | 87819005 | DB-2A-3 | TRUE
Block A | Aprt BL A/02/224 | 87819169 | 87819005 | DB-2A-3 | TRUE
Block A | Aprt BL A/02/225 | 87819263 | 87819005 | DB-2A-3 | TRUE
Block A | Aprt BL A/02/226 | 87819298 | 87819005 | DB-2A-3 | TRUE
Block A | Aprt BL A/02/227 | 87819241 | 87819005 | DB-2A-3 | TRUE
Block A | Aprt BL A/02/228 | 87778578 | 87819005 | DB-2A-3 | TRUE
Block A | Aprt BL A/02/229 | 87819165 | 87818959 | DB-2A-4 | TRUE
Block A | Aprt BL A/02/230 | 87819201 | 87818959 | DB-2A-4 | TRUE
Block A | Aprt BL A/02/231 | 87778588 | 87818959 | DB-2A-4 | TRUE
Block A | Aprt BL A/02/232 | 87819196 | 87818959 | DB-2A-4 | TRUE
Block A | Aprt BL A/02/233 | 87819062 | 87818959 | DB-2A-4 | TRUE
Block A | Aprt BL A/02/234 | 87819130 | 87818959 | DB-2A-4 | TRUE
Block A | Aprt BL A/02/235 | 87819247 | 87818959 | DB-2A-4 | TRUE
Block A | Aprt BL A/02/236 | 87819287 | 87818959 | DB-2A-4 | TRUE
Block A | Aprt BL A/02/237 | 87819113 | 87818959 | DB-2A-4 | TRUE
Block A | Aprt BL A/02/238 | 87778353 | 87818959 | DB-2A-4 | TRUE
Block A | Aprt BL A/02/239 | 87778563 | 87818959 | DB-2A-4 | TRUE
Block A | Aprt BL A/02/240 | 87819060 | 87818959 | DB-2A-4 | TRUE
Block A | Aprt BL A/02/241 | 87819214 | 87818959 | DB-2A-4 | TRUE
Block A | Aprt BL A/02/242 | 87819458 | 87818959 | DB-2A-4 | TRUE
Block A | Block A Bulk Meter | 83013890 | 82929684 | MS2 | TRUE
Block A | DB-GA-1 | 87818883 | 83013890 | Block A Bulk Meter | TRUE
Block A | DB-GA-2 | 87818877 | 83013890 | Block A Bulk Meter | TRUE
Block A | DB-GA-3 | 87818878 | 83013890 | Block A Bulk Meter | TRUE
Block A | DB-GA-4 | 87819009 | 83013890 | Block A Bulk Meter | TRUE
Block A | DB-1A-1 | 87819003 | 83013890 | Block A Bulk Meter | TRUE
Block A | DB-1A-2 | 87819002 | 83013890 | Block A Bulk Meter | TRUE
Block A | DB-1A-3 | 87818863 | 83013890 | Block A Bulk Meter | TRUE
Block A | DB-1A-4 | 87819008 | 83013890 | Block A Bulk Meter | TRUE
Block A | DB-2A-1 | 87818879 | 83013890 | Block A Bulk Meter | TRUE
Block A | DB-2A-2 | 87819007 | 83013890 | Block A Bulk Meter | TRUE
Block A | DB-2A-3 | 87819005 | 83013890 | Block A Bulk Meter | TRUE
Block A | DB-2A-4 | 87818959 | 83013890 | Block A Bulk Meter | TRUE
Block A | DB-Plant A | 87819001 | 83013890 | Block A Bulk Meter | TRUE
Block A | DB-UPS A | 87818957 | 83013890 | Block A Bulk Meter | TRUE
Block A | Lift 1 | 87818870 | 83013890 | Block A Bulk Meter | TRUE
Block A | Lift 2 | 87819004 | 83013890 | Block A Bulk Meter | TRUE
Block B | Aprt BL B/00/001 | 90007625 | 87818880 | DB-GB-4 | TRUE
Block B | Aprt BL B/00/002 | 90007633 | 87818880 | DB-GB-4 | TRUE
Block B | Aprt BL B/00/003 | 90008131 | 87818880 | DB-GB-4 | TRUE
Block B | Aprt BL B/00/004 | 90007593 | 87818880 | DB-GB-4 | TRUE
Block B | Aprt BL B/00/005 | 90008126 | 87818880 | DB-GB-4 | TRUE
Block B | Aprt BL B/00/006 | 90008097 | 87818880 | DB-GB-4 | TRUE
Block B | Aprt BL B/00/007 | 90007605 | 87818880 | DB-GB-4 | TRUE
Block B | Aprt BL B/00/008 | 90008115 | 87818880 | DB-GB-4 | TRUE
Block B | Aprt BL B/00/009 | 90008139 | 87818880 | DB-GB-4 | TRUE
Block B | Aprt BL B/00/010 | 90007629 | 87818880 | DB-GB-4 | TRUE
Block B | Aprt BL B/00/011 | 90008121 | 87818880 | DB-GB-4 | TRUE
Block B | Aprt BL B/00/012 | 90008135 | 87818880 | DB-GB-4 | TRUE
Block B | Aprt BL B/00/013 | 90008078 | 87818880 | DB-GB-4 | TRUE
Block B | Aprt BL B/00/014 | 90008107 | 87818880 | DB-GB-4 | TRUE
Block B | Aprt BL B/00/015 | 90008029 | 87819000 | DB-1B-3 | TRUE
Block B | Aprt BL B/00/016 | 90007981 | 87819000 | DB-1B-3 | TRUE
Block B | Aprt BL B/00/017 | 90008000 | 87819000 | DB-1B-3 | TRUE
Block B | Aprt BL B/00/018 | 90008003 | 87819000 | DB-1B-3 | TRUE
Block B | Aprt BL B/00/019 | 90007995 | 87819000 | DB-1B-3 | TRUE
Block B | Aprt BL B/00/020 | 90008011 | 87819000 | DB-1B-3 | TRUE
Block B | Aprt BL B/00/021 | 90008123 | 87818875 | DB-GB-2 | TRUE
Block B | Aprt BL B/00/022 | 90008043 | 87818875 | DB-GB-2 | TRUE
Block B | Aprt BL B/00/023 | 90007994 | 87818875 | DB-GB-2 | TRUE
Block B | Aprt BL B/00/024 | 90008102 | 87818875 | DB-GB-2 | TRUE
Block B | Aprt BL B/00/025 | 90007980 | 87818875 | DB-GB-2 | TRUE
Block B | Aprt BL B/00/026 | 90008001 | 87818875 | DB-GB-2 | TRUE
Block B | Aprt BL B/00/027 | 90007998 | 87818875 | DB-GB-2 | TRUE
Block B | Aprt BL B/00/028 | 90008094 | 87818875 | DB-GB-2 | TRUE
Block B | Aprt BL B/00/029 | 90008276 | 87818865 | DB-GB-1 | TRUE
Block B | Aprt BL B/00/030 | 90008144 | 87818865 | DB-GB-1 | TRUE
Block B | Aprt BL B/00/031 | 90008153 | 87818865 | DB-GB-1 | TRUE
Block B | Aprt BL B/00/032 | 90008258 | 87818865 | DB-GB-1 | TRUE
Block B | Aprt BL B/00/033 | 90008032 | 87818865 | DB-GB-1 | TRUE
Block B | Aprt BL B/00/034 | 90008188 | 87818865 | DB-GB-1 | TRUE
Block B | Aprt BL B/00/035 | 90008168 | 87818865 | DB-GB-1 | TRUE
Block B | Aprt BL B/00/036 | 90008196 | 87818865 | DB-GB-1 | TRUE
Block B | Aprt BL B/00/037 | 90008204 | 87818865 | DB-GB-1 | TRUE
Block B | Aprt BL B/00/038 | 90008283 | 87818865 | DB-GB-1 | TRUE
Block B | Aprt BL B/00/039 | 90008159 | 87818865 | DB-GB-1 | TRUE
Block B | Aprt BL B/00/040 | 90008156 | 87818865 | DB-GB-1 | TRUE
Block B | Aprt BL B/00/041 | 90008155 | 87818865 | DB-GB-1 | TRUE
Block B | Aprt BL B/00/042 | 90007997 | 87818865 | DB-GB-1 | TRUE
Block B | Aprt BL B/01/101 | 90008120 | 87818869 | DB-1B-4 | TRUE
Block B | Aprt BL B/01/102 | 90008091 | 87818869 | DB-1B-4 | TRUE
Block B | Aprt BL B/01/103 | 90007986 | 87818869 | DB-1B-4 | TRUE
Block B | Aprt BL B/01/104 | 90008082 | 87818869 | DB-1B-4 | TRUE
Block B | Aprt BL B/01/105 | 90008073 | 87818869 | DB-1B-4 | TRUE
Block B | Aprt BL B/01/106 | 90008054 | 87818869 | DB-1B-4 | TRUE
Block B | Aprt BL B/01/107 | 90007601 | 87818869 | DB-1B-4 | TRUE
Block B | Aprt BL B/01/108 | 90008087 | 87818869 | DB-1B-4 | TRUE
Block B | Aprt BL B/01/109 | 90008118 | 87818869 | DB-1B-4 | TRUE
Block B | Aprt BL B/01/110 | 90008026 | 87818869 | DB-1B-4 | TRUE
Block B | Aprt BL B/01/111 | 90008122 | 87818869 | DB-1B-4 | TRUE
Block B | Aprt BL B/01/112 | 90008034 | 87818869 | DB-1B-4 | TRUE
Block B | Aprt BL B/01/113 | 90007609 | 87818869 | DB-1B-4 | TRUE
Block B | Aprt BL B/01/114 | 90008039 | 87818869 | DB-1B-4 | TRUE
Block B | Aprt BL B/01/115 | 90008009 | 87818876 | DB-1B-3 | TRUE
Block B | Aprt BL B/01/116 | 90007991 | 87818876 | DB-1B-3 | TRUE
Block B | Aprt BL B/01/117 | 90008152 | 87818876 | DB-1B-3 | TRUE
Block B | Aprt BL B/01/118 | 90007990 | 87818876 | DB-1B-3 | TRUE
Block B | Aprt BL B/01/119 | 90008014 | 87818876 | DB-1B-3 | TRUE
Block B | Aprt BL B/01/120 | 90008031 | 87818876 | DB-1B-3 | TRUE
Block B | Aprt BL B/01/121 | 90008027 | 87818872 | DB-1B-2 | TRUE
Block B | Aprt BL B/01/122 | 90008018 | 87818872 | DB-1B-2 | TRUE
Block B | Aprt BL B/01/123 | 90008021 | 87818872 | DB-1B-2 | TRUE
Block B | Aprt BL B/01/124 | 90007985 | 87818872 | DB-1B-2 | TRUE
Block B | Aprt BL B/01/125 | 90008028 | 87818872 | DB-1B-2 | TRUE
Block B | Aprt BL B/01/126 | 90008035 | 87818872 | DB-1B-2 | TRUE
Block B | Aprt BL B/01/127 | 90008025 | 87818872 | DB-1B-2 | TRUE
Block B | Aprt BL B/01/128 | 90008002 | 87818872 | DB-1B-2 | TRUE
Block B | Aprt BL B/01/129 | 90008007 | 87818868 | DB-1B-1 | TRUE
Block B | Aprt BL B/01/130 | 90008172 | 87818868 | DB-1B-1 | TRUE
Block B | Aprt BL B/01/131 | 90008181 | 87818868 | DB-1B-1 | TRUE
Block B | Aprt BL B/01/132 | 90008164 | 87818868 | DB-1B-1 | TRUE
Block B | Aprt BL B/01/133 | 90008234 | 87818868 | DB-1B-1 | TRUE
Block B | Aprt BL B/01/134 | 90008229 | 87818868 | DB-1B-1 | TRUE
Block B | Aprt BL B/01/135 | 90008022 | 87818868 | DB-1B-1 | TRUE
Block B | Aprt BL B/01/136 | 90008024 | 87818868 | DB-1B-1 | TRUE
Block B | Aprt BL B/01/137 | 90008282 | 87818868 | DB-1B-1 | TRUE
Block B | Aprt BL B/01/138 | 90008233 | 87818868 | DB-1B-1 | TRUE
Block B | Aprt BL B/01/139 | 90008252 | 87818868 | DB-1B-1 | TRUE
Block B | Aprt BL B/01/140 | 90008004 | 87818868 | DB-1B-1 | TRUE
Block B | Aprt BL B/01/141 | 90008180 | 87818868 | DB-1B-1 | TRUE
Block B | Aprt BL B/01/142 | 90008259 | 87818868 | DB-1B-1 | TRUE
Block B | Aprt BL B/02/201 | 90008049 | 87818948 | DB-2B-4 | TRUE
Block B | Aprt BL B/02/202 | 90008050 | 87818948 | DB-2B-4 | TRUE
Block B | Aprt BL B/02/203 | 90008099 | 87818948 | DB-2B-4 | TRUE
Block B | Aprt BL B/02/204 | 90008083 | 87818948 | DB-2B-4 | TRUE
Block B | Aprt BL B/02/205 | 90008052 | 87818948 | DB-2B-4 | TRUE
Block B | Aprt BL B/02/206 | 90008074 | 87818948 | DB-2B-4 | TRUE
Block B | Aprt BL B/02/207 | 90008048 | 87818948 | DB-2B-4 | TRUE
Block B | Aprt BL B/02/208 | 90008127 | 87818948 | DB-2B-4 | TRUE
Block B | Aprt BL B/02/209 | 90008098 | 87818948 | DB-2B-4 | TRUE
Block B | Aprt BL B/02/210 | 90007538 | 87818948 | DB-2B-4 | TRUE
Block B | Aprt BL B/02/211 | 90008111 | 87818948 | DB-2B-4 | TRUE
Block B | Aprt BL B/02/212 | 90008096 | 87818948 | DB-2B-4 | TRUE
Block B | Aprt BL B/02/213 | 90008053 | 87818948 | DB-2B-4 | TRUE
Block B | Aprt BL B/02/214 | 90008103 | 87818948 | DB-2B-4 | TRUE
Block B | Aprt BL B/02/215 | 90008008 | 87819013 | DB-2B-3 | TRUE
Block B | Aprt BL B/02/216 | 90008019 | 87819013 | DB-2B-3 | TRUE
Block B | Aprt BL B/02/217 | 90008023 | 87819013 | DB-2B-3 | TRUE
Block B | Aprt BL B/02/218 | 90007982 | 87819013 | DB-2B-3 | TRUE
Block B | Aprt BL B/02/219 | 90008146 | 87819013 | DB-2B-3 | TRUE
Block B | Aprt BL B/02/220 | 90008192 | 87819013 | DB-2B-3 | TRUE
Block B | Aprt BL B/02/221 | 90008030 | 87818955 | DB-2B-2 | TRUE
Block B | Aprt BL B/02/222 | 90008033 | 87818955 | DB-2B-2 | TRUE
Block B | Aprt BL B/02/223 | 90008005 | 87818955 | DB-2B-2 | TRUE
Block B | Aprt BL B/02/224 | 90008157 | 87818955 | DB-2B-2 | TRUE
Block B | Aprt BL B/02/225 | 90008165 | 87818955 | DB-2B-2 | TRUE
Block B | Aprt BL B/02/226 | 90007984 | 87818955 | DB-2B-2 | TRUE
Block B | Aprt BL B/02/227 | 90008015 | 87818955 | DB-2B-2 | TRUE
Block B | Aprt BL B/02/228 | 90008205 | 87818955 | DB-2B-2 | TRUE
Block B | Aprt BL B/02/229 | 90008235 | 87818874 | DB-2B-1 | TRUE
Block B | Aprt BL B/02/230 | 90008281 | 87818874 | DB-2B-1 | TRUE
Block B | Aprt BL B/02/231 | 90008006 | 87818874 | DB-2B-1 | TRUE
Block B | Aprt BL B/02/232 | 90008141 | 87818874 | DB-2B-1 | TRUE
Block B | Aprt BL B/02/233 | 90008228 | 87818874 | DB-2B-1 | TRUE
Block B | Aprt BL B/02/234 | 90008189 | 87818874 | DB-2B-1 | TRUE
Block B | Aprt BL B/02/235 | 90008257 | 87818874 | DB-2B-1 | TRUE
Block B | Aprt BL B/02/236 | 90008158 | 87818874 | DB-2B-1 | TRUE
Block B | Aprt BL B/02/237 | 90008176 | 87818874 | DB-2B-1 | TRUE
Block B | Aprt BL B/02/238 | 90008010 | 87818874 | DB-2B-1 | TRUE
Block B | Aprt BL B/02/239 | 90008200 | 87818874 | DB-2B-1 | TRUE
Block B | Aprt BL B/02/240 | 90008177 | 87818874 | DB-2B-1 | TRUE
Block B | Aprt BL B/02/241 | 90008140 | 87818874 | DB-2B-1 | TRUE
Block B | Aprt BL B/02/242 | 90008178 | 87818874 | DB-2B-1 | TRUE
Block B | Block B Bulk Meter | 83013891 | 71205556 | MS3 | TRUE
Block B | DB-GB-1 | 87818865 | 83013891 | Block B Bulk Meter | TRUE
Block B | DB-GB-2 | 87818875 | 83013891 | Block B Bulk Meter | TRUE
Block B | DB-GB-3 | 87819000 | 83013891 | Block B Bulk Meter | TRUE
Block B | DB-GB-4 | 87818880 | 83013891 | Block B Bulk Meter | TRUE
Block B | DB-1B-1 | 87818868 | 83013891 | Block B Bulk Meter | TRUE
Block B | DB-1B-2 | 87818872 | 83013891 | Block B Bulk Meter | TRUE
Block B | DB-1B-3 | 87818876 | 83013891 | Block B Bulk Meter | TRUE
Block B | DB-1B-4 | 87818869 | 83013891 | Block B Bulk Meter | TRUE
Block B | DB-2B-1 | 87818874 | 83013891 | Block B Bulk Meter | TRUE
Block B | DB-2B-2 | 87818955 | 83013891 | Block B Bulk Meter | TRUE
Block B | DB-2B-3 | 87819013 | 83013891 | Block B Bulk Meter | TRUE
Block B | DB-2B-4 | 87818948 | 83013891 | Block B Bulk Meter | TRUE
Block B | DB-Plant B | 87818867 | 83013891 | Block B Bulk Meter | TRUE
Block B | DB-UPS B | 87818882 | 83013891 | Block B Bulk Meter | TRUE
Block B | Lift 1 | 87818999 | 83013891 | Block B Bulk Meter | TRUE
Block B | Lift 2 | 87818933 | 83013891 | Block B Bulk Meter | TRUE

## Aprt Water
Apartment Block | Stand | Cold water Serial | Hot water serial | AMR installed
Block A | Aprt BL A/00/001 | 1012-193-9022 | 1012-193-9024 | TRUE
Block A | Aprt BL A/00/002 | 1012-193-9115 | 1012-193-9117 | TRUE
Block A | Aprt BL A/00/003 | 1012-193-9021 | 1012-193-9018 | TRUE
Block A | Aprt BL A/00/004 | 1012-193-9020 | 1012-193-9017 | TRUE
Block A | Aprt BL A/00/005 | 1012-193-9015 | 1012-193-9019 | TRUE
Block A | Aprt BL A/00/006 | 1012-193-9455 | 1012-193-9154 | TRUE
Block A | Aprt BL A/00/007 | 1012-193-9458 | 1012-193-9464 | TRUE
Block A | Aprt BL A/00/008 | 1012-193-9461 | 1012-193-9463 | TRUE
Block A | Aprt BL A/00/009 | 1012-193-9457 | 1012-193-9459 | TRUE
Block A | Aprt BL A/00/010 | 1012-193-8146 | 1012-193-9462 | TRUE
Block A | Aprt BL A/00/011 | 1012-193-9193 | 1012-193-9185 | TRUE
Block A | Aprt BL A/00/012 | 1012-193-8368 | 1012-193-8148 | TRUE
Block A | Aprt BL A/00/013 | 1012-193-9023 | 1012-193-8122 | TRUE
Block A | Aprt BL A/00/014 | 1012-193-9188 | 1012-193-9189 | TRUE
Block A | Aprt BL A/00/015 | 1012-193-8391 | 1012-193-9460 | TRUE
Block A | Aprt BL A/00/016 | 1012-193-9148 | 1012-193-9144 | TRUE
Block A | Aprt BL A/00/017 | 1012-193-9201 | 1012-193-9137 | TRUE
Block A | Aprt BL A/00/018 | 1012-193-9142 | 1012-193-9198 | TRUE
Block A | Aprt BL A/00/019 | 1012-193-9143 | 1012-193-9003 | TRUE
Block A | Aprt BL A/00/020 | 1012-193-9474 | 1012-193-9002 | TRUE
Block A | Aprt BL A/00/023 | 1012-193-8169 | 1012-193-8174 | TRUE
Block A | Aprt BL A/00/024 | 1012-193-8168 | 1012-193-8170 | TRUE
Block A | Aprt BL A/00/025 | 1012-193-8172 | 1012-193-8165 | TRUE
Block A | Aprt BL A/00/026 | 1012-193-9244 | 1012-193-9240 | TRUE
Block A | Aprt BL A/00/027 | 1012-193-9242 | 1012-193-9241 | TRUE
Block A | Aprt BL A/00/028 | 1012-193-9237 | 1012-193-9238 | TRUE
Block A | Aprt BL A/00/029 | 1012-194-1304 | 1012-193-9469 | TRUE
Block A | Aprt BL A/00/030 | 1012-193-9465 | 1012-193-9466 | TRUE
Block A | Aprt BL A/00/031 | 1012-193-8400 | 1012-193-9471 | TRUE
Block A | Aprt BL A/00/032 | 1012-193-9470 | 1012-193-9000 | TRUE
Block A | Aprt BL A/00/033 | 1012-193-9141 | 1012-193-9254 | TRUE
Block A | Aprt BL A/00/034 | 1012-193-8998 | 1012-193-9246 | TRUE
Block A | Aprt BL A/00/035 | 1012-193-8239 | 1012-193-8242 | TRUE
Block A | Aprt BL A/00/036 | 1012-177-2241 | 1012-193-1515 | TRUE
Block A | Aprt BL A/00/037 | 1012-194-1302 | 1012-194-1301 | TRUE
Block A | Aprt BL A/00/038 | 1012-177-2246 | 1012-177-2244 | TRUE
Block A | Aprt BL A/00/039 | 1012-177-2250 | 1012-177-2245 | TRUE
Block A | Aprt BL A/00/040 | 1012-194-1522 | 1012-177-2249 | TRUE
Block A | Aprt BL A/00/041 | 1012-194-1524 | 1012-177-2248 | TRUE
Block A | Aprt BL A/00/042 | 1012-194-1516 | 1012-194-1523 | TRUE
Block A | Aprt BL A/01/101 | 1012-193-8150 | 1012-193-8145 | TRUE
Block A | Aprt BL A/01/102 | 1012-193-8154 | 1012-193-9456 | TRUE
Block A | Aprt BL A/01/103 | 1012-193-8153 | 1012-193-8152 | TRUE
Block A | Aprt BL A/01/104 | 1012-193-9202 | 1012-193-8147 | TRUE
Block A | Aprt BL A/01/105 | 1012-193-9192 | 1012-193-9186 | TRUE
Block A | Aprt BL A/01/106 | 1012-193-9190 | 1012-193-9187 | TRUE
Block A | Aprt BL A/01/107 | 1012-193-8149 | 1012-193-9147 | TRUE
Block A | Aprt BL A/01/108 | 1012-193-9191 | 1012-193-9194 | TRUE
Block A | Aprt BL A/01/109 | 1012-193-8369 | 1012-193-8366 | TRUE
Block A | Aprt BL A/01/110 | 1012-193-8365 | 1012-193-9016 | TRUE
Block A | Aprt BL A/01/111 | 1012-193-8118 | 1012-193-8117 | TRUE
Block A | Aprt BL A/01/112 | 1012-193-8371 | 1012-193-8374 | TRUE
Block A | Aprt BL A/01/113 | 1012-193-8119 | 1012-193-8115 | TRUE
Block A | Aprt BL A/01/114 | 1012-193-8373 | 1012-193-8367 | TRUE
Block A | Aprt BL A/01/115 | 1012-193-8997 | 1012-193-9200 | TRUE
Block A | Aprt BL A/01/116 | 1012-193-8151 | 1012-193-8996 | TRUE
Block A | Aprt BL A/01/117 | 1012-193-9153 | 1012-193-9197 | TRUE
Block A | Aprt BL A/01/118 | 1012-193-9236 | 1012-193-9235 | TRUE
Block A | Aprt BL A/01/119 | 1012-193-8171 | 1012-193-8167 | TRUE
Block A | Aprt BL A/01/120 | 1012-193-8173 | 1012-193-8166 | TRUE
Block A | Aprt BL A/01/121 | 1012-193-9239 | 1012-193-9243 | TRUE
Block A | Aprt BL A/01/122 | 1012-193-9004 | 1012-193-8999 | TRUE
Block A | Aprt BL A/01/123 | 1012-193-9199 | 1012-193-9468 | TRUE
Block A | Aprt BL A/01/124 | 1012-193-9473 | 1012-193-9472 | TRUE
Block A | Aprt BL A/01/125 | 1012-193-8995 | 1012-193-8401 | TRUE
Block A | Aprt BL A/01/126 | 1012-193-8396 | 1012-193-9140 | TRUE
Block A | Aprt BL A/01/127 | 1012-193-9467 | 1012-193-8399 | TRUE
Block A | Aprt BL A/01/128 | 1012-193-9139 | 1012-193-9136 | TRUE
Block A | Aprt BL A/01/129 | 1012-194-1521 | 1012-194-1518 | TRUE
Block A | Aprt BL A/01/130 | 1012-194-1520 | 1012-194-1519 | TRUE
Block A | Aprt BL A/01/131 | 1012-177-2242 | 1012-177-2247 | TRUE
Block A | Aprt BL A/01/132 | 1012-194-1517 | 1012-177-2243 | TRUE
Block A | Aprt BL A/01/133 | 1012-193-8244 | 1012-193-8241 | TRUE
Block A | Aprt BL A/01/134 | 1012-193-8103 | 1012-193-8238 | TRUE
Block A | Aprt BL A/01/135 | 1012-193-8096 | 1012-193-9195 | TRUE
Block A | Aprt BL A/01/136 | 1012-193-8243 | 1012-193-8236 | TRUE
Block A | Aprt BL A/01/137 | 1012-193-8240 | 1012-193-8237 | TRUE
Block A | Aprt BL A/01/138 | 1012-193-8402 | 1012-193-9253 | TRUE
Block A | Aprt BL A/01/139 | 1012-193-8101 | 1012-193-8100 | TRUE
Block A | Aprt BL A/01/140 | 1012-193-8104 | 1012-193-8095 | TRUE
Block A | Aprt BL A/01/141 | 1012-193-9204 | 1012-193-8099 | TRUE
Block A | Aprt BL A/01/142 | 1012-193-8102 | 1012-193-8235 | TRUE
Block A | Aprt BL A/02/201 | 1012-193-8370 | 1012-193-8120 | TRUE
Block A | Aprt BL A/02/202 | 1012-193-8123 | 1012-193-8124 | TRUE
Block A | Aprt BL A/02/203 | 1012-193-9488 | 1012-193-9182 | TRUE
Block A | Aprt BL A/02/204 | 1012-193-9183 | 1012-193-9491 | TRUE
Block A | Aprt BL A/02/205 | 1012-193-9485 | 1012-194-9486 | TRUE
Block A | Aprt BL A/02/206 | 1012-193-9175 | 1012-193-9177 | TRUE
Block A | Aprt BL A/02/207 | 1012-193-9487 | 1012-193-9494 | TRUE
Block A | Aprt BL A/02/208 | 1012-193-9184 | 1012-193-9489 | TRUE
Block A | Aprt BL A/02/209 | 1012-193-9181 | 1012-193-9490 | TRUE
Block A | Aprt BL A/02/210 | 1012-193-9492 | 1012-193-9179 | TRUE
Block A | Aprt BL A/02/211 | 1012-193-9176 | 1012-193-9178 | TRUE
Block A | Aprt BL A/02/212 | 1012-193-8121 | 1012-193-8116 | TRUE
Block A | Aprt BL A/02/213 | 1012-193-9180 | 1012-193-9493 | TRUE
Block A | Aprt BL A/02/214 | 1012-193-9203 | 1012-193-9001 | TRUE
Block A | Aprt BL A/02/215 | 1012-193-9131 | 1012-193-9134 | TRUE
Block A | Aprt BL A/02/216 | 1012-193-9378 | 1012-193-9383 | TRUE
Block A | Aprt BL A/02/217 | 1012-193-8082 | 1012-193-9157 | TRUE
Block A | Aprt BL A/02/218 | 1012-193-9381 | 1012-193-9375 | TRUE
Block A | Aprt BL A/02/219 | 1012-193-9126 | 1012-193-9384 | TRUE
Block A | Aprt BL A/02/220 | 1012-193-9679 | 1012-193-9377 | TRUE
Block A | Aprt BL A/02/221 | 1012-193-8084 | 1012-193-8081 | TRUE
Block A | Aprt BL A/02/222 | 1012-193-8070 | 1012-193-9161 | TRUE
Block A | Aprt BL A/02/223 | 1012-193-9156 | 1012-193-8079 | TRUE
Block A | Aprt BL A/02/224 | 1012-193-9163 | 1012-193-8098 | TRUE
Block A | Aprt BL A/02/225 | 1012-193-9159 | 1012-193-8097 | TRUE
Block A | Aprt BL A/02/226 | 1012-193-8076 | 1012-193-9160 | TRUE
Block A | Aprt BL A/02/227 | 1012-193-9162 | 1012-193-8083 | TRUE
Block A | Aprt BL A/02/228 | 1012-193-9164 | 1012-193-9158 | TRUE
Block A | Aprt BL A/02/229 | 1012-193-8077 | 1012-193-8080 | TRUE
Block A | Aprt BL A/02/230 | 1012-193-9155 | 1012-193-8075 | TRUE
Block A | Aprt BL A/02/231 | 1012-193-9128 | 1012-193-9129 | TRUE
Block A | Aprt BL A/02/232 | 1012-193-9380 | 1012-193-9382 | TRUE
Block A | Aprt BL A/02/233 | 1012-193-9125 | 1012-193-9133 | TRUE
Block A | Aprt BL A/02/234 | 1012-193-9376 | 1012-193-9132 | TRUE
Block A | Aprt BL A/02/235 | 1012-193-9070 | 1012-193-9152 | TRUE
Block A | Aprt BL A/02/236 | 1012-193-9130 | 1012-193-9127 | TRUE
Block A | Aprt BL A/02/237 | 1012-193-9151 | 1012-193-9046 | TRUE
Block A | Aprt BL A/02/238 | 1012-193-9071 | 1012-193-9048 | TRUE
Block A | Aprt BL A/02/239 | 1012-193-9054 | 1012-196-9153 | TRUE
Block A | Aprt BL A/02/240 | 1012-193-9053 | 1012-193-9066 | TRUE
Block A | Aprt BL A/02/241 | 1012-193-9045 | 1012-194-1433 | TRUE
Block A | Aprt BL A/02/242 | 1012-193-9146 | 1012-193-9074 | TRUE
Block B | Aprt BL B/00/001 | 1012-193-9051 | 1012-193-9252 | TRUE
Block B | Aprt BL B/00/002 | 1012-193-9073 | 1012-193-9050 | TRUE
Block B | Aprt BL B/00/003 | 1012-193-8398 | 1012-193-9150 | TRUE
Block B | Aprt BL B/00/004 | 1012-193-9047 | 1012-193-1300 | TRUE
Block B | Aprt BL B/00/005 | 1012-193-8403 | 1012-193-8111 | TRUE
Block B | Aprt BL B/00/006 | 1012-193-8395 | 1012-193-9196 | TRUE
Block B | Aprt BL B/00/007 | 1012-193-9138 | 1012-193-8404 | TRUE
Block B | Aprt BL B/00/008 | 1012-193-9049 | 1012-193-9068 | TRUE
Block B | Aprt BL B/00/009 | 1012-193-9072 | 1012-193-9067 | TRUE
Block B | Aprt BL B/00/010 | 1012-193-9296 | 1012-193-9299 | TRUE
Block B | Aprt BL B/00/011 | 1012-194-1211 | 1012-194-1426 | TRUE
Block B | Aprt BL B/00/012 | 1012-193-9008 | 1012-177-1783 | TRUE
Block B | Aprt BL B/00/013 | 1012-193-9301 | 1012-193-9069 | TRUE
Block B | Aprt BL B/00/014 | 1012-193-1786 | 1012-193-9052 | TRUE
Block B | Aprt BL B/00/015 | 1012-193-8179 | 1012-193-8182 | TRUE
Block B | Aprt BL B/00/016 | 1012-193-8180 | 1012-193-8177 | TRUE
Block B | Aprt BL B/00/017 | 1012-193-8178 | 1012-193-8181 | TRUE
Block B | Aprt BL B/00/018 | 1012-193-8175 | 1012-193-8176 | TRUE
Block B | Aprt BL B/00/019 | 1012-193-8183 | 1012-1938184 | TRUE
Block B | Aprt BL B/00/020 | 1012-193-9145 | 1012-193-9123 | TRUE
Block B | Aprt BL B/00/021 | 1012-193-9120 | 1012-193-9149 | TRUE
Block B | Aprt BL B/00/022 | 1012-193-9118 | 1012-193-9124 | TRUE
Block B | Aprt BL B/00/023 | 1012-193-9119 | 1012-193-9116 | TRUE
Block B | Aprt BL B/00/024 | 1012-193-9121 | 1012-193-9122 | TRUE
Block B | Aprt BL B/00/025 | 1012-193-9086 | 1012-193-9087 | TRUE
Block B | Aprt BL B/00/026 | 1012-193-9088 | 1012-193-9093 | TRUE
Block B | Aprt BL B/00/027 | 1012-193-9090 | 1012-193-9091 | TRUE
Block B | Aprt BL B/00/028 | 1012-193-9089 | 1012-193-9085 | TRUE
Block B | Aprt BL B/00/029 | 1012-177-1621 | 1012-177-1622 | TRUE
Block B | Aprt BL B/00/030 | 1012-193-9450 | 1012-193-1627 | TRUE
Block B | Aprt BL B/00/031 | 1012-193-9452 | 1012-193-9106 | TRUE
Block B | Aprt BL B/00/032 | 1012-193-9113 | 1012-193-9107 | TRUE
Block B | Aprt BL B/00/033 | 1012-193-9109 | 1012-193-9484 | TRUE
Block B | Aprt BL B/00/034 | 1012-193-9481 | 1012-193-9112 | TRUE
Block B | Aprt BL B/00/035 | 1012-193-9114 | 1012-193-9108 | TRUE
Block B | Aprt BL B/00/036 | 1012-193-9105 | 1012-193-9441 | TRUE
Block B | Aprt BL B/00/037 | 1012-193-9442 | 1012-193-9436 | TRUE
Block B | Aprt BL B/00/038 | 1012-193-9437 | 1012-193-9443 | TRUE
Block B | Aprt BL B/00/039 | 1012-193-9440 | 1012-193-9444 | TRUE
Block B | Aprt BL B/00/040 | 1012-193-9435 | 1012-193-9439 | TRUE
Block B | Aprt BL B/00/041 | 1012-193-9111 | 1012-193-9110 | TRUE
Block B | Aprt BL B/00/042 | 1012-193-9438 | 1012-193-9044 | TRUE
Block B | Aprt BL B/01/101 | 1012-193-9005 | 1012-193-9013 | TRUE
Block B | Aprt BL B/01/102 | 1012-193-9006 | 1012-193-9012 | TRUE
Block B | Aprt BL B/01/103 | 1012-193-9303 | 1012-193-9007 | TRUE
Block B | Aprt BL B/01/104 | 1012-193-9298 | 1012-193-9300 | TRUE
Block B | Aprt BL B/01/105 | 1012-194-1429 | 1012-194-1428 | TRUE
Block B | Aprt BL B/01/106 | 1012-193-9014 | 1012-193-9009 | TRUE
Block B | Aprt BL B/01/107 | 1012-193-1430 | 1012-193-9295 | TRUE
Block B | Aprt BL B/01/108 | 1012-193-9297 | 1012-193-9302 | TRUE
Block B | Aprt BL B/01/109 | 1012-193-8106 | 1012-193-8114 | TRUE
Block B | Aprt BL B/01/110 | 1012-193-8135 | 1012-193-8141 | TRUE
Block B | Aprt BL B/01/111 | 1012-194-1295 | 1012-193-8107 | TRUE
Block B | Aprt BL B/01/112 | 1012-193-8109 | 1012-193-8112 | TRUE
Block B | Aprt BL B/01/113 | 1012-193-8105 | 1012-193-8113 | TRUE
Block B | Aprt BL B/01/114 | 1012-194-1303 | 1012-193-8108 | TRUE
Block B | Aprt BL B/01/115 | 1012-193-9394 | 1012-193-9388 | TRUE
Block B | Aprt BL B/01/116 | 1012-193-9094 | 1012-193-9393 | TRUE
Block B | Aprt BL B/01/117 | 1012-193-9363 | 1012-193-9359 | TRUE
Block B | Aprt BL B/01/118 | 1012-193-9392 | 1012-193-9389 | TRUE
Block B | Aprt BL B/01/119 | 1012-193-9357 | 1012-193-9362 | TRUE
Block B | Aprt BL B/01/120 | 1012-193-9358 | 1012-193-9360 | TRUE
Block B | Aprt BL B/01/121 | 1012-193-9356 | 1012-193-9364 | TRUE
Block B | Aprt BL B/01/122 | 1012-193-9361 | 1012-193-9355 | TRUE
Block B | Aprt BL B/01/123 | 1012-193-8190 | 1012-193-8139 | TRUE
Block B | Aprt BL B/01/124 | 1012-193-9011 | 1012-193-9062 | TRUE
Block B | Aprt BL B/01/125 | 1012-193-8192 | 1012-193-8186 | TRUE
Block B | Aprt BL B/01/126 | 1012-193-8189 | 1012-193-8185 | TRUE
Block B | Aprt BL B/01/127 | 1012-193-8191 | 1012-193-8188 | TRUE
Block B | Aprt BL B/01/128 | 1012-193-8194 | 1012-193-8187 | TRUE
Block B | Aprt BL B/01/129 | 1012-193-9172 | 1012-193-9170 | TRUE
Block B | Aprt BL B/01/130 | 1012-193-9171 | 1012-193-9043 | TRUE
Block B | Aprt BL B/01/131 | 1012-193-9174 | 1012-193-9165 | TRUE
Block B | Aprt BL B/01/132 | 1012-193-9079 | 1012-193-9166 | TRUE
Block B | Aprt BL B/01/133 | 1012-193-9169 | 1012-193-9168 | TRUE
Block B | Aprt BL B/01/134 | 1012-193-9173 | 1012-193-9167 | TRUE
Block B | Aprt BL B/01/135 | 1012-193-9080 | 1012-193-9077 | TRUE
Block B | Aprt BL B/01/136 | 1012-193-9076 | 1012-193-9081 | TRUE
Block B | Aprt BL B/01/137 | 1012-193-9082 | 1012-193-9078 | TRUE
Block B | Aprt BL B/01/138 | 1012-193-9083 | 1012-193-9084 | TRUE
Block B | Aprt BL B/01/139 | 1012-193-9280 | 1012-193-9279 | TRUE
Block B | Aprt BL B/01/140 | 1012-193-9283 | 1012-193-9282 | TRUE
Block B | Aprt BL B/01/141 | 1012-193-9275 | 1012-193-9281 | TRUE
Block B | Aprt BL B/01/142 | 1012-193-9278 | 1012-193-9276 | TRUE
Block B | Aprt BL B/02/201 | 1012-194-1209 | 1012-194-1214 | TRUE
Block B | Aprt BL B/02/202 | 1012-194-1205 | 1012-194-1208 | TRUE
Block B | Aprt BL B/02/203 | 1012-193-1210 | 1012-193-1207 | TRUE
Block B | Aprt BL B/02/204 | 1012-193-9304 | 1012-193-1212 | TRUE
Block B | Aprt BL B/02/205 | 1012-194-1206 | 1012-193-1213 | TRUE
Block B | Aprt BL B/02/206 | 1012-193-8140 | 1012-193-8143 | TRUE
Block B | Aprt BL B/02/207 | 1012-193-8136 | 1012-193-8142 | TRUE
Block B | Aprt BL B/02/208 | 1012-193-8144 | 1012-193-8138 | TRUE
Block B | Aprt BL B/02/209 | 1012-193-8137 | 1012-193-8193 | TRUE
Block B | Aprt BL B/02/210 | 1012-193-9010 | 1012-177-1782 | TRUE
Block B | Aprt BL B/02/211 | 1012-194-1434 | 1012-193-9065 | TRUE
Block B | Aprt BL B/02/212 | 1012-194-1425 | 1012-177-1789 | TRUE
Block B | Aprt BL B/02/213 | 1012-177-1785 | 1012-194-1432 | TRUE
Block B | Aprt BL B/02/214 | 1012-194-1431 | 1012-194-1427 | TRUE
Block B | Aprt BL B/02/215 | 1012-193-9390 | 1012-193-9385 | TRUE
Block B | Aprt BL B/02/216 | 1012-193-9386 | 1012-193-9391 | TRUE
Block B | Aprt BL B/02/217 | 1012-193-9372 | 1012-193-9366 | TRUE
Block B | Aprt BL B/02/218 | 1012-193-9370 | 1012-193-9373 | TRUE
Block B | Aprt BL B/02/219 | 1012-193-9075 | 1012-193-9387 | TRUE
Block B | Aprt BL B/02/220 | 1012-193-8085 | 1012-193-9374 | TRUE
Block B | Aprt BL B/02/221 | 1012-193-9369 | 1012-193-8089 | TRUE
Block B | Aprt BL B/02/222 | 1012-193-8090 | 1012-193-8093 | TRUE
Block B | Aprt BL B/02/223 | 1012-193-8092 | 1012-193-8094 | TRUE
Block B | Aprt BL B/02/224 | 1012-193-9365 | 1012-193-8086 | TRUE
Block B | Aprt BL B/02/225 | 1012-193-9371 | 1012-193-9368 | TRUE
Block B | Aprt BL B/02/226 | 1012-193-8091 | 1012-193-8087 | TRUE
Block B | Aprt BL B/02/227 | 1012-193-9367 | 1012-193-8088 | TRUE
Block B | Aprt BL B/02/228 | 1012-193-9277 | 1012-193-9284 | TRUE
Block B | Aprt BL B/02/229 | 1012-193-9483 | 1012-193-9477 | TRUE
Block B | Aprt BL B/02/230 | 1012-193-9476 | 1012-193-9479 | TRUE
Block B | Aprt BL B/02/231 | 1012-193-9445 | 1012-193-9475 | TRUE
Block B | Aprt BL B/02/232 | 1012-193-9448 | 1012-193-9446 | TRUE
Block B | Aprt BL B/02/233 | 1012-177-1630 | 1012-193-9451 | TRUE
Block B | Aprt BL B/02/234 | 1012-177-1625 | 1012-193-9480 | TRUE
Block B | Aprt BL B/02/235 | 1012-193-9447 | 1012-177-1629 | TRUE
Block B | Aprt BL B/02/236 | 1012-177-1628 | 1012-177-1624 | TRUE
Block B | Aprt BL B/02/237 | 1012-193-9453 | 1012-193-9449 | TRUE
Block B | Aprt BL B/02/238 | 1012-193-9454 | 1012-177-1623 | TRUE
Block B | Aprt BL B/02/239 | 1012-193-9038 | 1012-193-9042 | TRUE
Block B | Aprt BL B/02/240 | 1012-193-9040 | 1012-193-9035 | TRUE
Block B | Aprt BL B/02/241 | 1012-193-9041 | 1012-193-9039 | TRUE
Block B | Aprt BL B/02/242 | 1012-193-9037 | 1012-193-9036 | TRUE

## Kiosk Plan
Minisub | MS Serial | Kiosk Number | Original Planned |  |  | New planned units |  |  |  | Comments
|  |  | Uits fed | 8 probe | 16 probe | Updated units fed | 8 probe | 16 probe | Inc/dec units
1 | 82929702 | 1EVE1 | 8 | 1 | 0 | 8 | 1 | 0 | 0
1 | 82929702 | 2EVE1 | 7 | 1 | 0 | 7 | 1 | 0 | 0
1 | 82929702 | 3EVE1 | 9 | 0 | 1 | 9 | 0 | 1 | 0
1 | 82929702 | 4EVE1 | 9 | 0 | 1 | 9 | 0 | 1 | 0
1 | 82929702 | 5EVE1 | 6 | 1 | 0 | 6 | 1 | 0 | 0
1 | 82929702 | 6EVE1 | 9 | 0 | 1 | 9 | 0 | 1 | 0
2 | 82929684 | 1EVE2 | 6 | 1 | 0 | 6 | 1 | 0 | 0
2 | 82929684 | 2EVE2 | 8 | 1 | 0 | 7 | 1 | 0 | -1 | One less Unit fed
2 | 82929684 | 3EVE2 | 9 | 0 | 1 | 8 | 1 | 0 | -1 | One less Unit fed
2 | 82929684 | 4EVE2 | 9 | 0 | 1 | 9 | 0 | 1 | 0
2 | 82929684 | 5EVE2 | 7 | 1 | 0 | 7 | 1 | 0 | 0
2 | 82929684 | 6EVE2 | 6 | 1 | 0 | 6 | 1 | 0 | 0
2 | 82929684 | 7EVE2 | 6 | 1 | 0 | 6 | 1 | 0 | 0
2 | 82929684 | 8EVE2 | 6 | 1 | 0 | 4 | 1 | 0 | -2 | 2 less units fed
2 | 82929684 | 9EVE2 | 8 | 1 | 0 | 8 | 1 | 0 | 0
2 | 82929684 | 10EVE2 | 6 | 1 | 0 | 6 | 1 | 0 | 0
3 | 71205556 | 1EVE3 | 9 | 0 | 1 | 9 | 0 | 1 | 0
3 | 71205556 | 2EVE3 | 9 | 0 | 1 | 9 | 0 | 1 | 0
3 | 71205556 | 3EVE3 | 9 | 0 | 1 | 9 | 0 | 1 | 0
3 | 71205556 | 4EVE3 | 9 | 0 | 1 | 8 | 1 | 0 | -1 | One less Unit fed
3 | 71205556 | 5EVE3 | 9 | 0 | 1 | 5 | 1 | 0 | -4 | 4 less units fed
3 | 71205556 | 6EVE3 | 9 | 0 | 1 | 0 | 0 | 0 | -9 | Kiosk removed
3 | 71205556 | 7EVE3 | 9 | 0 | 1 | 3 | 1 | 0 | -6 | 6 less units
3 | 71205556 | 8EVE3 | 8 | 1 | 0 | 9 | 0 | 1 | 1 | one additional unit
3 | 71205556 | 9EVE3 | 0 | 0 | 0 | 8 | 1 | 0 | 8 | New additional kiosk
3 | 71205556 | 10EVE3 | 0 | 0 | 0 | 7 | 1 | 0 | 7 | New additional kiosk
3 | 71205556 | 11EVE3 | 0 | 0 | 0 | 8 | 1 | 0 | 8 | New additional kiosk
|  |  | 190 | 12 | 12 | 190 | 18 | 8
|  |  |  | 24 |  |  | 26

## Temp ME162 open and closings
Erf | Section | Meter serial number | Opening readings | Google docs Submitted | removal date | Closing Readings | Usage [WBHO] | Google docs Submitted
22 | A | 67573323 | 19375.9 |  | 2026-07-15 | 19888.1 | 512.2
44 | A | 67021362 | 56032.6 |  |  | 56111.5 | 78.9
53 | A | 67573216 | 17968.5 |  |  | 18120.9 | 152.4
58 | B | 42607693 | 59659 |  |  | 59659 | 0
60 | B | 42607645 | 97390 |  |  | 97390 | 0
61 | B | 42607493 | 23184 |  |  | 23184 | 0
62 | B | 42607616 | 7889 |  |  | 7889 | 0
63 | B | 42607457 | 27096 |  |  | 27095 | -1
64 | B | 42607809 | 15280 |  |  | 15280 | 0
65 | B | 42607653 | 20310 |  |  | 20310 | 0
66 | B | 42607631 | 24100 |  |  | 24100 | 0
67 | B | 46886910 | 172161.6 |  |  | 172161.6 | 0
68 | B | 42607609 | 11718 |  |  | 11718 | 0
69 | B | 47512547 | 38143 |  |  | 38145 | 2
70 | B | 47511635 | 35381.2 |  |  | 35381.2 | 0
71 | B | 4260700 | 179707 |  |  | 179707 | 0
72 | B | 46886909 | 103115.8 |  |  | 103121.8 | 6
73 | B | 47369448 | 18870 |  |  | 18870 | 0
74 | B | 47511330 | 72558.4 |  |  | 72558.4 | 0
75 | B | 42607467 | 12607 |  |  | 12608 | 1
82 |  | 91733392 | 0 |  |  | 274.6 | 274.6
87 | B | 67021344 | 30522 |  |  | 30522 | 0
88 | B | 67021354 | 42174 |  |  | 42174 | 0
89 | B | 91546861 | 0 |  |  | 101.9 | 101.9
90 | B | 66599353 | 0 |  |  | 47842.5 | 47842.5
91 | B | 87778411 | 0 |  |  | 54.7 | 54.7
92 | B | 67573171 | 55276.2 |  |  | 55295.6 | 19.4
93 | A | 90007553 | 1076.4 |  |  | 1234.5 | 158.1
94 | B | 67573207 | 26813.1 |  |  | 26832.8 | 19.7
95 | A | 42607759 | 26313 |  |  | 139657 | 113344
96 | B | 67573298 | 16956.2 |  |  | 16978.1 | 21.9
97 | A | 67573203 | 36948.8 |  |  | 36948.8 | 0
98 | B | 67573191 | 43330.5 |  |  | 43364.7 | 34.2
99 | A | 67572944 | 21735.7 |  |  | 21789.1 | 53.4
100 | B | 67573201 | 28815.3 |  |  | 28847.1 | 31.8
101 | A | 67021339 | 30210.7 |  |  | 30259.5 | 48.8
102 | B | 90008040 | 1849.3 |  |  | 1881.8 | 32.5
103 | A | 46886935 | 82275 |  |  | 82330 | 55
105 | A | 67572955 | 28976.3 |  |  | 29012.7 | 36.4
107 | A | 42607429 | 19376 |  |  |  | -19376 | Yes
109 | A | 67021338 | 29281.6 |  |  | 29406.1 | 124.5 | Yes
111 | A | 42607771 | 5509 |  |  | 5516 | 7 | Yes
113 | A | 67573205 | 38016.9 |  |  | 38086 | 69.1 | Yes
115 | A | 67573265 | 71144.2 |  |  | 71214.8 | 70.6 | Yes
117 | A | 66599401 | 63803.5 |  |  | 63860.4 | 56.9 | Yes
119 | A | 67573188 | 29124.2 |  |  | 29208.6 | 84.4 | Yes
121 | A | 84039773 | 9600.1 |  |  | 9668.1 | 68 | Yes
123 | A | 67573376 | 89289.8 |  |  | 89352.7 | 62.9 | Yes
125 | A | 67573196 | 89182.7 |  |  | 89225.2 | 42.5 | Yes
127 | A | 67573307 | 25290.8 |  |  | 25372.1 | 81.3 | Yes
145 |  | 84039773 | ? |  | 2026-07-16 | 9991.2 | #VALUE!
163 | A | 70694930 | 35892.8 |  | 2026-07-17 | 36164.5 | 271.7
186 |  | 91546036 | 0 |  |  | 488.5 | 488.5 | Yes
179 |  | 91546509 | 0 |  |  | 649.9 | 649.9 | Yes
1410.1

## Replaced meters
Stand Number | Old Meter serial number | Meter Model | Opening readings | Meter Commissioning Date | Faulty Replaced | Replacement Date | New meter serial | New meter opening
105 | 9898003 | Axioma | 0.075 | 2026-05-26 | TRUE | 2026-07-03 | 10192010 | 0.075
109 | 9898037 | Axioma | 0.068 | 2026-04-30 | TRUE | 2026-07-03 | 10192016 | 0.068
125 | 9898001 | Axioma | 0.091 | 2026-05-26 | TRUE | 2026-07-03 | 9993259 | 0.091
094 | 10172140 | Axioma | 0.086 | 2026-05-19 | TRUE | 2026-07-07 | 10192054 | 0.06
076 | 10172252 | Axioma | 0.096 | 2026-06-04 | TRUE | 2026-07-13 | 10192062 | 0.096
096 | 10172132 | Axioma | 0.086 | 2026-05-19 | TRUE | 2026-07-13 | 9993247 | 0.086
103 | 9897912 | Axioma | 0.097 | 2026-05-26 | TRUE | 2026-07-13 | 10192047 | 0.097
062 | 9993266 | Axioma | 0.074 | 2026-06-13 | TRUE | 2026-08-20 | 10596300 | 0.104
067 | 10192015 | Axioma | 0.113 | 2026-06-13 | TRUE | 2026-08-20 | 10596245 | 0.113
072 | 9897914 | Axioma | 0.101 | 2026-06-09 | TRUE | 2026-08-20 | 10596189 | 0.101
186 | 10192013 | Axioma | 0.106 | 2026-06-13 | TRUE | 2026-08-20 | 10596240 | 0.106
187 | 10192019 | Axioma | 0.104 | 2026-06-13 | TRUE | 2026-08-20 | 10596298 | 0.104
094 | 10192054 | Axioma | 0.086 | 2026-07-07 | TRUE | 2026-08-24 | 10596238 | 0.097
105 | 10192010 | Axioma | 0.075 | 2026-07-03 | TRUE | 2026-08-24 | 10596306 | 0.104
081 | 10172263 | Axioma | 10.404 | 2026-05-29 | TRUE | 2026-08-24 | 10596241 | 0.086
183 | 9993265 | Axioma | 0.075 | 2026-06-13 | TRUE | 2026-09-08 | 10596188 | 0.099
188 | 10192018 | Axioma | 0.068 | 2026-06-13 | TRUE | 2026-09-08 | 10596305 | 0.141
092 | 10172255 | Axioma | 0.102 | 2026-05-19 | TRUE | 2026-09-08 | 10596175 | 0.142
039 | 10192052 | Axioma | 0.067 | 2026-07-02 | TRUE | 2026-09-08 | 10596179 | 0.12
049 | 10192050 | Axioma | 0.068 | 2026-07-01 | TRUE | 2026-09-08 | 10596183 | 0.111
059 | 9993268 | Axioma | 0.082 | 2026-07-01 | TRUE | 2026-09-08 | 54789019 | 0.175
185 | 10192009 | Axioma | 0.067 | 2026-06-13 | TRUE | 2026-09-14 | 10596176 | 0.111
045 | 10192053 | Axioma | 0.088 | 2026-07-02 | TRUE | 2026-09-14 | 10596203 | 0.095