## Water meters
Stand Number | Section | Meter serial number | Manufacturer | Meter Model | Connection size | Opening readings | Meter Commissioning Date | AMR Commissioned | WBHO Subsection | Snag Date 1 | Snag Date 2 | Snag Date 3 | Snag Date 4
001 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 20 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
002 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 20 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
003 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 18 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06
004 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 20 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
005 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 18 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06
006 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 20 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
007 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 18 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06
008 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 20 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
009 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 18 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06
010 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 20 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
011 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 18 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06
012 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 20 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
013 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 18 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06
014 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 20 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
015 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 18 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06
016 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 20 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
017 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 17 | 2026-06-24 | 2026-07-01 | 2026-07-15 | 2026-07-21
018 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 20 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
019 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 17 | 2026-06-24 | 2026-07-01 | 2026-07-15 | 2026-07-21
020 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 19 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
021 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 17 | 2026-06-24 | 2026-07-01 | 2026-07-15 | 2026-07-21
022 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 19 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
023 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 17 | 2026-06-24 | 2026-07-01 | 2026-07-15 | 2026-07-21
024 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 19 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
025 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 17 | 2026-06-24 | 2026-07-01 | 2026-07-15 | 2026-07-21
026 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 19 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
027 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 17 | 2026-06-24 | 2026-07-01 | 2026-07-15 | 2026-07-21
028 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 19 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
029 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 17 | 2026-06-24 | 2026-07-01 | 2026-07-15 | 2026-07-21
030 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 19 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
031 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 17 | 2026-06-24 | 2026-07-01 | 2026-07-15 | 2026-07-21
032 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 19 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
033 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 19 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
034 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 14 | 2026-06-22 | 2026-06-29 | 2026-07-18 | 2026-07-18
035 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 11 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04
036 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 14 | 2026-06-22 | 2026-06-29 | 2026-07-18 | 2026-07-18
037 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 11 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04
038 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 14 | 2026-06-22 | 2026-06-29 | 2026-07-18 | 2026-07-18
039 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 11 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04
040 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 14 | 2026-06-22 | 2026-06-29 | 2026-07-18 | 2026-07-18
041 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 11 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04
042 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 14 | 2026-06-22 | 2026-06-29 | 2026-07-18 | 2026-07-18
043 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 11 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04
044 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 14 | 2026-06-22 | 2026-06-29 | 2026-07-18 | 2026-07-18
045 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 10 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22
046 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 13 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04
047 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 10 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22
048 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 13 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04
049 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 10 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22
050 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 13 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04
051 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 10 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22
052 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 13 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04
053 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 10 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22
054 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 13 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04
055 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 10 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22
056 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 13 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04
057 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 10 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22
058 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 13 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04
059 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 10 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22
060 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 13 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04
061 | B3 | 10192017 | Precision | Axioma | 15mm | 0.067 | 2026-06-13 | TRUE | Section 9 | 2026-05-11 | 2026-05-18 | 2026-06-01 | 2026-06-06
062 | A3 | 9993266 | Precision | Axioma | 15mm | 0.074 | 2026-06-13 | TRUE | Section 12 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22
063 | B3 | 10192021 | Precision | Axioma | 15mm | 0.066 | 2026-06-13 | TRUE | Section 9 | 2026-05-11 | 2026-05-18 | 2026-06-01 | 2026-06-06
064 | A3 | 9993250 | Precision | Axioma | 15mm | 0.081 | 2026-06-13 | TRUE | Section 12 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22
065 | B3 | 10192022 | Precision | Axioma | 15mm | 0.067 | 2026-06-13 | TRUE | Section 9 | 2026-05-11 | 2026-05-18 | 2026-06-01 | 2026-06-06
066 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 12 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22
067 | B3 | 10192015 | Precision | Axioma | 15mm | 0.065 | 2026-06-13 | TRUE | Section 9 | 2026-05-11 | 2026-05-18 | 2026-06-01 | 2026-06-06
068 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 12 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22
069 | B3 | 10192007 | Precision | Axioma | 15mm | 0.066 | 2026-06-13 | TRUE | Section 9 | 2026-05-11 | 2026-05-18 | 2026-06-01 | 2026-06-06
070 | A3 | 9897925 | Precision | Axioma | 15mm | 0.072 | 2026-06-13 | TRUE | Section 12 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22
071 | B3 | 10172133 | Precision | Axioma | 15mm | 0.083 | 2026-06-09 | TRUE | Section 9 | 2026-05-11 | 2026-05-18 | 2026-06-01 | 2026-06-06
072 | A3 | 9897914 | Precision | Axioma | 15mm | 0.042 | 2026-06-09 | TRUE | Section 12 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22
073 | B3 | 9897893 | Precision | Axioma | 15mm | 0.07 | 2026-06-09 | TRUE | Section 9 | 2026-05-11 | 2026-05-18 | 2026-06-01 | 2026-06-06
074 | A3 | 9897897 | Precision | Axioma | 15mm | 0.07 | 2026-06-09 | TRUE | Section 12 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22
075 | B3 | 9897987 | Precision | Axioma | 15mm | 0.072 | 2026-06-09 | TRUE | Section 9 | 2026-05-11 | 2026-05-18 | 2026-06-01 | 2026-06-06
076 | A2 | 10172252 | Precision | Axioma | 15mm | 0.102 | 2026-06-04 | TRUE | Section 5 | 2026-06-17 | 2026-06-24 | 2026-07-08 | 2026-07-14
077 | A2 | 10172251 | Precision | Axioma | 15mm | 0.103 | 2026-06-04 | TRUE | Section 5 | 2026-06-17 | 2026-06-24 | 2026-07-08 | 2026-07-14
078 | A2 | 10172260 | Precision | Axioma | 15mm | 0.103 | 2026-05-29 | TRUE | Section 5 | 2026-06-17 | 2026-06-24 | 2026-07-08 | 2026-07-14
079 | A2 | 10172246 | Precision | Axioma | 15mm | 0.097 | 2026-06-04 | TRUE | Section 5 | 2026-06-17 | 2026-06-24 | 2026-07-08 | 2026-07-14
080 | A2 | 10172248 | Precision | Axioma | 15mm | 0.096 | 2026-05-29 | TRUE | Section 4 | 2026-06-02 | 2026-06-09 | 2026-06-24 | 2026-06-30
081 | A2 | 10172263 | Precision | Axioma | 15mm | 0.102 | 2026-05-29 | TRUE | Section 4 | 2026-06-02 | 2026-06-09 | 2026-06-24 | 2026-06-30
082 | A2 | 10172257 | Precision | Axioma | 15mm | 0.102 | 2026-05-29 | TRUE | Section 4 | 2026-06-02 | 2026-06-09 | 2026-06-24 | 2026-06-30
083 | A2 | 10172256 | Precision | Axioma | 15mm | 0.102 | 2026-05-29 | TRUE | Section 4 | 2026-06-02 | 2026-06-09 | 2026-06-24 | 2026-06-30
084 | A2 | 10172262 | Precision | Axioma | 15mm | 0.102 | 2026-05-29 | TRUE | Section 4 | 2026-06-02 | 2026-06-09 | 2026-06-24 | 2026-06-30
085 | A2 | 10172253 | Precision | Axioma | 15mm | 0.101 | 2026-05-29 | TRUE | Section 4 | 2026-06-02 | 2026-06-09 | 2026-06-24 | 2026-06-30
086 | A2 | 10172135 | Precision | Axioma | 15mm | 0.088 | 2026-06-04 | TRUE | Section 4 | 2026-06-02 | 2026-06-09 | 2026-06-24 | 2026-06-30
087 | B2 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 3 | 2026-05-13 | 2026-05-20 | 2026-06-03 | 2026-06-09
088 | B2 | 10172138 | Precision | Axioma | 15mm | 0.085 | 2026-06-09 | TRUE | Section 3 | 2026-05-13 | 2026-05-20 | 2026-06-03 | 2026-06-09
089 | B2 | 10172265 | Precision | Axioma | 15mm | 0.102 | 2026-05-21 | TRUE | Section 3 | 2026-05-13 | 2026-05-20 | 2026-06-03 | 2026-06-09
090 | B2 | 10172247 | Precision | Axioma | 15mm | 0.097 | 2026-05-21 | TRUE | Section 3 | 2026-05-13 | 2026-05-20 | 2026-06-03 | 2026-06-09
091 | B2 | 10172249 | Precision | Axioma | 15mm | 0.099 | 2026-05-21 | TRUE | Section 3 | 2026-05-13 | 2026-05-20 | 2026-06-03 | 2026-06-09
092 | B2 | 10172255 | Precision | Axioma | 15mm | 0.102 | 2026-05-19 | TRUE | Section 5 | 2026-04-28 | 2026-05-06 | 2026-05-20 | 2026-05-26
093 | A1 | 9897995 | Precision | Axioma | 15mm | 0.095 | 2026-05-26 | TRUE | Section 2 | 2026-04-22 | 2026-04-30 | 2026-05-15 | 2026-05-21
094 | B2 | 10172140 | Precision | Axioma | 15mm | 0.086 | 2026-05-19 | TRUE | Section 5 | 2026-04-28 | 2026-05-06 | 2026-05-20 | 2026-05-26
095 | A1 | 10172258 | Precision | Axioma | 15mm | 0.104 | 2026-05-26 | TRUE | Section 2 | 2026-04-22 | 2026-04-30 | 2026-05-15 | 2026-05-21
096 | B2 | 10172132 | Precision | Axioma | 15mm | 0.086 | 2026-05-19 | TRUE | Section 5 | 2026-04-28 | 2026-05-06 | 2026-05-20 | 2026-05-26
097 | A1 | 10172250 | Precision | Axioma | 15mm | 0.099 | 2026-05-26 | TRUE | Section 2 | 2026-04-22 | 2026-04-30 | 2026-05-15 | 2026-05-21
098 | B2 | 10172259 | Precision | Axioma | 15mm | 0.102 | 2026-05-19 | TRUE | Section 5 | 2026-04-28 | 2026-05-06 | 2026-05-20 | 2026-05-26
099 | A1 | 10172261 | Precision | Axioma | 15mm | 0.101 | 2026-05-26 | TRUE | Section 2 | 2026-04-22 | 2026-04-30 | 2026-05-15 | 2026-05-21
100 | B2 | 10172254 | Precision | Axioma | 15mm | 0.102 | 2026-05-19 | TRUE | Section 5 | 2026-04-28 | 2026-05-06 | 2026-05-20 | 2026-05-26
101 | A1 | 9897994 | Precision | Axioma | 15mm | 0.091 | 2026-05-26 | TRUE | Section 2 | 2026-04-22 | 2026-04-30 | 2026-05-15 | 2026-05-21
102 | B2 | 10172264 | Precision | Axioma | 15mm | 0.105 | 2026-05-19 | TRUE | Section 5 | 2026-04-28 | 2026-05-06 | 2026-05-20 | 2026-05-26
103 | A1 | 9897912 | Precision | Axioma | 15mm | 0.073 | 2026-05-26 | TRUE | Section 2 | 2026-04-22 | 2026-04-30 | 2026-05-15 | 2026-05-21
104 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 21 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06
105 | A1 | 9898003 | Precision | Axioma | 15mm | 0.093 | 2026-05-26 | TRUE | Section 2 | 2026-04-22 | 2026-04-30 | 2026-05-15 | 2026-05-21
106 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 21 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06
107 | A1 | 9898044 | Precision | Axioma | 15mm | 0.081 | 2026-05-26 | TRUE | Section 2 | 2026-04-22 | 2026-04-30 | 2026-05-15 | 2026-05-21
108 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 21 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06
109 | A1 | 9898037 | Precision | Axioma | 15mm | 0.071 | 2026-04-30 | TRUE | Section 2 | 2026-04-22 | 2026-04-30 | 2026-05-15 | 2026-05-21
110 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 21 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06
111 | A1 | 9897906 | Precision | Axioma | 15mm | 0.068 | 2026-04-30 | TRUE | Section 2 | 2026-04-22 | 2026-04-30 | 2026-05-15 | 2026-05-21
112 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 21 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06
113 | A1 | 9897997 | Precision | Axioma | 15mm | 0.091 | 2026-04-30 | TRUE | Section 1 | 2026-04-13 | 2026-04-20 | 2026-05-06 | 2026-05-12
114 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 21 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06
115 | A1 | 9898005 | Precision | Axioma | 15mm | 0.093 | 2026-04-30 | TRUE | Section 1 | 2026-04-13 | 2026-04-20 | 2026-05-06 | 2026-05-12
116 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 21 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06
117 | A1 | 9897913 | Precision | Axioma | 15mm | 0.082 | 2026-04-24 | TRUE | Section 1 | 2026-04-13 | 2026-04-20 | 2026-05-06 | 2026-05-12
118 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 21 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06
119 | A1 | 9897993 | Precision | Axioma | 15mm | 0.223 | 2026-04-24 | TRUE | Section 1 | 2026-04-13 | 2026-04-20 | 2026-05-06 | 2026-05-12
120 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 22 | 2026-07-24 | 2026-07-31 | 2026-08-15 | 2026-08-21
121 | A1 | 9897907 | Precision | Axioma | 15mm | 0.08 | 2026-04-24 | TRUE | Section 1 | 2026-04-13 | 2026-04-20 | 2026-05-06 | 2026-05-12
122 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 22 | 2026-07-24 | 2026-07-31 | 2026-08-15 | 2026-08-21
123 | A1 | 9897911 | Precision | Axioma | 15mm | 0.071 | 2026-05-26 | TRUE | Section 1 | 2026-04-13 | 2026-04-20 | 2026-05-06 | 2026-05-12
124 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 22 | 2026-07-24 | 2026-07-31 | 2026-08-15 | 2026-08-21
125 | A1 | 9898001 | Precision | Axioma | 15mm | 1.163 | 2026-05-26 | TRUE | Section 1 | 2026-04-13 | 2026-04-20 | 2026-05-06 | 2026-05-12
126 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 22 | 2026-07-24 | 2026-07-31 | 2026-08-15 | 2026-08-21
127 | A1 | 9897908 | Precision | Axioma | 15mm | 0.076 | 2026-05-26 | TRUE | Section 1 | 2026-04-13 | 2026-04-20 | 2026-05-06 | 2026-05-12
128 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 22 | 2026-07-24 | 2026-07-31 | 2026-08-15 | 2026-08-21
129 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 22 | 2026-07-24 | 2026-07-31 | 2026-08-15 | 2026-08-21
130 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 22 | 2026-07-24 | 2026-07-31 | 2026-08-15 | 2026-08-21
131 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 22 | 2026-07-24 | 2026-07-31 | 2026-08-15 | 2026-08-21
132 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 23 | 2026-08-08 | 2026-08-17 | 2026-08-31 | 2026-09-05
133 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 23 | 2026-08-08 | 2026-08-17 | 2026-08-31 | 2026-09-05
134 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 23 | 2026-08-08 | 2026-08-17 | 2026-08-31 | 2026-09-05
135 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 23 | 2026-08-08 | 2026-08-17 | 2026-08-31 | 2026-09-05
136 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 23 | 2026-08-08 | 2026-08-17 | 2026-08-31 | 2026-09-05
137 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 23 | 2026-08-08 | 2026-08-17 | 2026-08-31 | 2026-09-05
138 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 23 | 2026-08-08 | 2026-08-17 | 2026-08-31 | 2026-09-05
139 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 23 | 2026-08-08 | 2026-08-17 | 2026-08-31 | 2026-09-05
140 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 25 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
141 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 24 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
142 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 25 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
143 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 24 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
144 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 25 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
145 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 24 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
146 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 25 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
147 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 24 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
148 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 25 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
149 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 24 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
150 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 25 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
151 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 24 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
152 | B3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 25 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
153 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 24 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
154 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 24 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
155 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 16 | 2026-07-23 | 2026-07-30 | 2026-08-14 | 2026-08-20
156 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 16 | 2026-07-23 | 2026-07-30 | 2026-08-14 | 2026-08-20
157 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 16 | 2026-07-23 | 2026-07-30 | 2026-08-14 | 2026-08-20
158 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 16 | 2026-07-23 | 2026-07-30 | 2026-08-14 | 2026-08-20
159 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 16 | 2026-07-23 | 2026-07-30 | 2026-08-14 | 2026-08-20
160 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 16 | 2026-07-23 | 2026-07-30 | 2026-08-14 | 2026-08-20
161 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 16 | 2026-07-23 | 2026-07-30 | 2026-08-14 | 2026-08-20
162 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 16 | 2026-07-23 | 2026-07-30 | 2026-08-14 | 2026-08-20
163 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 15 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04
164 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 15 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04
165 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 15 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04
166 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 15 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04
167 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 15 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04
168 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 15 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04
169 | A3 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 15 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04
170 | A2 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 8 | 2026-08-04 | 2026-08-12 | 2026-08-26 | 2026-09-01
171 | A2 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 8 | 2026-08-04 | 2026-08-12 | 2026-08-26 | 2026-09-01
172 | A2 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 8 | 2026-08-04 | 2026-08-12 | 2026-08-26 | 2026-09-01
173 | A2 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 8 | 2026-08-04 | 2026-08-12 | 2026-08-26 | 2026-09-01
174 | A2 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 8 | 2026-08-04 | 2026-08-12 | 2026-08-26 | 2026-09-01
175 | A2 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 7 | 2026-07-21 | 2026-07-28 | 2026-08-12 | 2026-08-18
176 | A2 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 7 | 2026-07-21 | 2026-07-28 | 2026-08-12 | 2026-08-18
177 | A2 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 7 | 2026-07-21 | 2026-07-28 | 2026-08-12 | 2026-08-18
178 | A2 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 7 | 2026-07-21 | 2026-07-28 | 2026-08-12 | 2026-08-18
179 | A2 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 7 | 2026-07-21 | 2026-07-28 | 2026-08-12 | 2026-08-18
180 | A2 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 7 | 2026-07-21 | 2026-07-28 | 2026-08-12 | 2026-08-18
181 | A2 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 7 | 2026-07-21 | 2026-07-28 | 2026-08-12 | 2026-08-18
182 | A2 |  | Precision | Axioma | 15mm |  |  | FALSE | Section 7 | 2026-07-21 | 2026-07-28 | 2026-08-12 | 2026-08-18
183 | A2 | 9993265 | Precision | Axioma | 15mm | 0.075 | 2026-06-13 | TRUE | Section 6 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04
184 | A2 | 10192025 | Precision | Axioma | 15mm | 0.067 | 2026-06-13 | TRUE | Section 6 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04
185 | A2 | 10192009 | Precision | Axioma | 15mm | 0.067 | 2026-06-13 | TRUE | Section 6 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04
186 | A2 | 10192013 | Precision | Axioma | 15mm | 0.066 | 2026-06-13 | TRUE | Section 6 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04
187 | A2 | 10192019 | Precision | Axioma | 15mm | 0.069 | 2026-06-13 | TRUE | Section 6 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04
188 | A2 | 10192018 | Precision | Axioma | 15mm | 0.068 | 2026-06-13 | TRUE | Section 6 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04
189 | A2 | 10192205 | Precision | Axioma | 15mm | 0.087 | 2026-06-13 | TRUE | Section 6 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04
190 | A2 | 10192011 | Precision | Axioma | 15mm | 0.069 | 2026-06-13 | TRUE | Section 6 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04
Lifestyle Cetre Meter 1 | A1 | 10228692 | Precision | Axioma | 25mm | 0.094 | 2026-05-29 | FALSE | Section 2 | 2026-04-22 | 2026-04-30 | 2026-05-15 | 2026-05-21
Lifestyle Cetre Meter 2 | A1 | 9279142 | Precision | Axioma | 32mm | 0.131 | 2026-04-24 | TRUE | Section 2 | 2026-04-22 | 2026-04-30 | 2026-05-15 | 2026-05-21

## Elec Meters
Stand Number | Section | Meter Serial | Parent Meter | Manufacturer | Meter Model | Connection size | Phase connected | Kiosk Number | Opening reading [kWh] | Meter Commission Date | AMR Installed | WBHO Subsection | Snag Date 1 | Snag Date 2 | Snag Date 3 | Snag Date 4
113 | A1 | 14558067907 | 71205556 | Hexing | HXP100DII | 1x80A | W | 3EVE3 | 0.53 | 2026-06-20 | FALSE | Section 1 | 2026-04-13 | 2026-04-20 | 2026-05-06 | 2026-05-12
115 | A1 | 14558067964 | 71205556 | Hexing | HXP100DII | 1x80A | R | 3EVE3 | 0 | 2026-06-20 | FALSE | Section 1 | 2026-04-13 | 2026-04-20 | 2026-05-06 | 2026-05-12
117 | A1 | 14558069713 | 71205556 | Hexing | HXP100DII | 1x80A | R | 2EVE3 | 0 | 2026-06-20 | FALSE | Section 1 | 2026-04-13 | 2026-04-20 | 2026-05-06 | 2026-05-12
119 | A1 | 14558069705 | 71205556 | Hexing | HXP100DII | 1x80A | B | 2EVE3 | 0 | 2026-06-20 | FALSE | Section 1 | 2026-04-13 | 2026-04-20 | 2026-05-06 | 2026-05-12
121 | A1 | 14558069762 | 71205556 | Hexing | HXP100DII | 1x80A | W | 2EVE3 | 0 | 2026-06-20 | FALSE | Section 1 | 2026-04-13 | 2026-04-20 | 2026-05-06 | 2026-05-12
123 | A1 | 14558069887 | 71205556 | Hexing | HXP100DII | 1x80A | R | 2EVE3 | 0 | 2026-06-20 | FALSE | Section 1 | 2026-04-13 | 2026-04-20 | 2026-05-06 | 2026-05-12
125 | A1 | 14558068111 | 71205556 | Hexing | HXP100DII | 1x80A | B | 1EVE3 | 0 | 2026-06-20 | TRUE | Section 1 | 2026-04-13 | 2026-04-20 | 2026-05-06 | 2026-05-12
127 | A1 | 14558068152 | 71205556 | Hexing | HXP100DII | 1x80A | R | 1EVE3 | 0 | 2026-06-20 | TRUE | Section 1 | 2026-04-13 | 2026-04-20 | 2026-05-06 | 2026-05-12
Clubhouse | A1 | 98819618 |  | Iskra | MT174D | 3x100A | RWB |  | 0 | 2026-06-09 | FALSE | Section 1 | 2026-04-13 | 2026-04-20 | 2026-05-06 | 2026-05-12
045 | B3 |  | 82929684 | Hexing | HXP100DII | 1x80A |  | 9EVE2 | 0 |  | FALSE | Section 10 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22
047 | B3 |  | 82929684 | Hexing | HXP100DII | 1x80A |  | 10EVE2 | 0 |  | FALSE | Section 10 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22
049 | B3 |  | 82929684 | Hexing | HXP100DII | 1x80A |  | 10EVE2 | 0 |  | FALSE | Section 10 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22
051 | B3 |  | 82929684 | Hexing | HXP100DII | 1x80A |  | 10EVE2 | 0 |  | FALSE | Section 10 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22
053 | B3 |  | 82929684 | Hexing | HXP100DII | 1x80A |  | 5EVE2 | 0 |  | FALSE | Section 10 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22
055 | B3 |  | 82929684 | Hexing | HXP100DII | 1x80A |  | 5EVE2 | 0 |  | FALSE | Section 10 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22
057 | B3 |  | 82929684 | Hexing | HXP100DII | 1x80A |  | 5EVE2 | 0 |  | FALSE | Section 10 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22
059 | B3 |  | 82929684 | Hexing | HXP100DII | 1x80A |  | 5EVE2 | 0 |  | FALSE | Section 10 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22
035 | B3 |  | 82929684 | Hexing | HXP100DII | 1x80A |  | 8EVE2 | 0 |  | FALSE | Section 11 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04
037 | B3 |  | 82929684 | Hexing | HXP100DII | 1x80A |  | 8EVE2 | 0 |  | FALSE | Section 11 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04
039 | B3 |  | 82929684 | Hexing | HXP100DII | 1x80A |  | 9EVE2 | 0 |  | FALSE | Section 11 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04
041 | B3 |  | 82929684 | Hexing | HXP100DII | 1x80A |  | 9EVE2 | 0 |  | FALSE | Section 11 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04
043 | B3 |  | 82929684 | Hexing | HXP100DII | 1x80A |  | 9EVE2 | 0 |  | FALSE | Section 11 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04
062 | A3 | 14558069341 | 82929684 | Hexing | HXP100DII | 1x80A | B | 4EVE2 | 0 | 2026-06-24 | FALSE | Section 12 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22
064 | A3 | 14558069200 | 82929684 | Hexing | HXP100DII | 1x80A | R | 4EVE2 | 0 | 2026-06-24 | FALSE | Section 12 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22
066 | A3 | 14558069168 | 82929684 | Hexing | HXP100DII | 1x80A | W | 4EVE2 | 0 | 2026-06-24 | FALSE | Section 12 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22
068 | A3 | 14558068244 | 82929684 | Hexing | HXP100DII | 1x80A | R | 3EVE2 | 0 | 2026-06-24 | FALSE | Section 12 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22
070 | A3 | 14558068228 | 82929684 | Hexing | HXP100DII | 1x80A | R | 3EVE2 | 0 | 2026-06-24 | FALSE | Section 12 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22
072 | A3 | 14558068442 | 82929684 | Hexing | HXP100DII | 1x80A | R | 3EVE2 | 0 | 2026-06-24 | FALSE | Section 12 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22
074 | A3 | 14558069317 | 82929684 | Hexing | HXP100DII | 1x80A | W | 3EVE2 | 0 | 2026-06-24 | FALSE | Section 12 | 2026-05-25 | 2026-06-01 | 2026-06-15 | 2026-06-22
046 | A3 |  | 82929684 | Hexing | HXP100DII | 1x80A |  | 10EVE2 | 0 |  | FALSE | Section 13 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04
048 | A3 |  | 82929684 | Hexing | HXP100DII | 1x80A |  | 10EVE2 | 0 |  | FALSE | Section 13 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04
050 | A3 |  | 82929684 | Hexing | HXP100DII | 1x80A |  | 10EVE2 | 0 |  | FALSE | Section 13 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04
052 | A3 |  | 82929684 | Hexing | HXP100DII | 1x80A |  | 5EVE2 | 0 |  | FALSE | Section 13 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04
054 | A3 |  | 82929684 | Hexing | HXP100DII | 1x80A |  | 5EVE2 | 0 |  | FALSE | Section 13 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04
056 | A3 |  | 82929684 | Hexing | HXP100DII | 1x80A |  | 5EVE2 | 0 |  | FALSE | Section 13 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04
058 | A3 | 14558069093 | 82929684 | Hexing | HXP100DII | 1x80A | R | 4EVE2 | 0 | 2026-06-24 | FALSE | Section 13 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04
060 | A3 | 14558069242 | 82929684 | Hexing | HXP100DII | 1x80A | W | 4EVE2 | 0 | 2026-06-24 | FALSE | Section 13 | 2026-06-06 | 2026-06-13 | 2026-06-29 | 2026-07-04
034 | A3 |  | 82929684 | Hexing | HXP100DII | 1x80A |  | 8EVE2 | 0 |  | FALSE | Section 14 | 2026-06-22 | 2026-06-29 | 2026-07-18 | 2026-07-18
036 | A3 |  | 82929684 | Hexing | HXP100DII | 1x80A |  | 8EVE2 | 0 |  | FALSE | Section 14 | 2026-06-22 | 2026-06-29 | 2026-07-18 | 2026-07-18
038 | A3 |  | 82929684 | Hexing | HXP100DII | 1x80A |  | 9EVE2 | 0 |  | FALSE | Section 14 | 2026-06-22 | 2026-06-29 | 2026-07-18 | 2026-07-18
040 | A3 |  | 82929684 | Hexing | HXP100DII | 1x80A |  | 9EVE2 | 0 |  | FALSE | Section 14 | 2026-06-22 | 2026-06-29 | 2026-07-18 | 2026-07-18
042 | A3 |  | 82929684 | Hexing | HXP100DII | 1x80A |  | 9EVE2 | 0 |  | FALSE | Section 14 | 2026-06-22 | 2026-06-29 | 2026-07-18 | 2026-07-18
044 | A3 |  | 82929684 | Hexing | HXP100DII | 1x80A |  | 9EVE2 | 0 |  | FALSE | Section 14 | 2026-06-22 | 2026-06-29 | 2026-07-18 | 2026-07-18
163 | A3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 2EVE1 | 0 |  | FALSE | Section 15 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04
164 | A3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 2EVE1 | 0 |  | FALSE | Section 15 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04
165 | A3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 2EVE1 | 0 |  | FALSE | Section 15 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04
166 | A3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 2EVE1 | 0 |  | FALSE | Section 15 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04
167 | A3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 2EVE1 | 0 |  | FALSE | Section 15 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04
168 | A3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 2EVE1 | 0 |  | FALSE | Section 15 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04
169 | A3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 2EVE1 | 0 |  | FALSE | Section 15 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04
155 | A3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 1EVE1 | 0 |  | FALSE | Section 16 | 2026-07-23 | 2026-07-30 | 2026-08-14 | 2026-08-20
156 | A3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 1EVE1 | 0 |  | FALSE | Section 16 | 2026-07-23 | 2026-07-30 | 2026-08-14 | 2026-08-20
157 | A3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 1EVE1 | 0 |  | FALSE | Section 16 | 2026-07-23 | 2026-07-30 | 2026-08-14 | 2026-08-20
158 | A3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 1EVE1 | 0 |  | FALSE | Section 16 | 2026-07-23 | 2026-07-30 | 2026-08-14 | 2026-08-20
159 | A3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 1EVE1 | 0 |  | FALSE | Section 16 | 2026-07-23 | 2026-07-30 | 2026-08-14 | 2026-08-20
160 | A3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 1EVE1 | 0 |  | FALSE | Section 16 | 2026-07-23 | 2026-07-30 | 2026-08-14 | 2026-08-20
161 | A3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 1EVE1 | 0 |  | FALSE | Section 16 | 2026-07-23 | 2026-07-30 | 2026-08-14 | 2026-08-20
162 | A3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 1EVE1 | 0 |  | FALSE | Section 16 | 2026-07-23 | 2026-07-30 | 2026-08-14 | 2026-08-20
017 | B3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 4EVE1 | 0 |  | FALSE | Section 17 | 2026-06-24 | 2026-07-01 | 2026-07-15 | 2026-07-21
019 | B3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 5EVE1 | 0 |  | FALSE | Section 17 | 2026-06-24 | 2026-07-01 | 2026-07-15 | 2026-07-21
021 | B3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 5EVE1 | 0 |  | FALSE | Section 17 | 2026-06-24 | 2026-07-01 | 2026-07-15 | 2026-07-21
023 | B3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 5EVE1 | 0 |  | FALSE | Section 17 | 2026-06-24 | 2026-07-01 | 2026-07-15 | 2026-07-21
025 | B3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 6EVE1 | 0 |  | FALSE | Section 17 | 2026-06-24 | 2026-07-01 | 2026-07-15 | 2026-07-21
027 | B3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 6EVE1 | 0 |  | FALSE | Section 17 | 2026-06-24 | 2026-07-01 | 2026-07-15 | 2026-07-21
029 | B3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 6EVE1 | 0 |  | FALSE | Section 17 | 2026-06-24 | 2026-07-01 | 2026-07-15 | 2026-07-21
031 | B3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 6EVE1 | 0 |  | FALSE | Section 17 | 2026-06-24 | 2026-07-01 | 2026-07-15 | 2026-07-21
003 | B3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 3EVE1 | 0 |  | FALSE | Section 18 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06
005 | B3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 3EVE1 | 0 |  | FALSE | Section 18 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06
007 | B3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 3EVE1 | 0 |  | FALSE | Section 18 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06
009 | B3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 3EVE1 | 0 |  | FALSE | Section 18 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06
011 | B3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 4EVE1 | 0 |  | FALSE | Section 18 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06
013 | B3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 4EVE1 | 0 |  | FALSE | Section 18 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06
015 | B3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 4EVE1 | 0 |  | FALSE | Section 18 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06
020 | A3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 5EVE1 | 0 |  | FALSE | Section 19 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
022 | A3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 5EVE1 | 0 |  | FALSE | Section 19 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
024 | A3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 5EVE1 | 0 |  | FALSE | Section 19 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
026 | A3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 6EVE1 | 0 |  | FALSE | Section 19 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
028 | A3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 6EVE1 | 0 |  | FALSE | Section 19 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
030 | A3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 6EVE1 | 0 |  | FALSE | Section 19 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
032 | A3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 6EVE1 | 0 |  | FALSE | Section 19 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
033 | A3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 6EVE1 | 0 |  | FALSE | Section 19 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
093 | A1 | 14558069796 | 71205556 | Hexing | HXP100DII | 1x80A | W | 5EVE3 | 0.01 | 2026-06-22 | TRUE | Section 2 | 2026-04-22 | 2026-04-30 | 2026-05-15 | 2026-05-21
095 | A1 | 14558069945 | 71205556 | Hexing | HXP100DII | 1x80A | R | 5EVE3 | 0 | 2026-06-22 | TRUE | Section 2 | 2026-04-22 | 2026-04-30 | 2026-05-15 | 2026-05-21
097 | A1 | 14558068194 | 71205556 | Hexing | HXP100DII | 1x80A | W | 4EVE3 | 1.09 | 2026-06-22 | TRUE | Section 2 | 2026-04-22 | 2026-04-30 | 2026-05-15 | 2026-05-21
099 | A1 | 14558068178 | 71205556 | Hexing | HXP100DII | 1x80A | R | 4EVE3 | 1.11 | 2026-06-22 | TRUE | Section 2 | 2026-04-22 | 2026-04-30 | 2026-05-15 | 2026-05-21
101 | A1 | 14558068160 | 71205556 | Hexing | HXP100DII | 1x80A | B | 4EVE3 | 0.38 | 2026-06-22 | TRUE | Section 2 | 2026-04-22 | 2026-04-30 | 2026-05-15 | 2026-05-21
103 | A1 | 14558068285 | 71205556 | Hexing | HXP100DII | 1x80A | W | 4EVE3 | 1.37 | 2026-06-22 | TRUE | Section 2 | 2026-04-22 | 2026-04-30 | 2026-05-15 | 2026-05-21
105 | A1 | 14558068301 | 71205556 | Hexing | HXP100DII | 1x80A | R | 4EVE3 | 1.63 | 2026-06-22 | TRUE | Section 2 | 2026-04-22 | 2026-04-30 | 2026-05-15 | 2026-05-21
107 | A1 | 14558067899 | 71205556 | Hexing | HXP100DII | 1x80A | W | 3EVE3 | 0.02 | 2026-06-20 | FALSE | Section 2 | 2026-04-22 | 2026-04-30 | 2026-05-15 | 2026-05-21
109 | A1 | 14558067873 | 71205556 | Hexing | HXP100DII | 1x80A | R | 3EVE3 | 0.04 | 2026-06-20 | FALSE | Section 2 | 2026-04-22 | 2026-04-30 | 2026-05-15 | 2026-05-21
111 | A1 | 14558067881 | 71205556 | Hexing | HXP100DII | 1x80A | B | 3EVE3 | 0.55 | 2026-06-20 | FALSE | Section 2 | 2026-04-22 | 2026-04-30 | 2026-05-15 | 2026-05-21
001 | A3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 3EVE1 | 0 |  | FALSE | Section 20 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
002 | A3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 3EVE1 | 0 |  | FALSE | Section 20 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
004 | A3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 3EVE1 | 0 |  | FALSE | Section 20 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
006 | A3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 3EVE1 | 0 |  | FALSE | Section 20 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
008 | A3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 3EVE1 | 0 |  | FALSE | Section 20 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
010 | A3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 4EVE1 | 0 |  | FALSE | Section 20 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
012 | A3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 4EVE1 | 0 |  | FALSE | Section 20 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
014 | A3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 4EVE1 | 0 |  | FALSE | Section 20 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
016 | A3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 4EVE1 | 0 |  | FALSE | Section 20 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
018 | A3 |  | 82929702 | Hexing | HXP100DII | 1x80A |  | 4EVE1 | 0 |  | FALSE | Section 20 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
104 | B3 | 14558068376 | 71205556 | Hexing | HXP100DII | 1x80A | B | 3EVE3 | 0 | 2026-06-20 | FALSE | Section 21 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06
106 | B3 | 14558068293 | 71205556 | Hexing | HXP100DII | 1x80A | W | 3EVE3 | 0 | 2026-06-20 | FALSE | Section 21 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06
108 | B3 | 14558068277 | 71205556 | Hexing | HXP100DII | 1x80A | R | 3EVE3 | 0 | 2026-06-20 | FALSE | Section 21 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06
110 | B3 | 14558068202 | 71205556 | Hexing | HXP100DII | 1x80A | B | 3EVE3 | 0 | 2026-06-20 | FALSE | Section 21 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06
112 | B3 | 14558068053 | 71205556 | Hexing | HXP100DII | 1x80A | B | 2EVE3 | 0 | 2026-06-20 | FALSE | Section 21 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06
114 | B3 | 14558068004 | 71205556 | Hexing | HXP100DII | 1x80A | W | 2EVE3 | 0.16 | 2026-06-20 | FALSE | Section 21 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06
116 | B3 | 14558068079 | 71205556 | Hexing | HXP100DII | 1x80A | R | 2EVE3 | 0 | 2026-06-20 | FALSE | Section 21 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06
118 | B3 | 14558068095 | 71205556 | Hexing | HXP100DII | 1x80A | B | 2EVE3 | 0 | 2026-06-20 | FALSE | Section 21 | 2026-07-10 | 2026-07-17 | 2026-07-31 | 2026-08-06
120 | B3 | 14558069663 | 71205556 | Hexing | HXP100DII | 1x80A | W | 2EVE3 | 0 | 2026-06-20 | FALSE | Section 22 | 2026-07-24 | 2026-07-31 | 2026-08-15 | 2026-08-21
122 | B3 | 14558069432 | 71205556 | Hexing | HXP100DII | 1x80A | W | 1EVE3 | 0 | 2026-06-20 | FALSE | Section 22 | 2026-07-24 | 2026-07-31 | 2026-08-15 | 2026-08-21
124 | B3 | 14558068020 | 71205556 | Hexing | HXP100DII | 1x80A | B | 1EVE3 | 0 | 2026-06-20 | TRUE | Section 22 | 2026-07-24 | 2026-07-31 | 2026-08-15 | 2026-08-21
126 | B3 | 14558069846 | 71205556 | Hexing | HXP100DII | 1x80A | W | 1EVE3 | 0 | 2026-06-20 | FALSE | Section 22 | 2026-07-24 | 2026-07-31 | 2026-08-15 | 2026-08-21
128 | B3 | 14558069804 | 71205556 | Hexing | HXP100DII | 1x80A | R | 1EVE3 | 0 | 2026-06-20 | FALSE | Section 22 | 2026-07-24 | 2026-07-31 | 2026-08-15 | 2026-08-21
129 | B3 | 14558069671 | 71205556 | Hexing | HXP100DII | 1x80A | B | 1EVE3 | 0 | 2026-06-20 | FALSE | Section 22 | 2026-07-24 | 2026-07-31 | 2026-08-15 | 2026-08-21
130 | B3 | 14558067949 | 71205556 | Hexing | HXP100DII | 1x80A | W | 1EVE3 | 0 | 2026-06-20 | FALSE | Section 22 | 2026-07-24 | 2026-07-31 | 2026-08-15 | 2026-08-21
131 | B3 | 14558068335 | 71205556 | Hexing | HXP100DII | 1x80A | R | 1EVE3 | 0 | 2026-06-20 | TRUE | Section 22 | 2026-07-24 | 2026-07-31 | 2026-08-15 | 2026-08-21
132 | B3 |  | 71205556 | Hexing | HXP100DII | 1x80A |  | 9EVE3 | 0 |  | FALSE | Section 23 | 2026-08-08 | 2026-08-17 | 2026-08-31 | 2026-09-05
133 | B3 |  | 71205556 | Hexing | HXP100DII | 1x80A |  | 9EVE3 | 0 |  | FALSE | Section 23 | 2026-08-08 | 2026-08-17 | 2026-08-31 | 2026-09-05
134 | B3 |  | 71205556 | Hexing | HXP100DII | 1x80A |  | 9EVE3 | 0 |  | FALSE | Section 23 | 2026-08-08 | 2026-08-17 | 2026-08-31 | 2026-09-05
135 | B3 |  | 71205556 | Hexing | HXP100DII | 1x80A |  | 9EVE3 | 0 |  | FALSE | Section 23 | 2026-08-08 | 2026-08-17 | 2026-08-31 | 2026-09-05
136 | B3 |  | 71205556 | Hexing | HXP100DII | 1x80A |  | 9EVE3 | 0 |  | FALSE | Section 23 | 2026-08-08 | 2026-08-17 | 2026-08-31 | 2026-09-05
137 | B3 |  | 71205556 | Hexing | HXP100DII | 1x80A |  | 9EVE3 | 0 |  | FALSE | Section 23 | 2026-08-08 | 2026-08-17 | 2026-08-31 | 2026-09-05
138 | B3 |  | 71205556 | Hexing | HXP100DII | 1x80A |  | 9EVE3 | 0 |  | FALSE | Section 23 | 2026-08-08 | 2026-08-17 | 2026-08-31 | 2026-09-05
139 | B3 |  | 71205556 | Hexing | HXP100DII | 1x80A |  | 9EVE3 | 0 |  | FALSE | Section 23 | 2026-08-08 | 2026-08-17 | 2026-08-31 | 2026-09-05
141 | A3 |  | 71205556 | Hexing | HXP100DII | 1x80A |  | 10EVE3 | 0 |  | FALSE | Section 24 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
143 | A3 |  | 71205556 | Hexing | HXP100DII | 1x80A |  | 10EVE3 | 0 |  | FALSE | Section 24 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
145 | A3 |  | 71205556 | Hexing | HXP100DII | 1x80A |  | 10EVE3 | 0 |  | FALSE | Section 24 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
147 | A3 |  | 71205556 | Hexing | HXP100DII | 1x80A |  | 10EVE3 | 0 |  | FALSE | Section 24 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
149 | A3 |  | 71205556 | Hexing | HXP100DII | 1x80A |  | 11EVE3 | 0 |  | FALSE | Section 24 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
151 | A3 |  | 71205556 | Hexing | HXP100DII | 1x80A |  | 11EVE3 | 0 |  | FALSE | Section 24 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
153 | A3 |  | 71205556 | Hexing | HXP100DII | 1x80A |  | 11EVE3 | 0 |  | FALSE | Section 24 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
154 | A3 |  | 71205556 | Hexing | HXP100DII | 1x80A |  | 11EVE3 | 0 |  | FALSE | Section 24 | 2026-08-25 | 2026-09-01 | 2026-09-15 | 2026-09-21
140 | B3 |  | 71205556 | Hexing | HXP100DII | 1x80A |  | 10EVE3 | 0 |  | FALSE | Section 25 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
142 | B3 |  | 71205556 | Hexing | HXP100DII | 1x80A |  | 10EVE3 | 0 |  | FALSE | Section 25 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
144 | B3 |  | 71205556 | Hexing | HXP100DII | 1x80A |  | 10EVE3 | 0 |  | FALSE | Section 25 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
146 | B3 |  | 71205556 | Hexing | HXP100DII | 1x80A |  | 11EVE3 | 0 |  | FALSE | Section 25 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
148 | B3 |  | 71205556 | Hexing | HXP100DII | 1x80A |  | 11EVE3 | 0 |  | FALSE | Section 25 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
150 | B3 |  | 71205556 | Hexing | HXP100DII | 1x80A |  | 11EVE3 | 0 |  | FALSE | Section 25 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
152 | B3 |  | 71205556 | Hexing | HXP100DII | 1x80A |  | 11EVE3 | 0 |  | FALSE | Section 25 | 2026-09-08 | 2026-09-15 | 2026-09-30 | 2026-10-06
087 | B2 | 14558069069 | 71205556 | Hexing | HXP100DII | 1x80A | R | 8EVE3 | 0 | 2026-06-23 | FALSE | Section 3 | 2026-05-13 | 2026-05-20 | 2026-06-03 | 2026-06-09
088 | B2 | 14558069333 | 71205556 | Hexing | HXP100DII | 1x80A | W | 8EVE3 | 0 | 2026-06-23 | FALSE | Section 3 | 2026-05-13 | 2026-05-20 | 2026-06-03 | 2026-06-09
089 | B2 | 14558069937 | 71205556 | Hexing | HXP100DII | 1x80A | R | 7EVE3 | 0 | 2026-06-23 | TRUE | Section 3 | 2026-05-13 | 2026-05-20 | 2026-06-03 | 2026-06-09
090 | B2 | 14558070059 | 71205556 | Hexing | HXP100DII | 1x80A | W | 7EVE3 | 0 | 2026-06-23 | TRUE | Section 3 | 2026-05-13 | 2026-05-20 | 2026-06-03 | 2026-06-09
091 | B2 | 14558068343 | 71205556 | Hexing | HXP100DII | 1x80A | B | 7EVE3 | 0 | 2026-06-23 | TRUE | Section 3 | 2026-05-13 | 2026-05-20 | 2026-06-03 | 2026-06-09
080 | A2 | 14558068806 | 71205556 | Hexing | HXP100DII | 1x80A |  | 8EVE3 | 0 | 2026-06-25 | FALSE | Section 4 | 2026-06-02 | 2026-06-09 | 2026-06-24 | 2026-06-30
081 | A2 | 14558069127 | 71205556 | Hexing | HXP100DII | 1x80A | W | 8EVE3 | 0 | 2026-06-23 | FALSE | Section 4 | 2026-06-02 | 2026-06-09 | 2026-06-24 | 2026-06-30
082 | A2 | 14558069077 | 71205556 | Hexing | HXP100DII | 1x80A | R | 8EVE3 | 0 | 2026-06-23 | FALSE | Section 4 | 2026-06-02 | 2026-06-09 | 2026-06-24 | 2026-06-30
083 | A2 | 14558068251 | 71205556 | Hexing | HXP100DII | 1x80A | B | 8EVE3 | 0 | 2026-06-23 | FALSE | Section 4 | 2026-06-02 | 2026-06-09 | 2026-06-24 | 2026-06-30
084 | A2 | 14558068210 | 71205556 | Hexing | HXP100DII | 1x80A | W | 8EVE3 | 0 | 2026-06-23 | FALSE | Section 4 | 2026-06-02 | 2026-06-09 | 2026-06-24 | 2026-06-30
085 | A2 | 14558069853 | 71205556 | Hexing | HXP100DII | 1x80A | R | 8EVE3 | 0 | 2026-06-23 | FALSE | Section 4 | 2026-06-02 | 2026-06-09 | 2026-06-24 | 2026-06-30
086 | A2 | 14558069911 | 71205556 | Hexing | HXP100DII | 1x80A | B | 8EVE3 | 0 | 2026-06-23 | FALSE | Section 4 | 2026-06-02 | 2026-06-09 | 2026-06-24 | 2026-06-30
076 | A2 | 14558068954 | 82929684 | Hexing | HXP100DII | 1x80A | R | 2EVE2 | 0 | 2026-06-25 | FALSE | Section 5 | 2026-06-17 | 2026-06-24 | 2026-07-08 | 2026-07-14
077 | A2 | 14558068764 | 82929684 | Hexing | HXP100DII | 1x80A | W | 2EVE2 | 0 |  | FALSE | Section 5 | 2026-06-17 | 2026-06-24 | 2026-07-08 | 2026-07-14
078 | A2 | 14558068822 | 82929684 | Hexing | HXP100DII | 1x80A | B | 2EVE2 | 0 |  | FALSE | Section 5 | 2026-06-17 | 2026-06-24 | 2026-07-08 | 2026-07-14
079 | A2 | 14558068848 | 82929684 | Hexing | HXP100DII | 1x80A | R | 2EVE2 | 0 |  | FALSE | Section 5 | 2026-06-17 | 2026-06-24 | 2026-07-08 | 2026-07-14
092 | B2 | 14558068186 | 71205556 | Hexing | HXP100DII | 1x80A | W | 5EVE3 | 0.04 | 2026-06-22 | TRUE | Section 5 | 2026-04-28 | 2026-05-06 | 2026-05-20 | 2026-05-26
094 | B2 | 14558068319 | 71205556 | Hexing | HXP100DII | 1x80A | R | 5EVE3 | 1.56 | 2026-06-22 | TRUE | Section 5 | 2026-04-28 | 2026-05-06 | 2026-05-20 | 2026-05-26
096 | B2 | 14558069952 | 71205556 | Hexing | HXP100DII | 1x80A | B | 5EVE3 | 0.01 | 2026-06-22 | TRUE | Section 5 | 2026-04-28 | 2026-05-06 | 2026-05-20 | 2026-05-26
098 | B2 | 14558068236 | 71205556 | Hexing | HXP100DII | 1x80A | B | 4EVE3 | 4.23 | 2026-06-22 | TRUE | Section 5 | 2026-04-28 | 2026-05-06 | 2026-05-20 | 2026-05-26
100 | B2 | 14558068368 | 71205556 | Hexing | HXP100DII | 1x80A | W | 4EVE3 | 5.23 | 2026-06-22 | TRUE | Section 5 | 2026-04-28 | 2026-05-06 | 2026-05-20 | 2026-05-26
102 | B2 | 14558068392 | 71205556 | Hexing | HXP100DII | 1x80A | R | 4EVE3 | 2.74 | 2026-06-22 | TRUE | Section 5 | 2026-04-28 | 2026-05-06 | 2026-05-20 | 2026-05-26
183 | A2 |  | 82929684 | Hexing | HXP100DII | 1x80A |  | 1EVE2 | 0 |  | FALSE | Section 6 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04
184 | A2 |  | 82929684 | Hexing | HXP100DII | 1x80A |  | 1EVE2 | 0 |  | FALSE | Section 6 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04
185 | A2 |  | 82929684 | Hexing | HXP100DII | 1x80A |  | 1EVE2 | 0 |  | FALSE | Section 6 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04
186 | A2 |  | 82929684 | Hexing | HXP100DII | 1x80A |  | 1EVE2 | 0 |  | FALSE | Section 6 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04
187 | A2 |  | 82929684 | Hexing | HXP100DII | 1x80A |  | 1EVE2 | 0 |  | FALSE | Section 6 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04
188 | A2 | 14558069291 | 82929684 | Hexing | HXP100DII | 1x80A | R | 2EVE2 | 0 | 2026-06-25 | FALSE | Section 6 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04
189 | A2 | 14558069036 | 82929684 | Hexing | HXP100DII | 1x80A | W | 2EVE2 | 0 | 2026-06-25 | FALSE | Section 6 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04
190 | A2 | 14558068897 | 82929684 | Hexing | HXP100DII | 1x80A | B | 2EVE2 | 0 | 2026-06-25 | FALSE | Section 6 | 2026-07-08 | 2026-07-15 | 2026-07-29 | 2026-08-04
175 | A2 |  | 82929684 | Hexing | HXP100DII | 1x80A |  | 7EVE2 | 0 |  | FALSE | Section 7 | 2026-07-21 | 2026-07-28 | 2026-08-12 | 2026-08-18
176 | A2 |  | 82929684 | Hexing | HXP100DII | 1x80A |  | 6EVE2 | 0 |  | FALSE | Section 7 | 2026-07-21 | 2026-07-28 | 2026-08-12 | 2026-08-18
177 | A2 |  | 82929684 | Hexing | HXP100DII | 1x80A |  | 6EVE2 | 0 |  | FALSE | Section 7 | 2026-07-21 | 2026-07-28 | 2026-08-12 | 2026-08-18
178 | A2 |  | 82929684 | Hexing | HXP100DII | 1x80A |  | 6EVE2 | 0 |  | FALSE | Section 7 | 2026-07-21 | 2026-07-28 | 2026-08-12 | 2026-08-18
179 | A2 |  | 82929684 | Hexing | HXP100DII | 1x80A |  | 6EVE2 | 0 |  | FALSE | Section 7 | 2026-07-21 | 2026-07-28 | 2026-08-12 | 2026-08-18
180 | A2 |  | 82929684 | Hexing | HXP100DII | 1x80A |  | 6EVE2 | 0 |  | FALSE | Section 7 | 2026-07-21 | 2026-07-28 | 2026-08-12 | 2026-08-18
181 | A2 |  | 82929684 | Hexing | HXP100DII | 1x80A |  | 6EVE2 | 0 |  | FALSE | Section 7 | 2026-07-21 | 2026-07-28 | 2026-08-12 | 2026-08-18
182 | A2 |  | 82929684 | Hexing | HXP100DII | 1x80A |  | 1EVE2 | 0 |  | FALSE | Section 7 | 2026-07-21 | 2026-07-28 | 2026-08-12 | 2026-08-18
170 | A4 |  | 82929684 | Hexing | HXP100DII | 1x80A |  | 7EVE2 | 0 |  | FALSE | Section 8 | 2026-08-04 | 2026-08-12 | 2026-08-26 | 2026-09-01
171 | A2 |  | 82929684 | Hexing | HXP100DII | 1x80A |  | 7EVE2 | 0 |  | FALSE | Section 8 | 2026-08-04 | 2026-08-12 | 2026-08-26 | 2026-09-01
172 | A2 |  | 82929684 | Hexing | HXP100DII | 1x80A |  | 7EVE2 | 0 |  | FALSE | Section 8 | 2026-08-04 | 2026-08-12 | 2026-08-26 | 2026-09-01
173 | A2 |  | 82929684 | Hexing | HXP100DII | 1x80A |  | 7EVE2 | 0 |  | FALSE | Section 8 | 2026-08-04 | 2026-08-12 | 2026-08-26 | 2026-09-01
174 | A2 |  | 82929684 | Hexing | HXP100DII | 1x80A |  | 7EVE2 | 0 |  | FALSE | Section 8 | 2026-08-04 | 2026-08-12 | 2026-08-26 | 2026-09-01
061 | B3 | 14558070083 | 82929684 | Hexing | HXP100DII | 1x80A | B | 4EVE2 | 0 | 2026-06-24 | FALSE | Section 9 | 2026-05-11 | 2026-05-18 | 2026-06-01 | 2026-06-06
063 | B3 | 14558068384 | 82929684 | Hexing | HXP100DII | 1x80A | W | 4EVE2 | 0 | 2026-06-24 | FALSE | Section 9 | 2026-05-11 | 2026-05-18 | 2026-06-01 | 2026-06-06
065 | B3 | 14558067972 | 82929684 | Hexing | HXP100DII | 1x80A | R | 4EVE2 | 0 | 2026-06-24 | FALSE | Section 9 | 2026-05-11 | 2026-05-18 | 2026-06-01 | 2026-06-06
067 | B3 | 14558069267 | 82929684 | Hexing | HXP100DII | 1x80A | B | 4EVE2 | 0 | 2026-06-24 | FALSE | Section 9 | 2026-05-11 | 2026-05-18 | 2026-06-01 | 2026-06-06
069 | B3 | 14558070026 | 82929684 | Hexing | HXP100DII | 1x80A | W | 3EVE2 | 0 | 2026-06-24 | FALSE | Section 9 | 2026-05-11 | 2026-05-18 | 2026-06-01 | 2026-06-06
071 | B3 | 14558069176 | 82929684 | Hexing | HXP100DII | 1x80A | B | 3EVE2 | 0 | 2026-06-24 | FALSE | Section 9 | 2026-05-11 | 2026-05-18 | 2026-06-01 | 2026-06-06
073 | B3 | 14558070000 | 82929684 | Hexing | HXP100DII | 1x80A | B | 3EVE2 | 0 | 2026-06-24 | FALSE | Section 9 | 2026-05-11 | 2026-05-18 | 2026-06-01 | 2026-06-06
075 | B3 | 14558070109 | 82929684 | Hexing | HXP100DII | 1x80A | B | 3EVE2 | 0 | 2026-06-24 | FALSE | Section 9 | 2026-05-11 | 2026-05-18 | 2026-06-01 | 2026-06-06

## Kiosk Plan
Minisub | MS Serial | Kiosk Number | Original Planned |  |  | New planned units |  |  |  | Comments
|  |  | Uits fed | 8 probe | 16 probe | Updated units fed | 8 probe | 16 probe | Inc/dec units
1 | 82929702 | 1EVE1 | 8 | 1 | 0 | 8 | 1 | 0 | 0
1 | 82929702 | 2EVE1 | 7 | 1 | 0 | 7 | 1 | 0 | 0
1 | 82929702 | 3EVE1 | 9 | 0 | 1 | 9 | 0 | 1 | 0
1 | 82929702 | 4EVE1 | 9 | 0 | 1 | 9 | 0 | 1 | 0
1 | 82929702 | 5EVE1 | 6 | 1 | 0 | 6 | 1 | 0 | 0
1 | 82929702 | 6EVE1 | 9 | 0 | 1 | 9 | 0 | 1 | 0
2 | 82929684 | 1EVE2 | 6 | 1 | 0 | 6 | 1 | 0 | 0
2 | 82929684 | 2EVE2 | 8 | 1 | 0 | 7 | 1 | 0 | -1 | One less Unit fed
2 | 82929684 | 3EVE2 | 9 | 0 | 1 | 8 | 1 | 0 | -1 | One less Unit fed
2 | 82929684 | 4EVE2 | 9 | 0 | 1 | 9 | 0 | 1 | 0
2 | 82929684 | 5EVE2 | 7 | 1 | 0 | 7 | 1 | 0 | 0
2 | 82929684 | 6EVE2 | 6 | 1 | 0 | 6 | 1 | 0 | 0
2 | 82929684 | 7EVE2 | 6 | 1 | 0 | 6 | 1 | 0 | 0
2 | 82929684 | 8EVE2 | 6 | 1 | 0 | 4 | 1 | 0 | -2 | 2 less units fed
2 | 82929684 | 9EVE2 | 8 | 1 | 0 | 8 | 1 | 0 | 0
2 | 82929684 | 10EVE2 | 6 | 1 | 0 | 6 | 1 | 0 | 0
3 | 71205556 | 1EVE3 | 9 | 0 | 1 | 9 | 0 | 1 | 0
3 | 71205556 | 2EVE3 | 9 | 0 | 1 | 9 | 0 | 1 | 0
3 | 71205556 | 3EVE3 | 9 | 0 | 1 | 9 | 0 | 1 | 0
3 | 71205556 | 4EVE3 | 9 | 0 | 1 | 8 | 1 | 0 | -1 | One less Unit fed
3 | 71205556 | 5EVE3 | 9 | 0 | 1 | 5 | 1 | 0 | -4 | 4 less units fed
3 | 71205556 | 6EVE3 | 9 | 0 | 1 | 0 | 0 | 0 | -9 | Kiosk removed
3 | 71205556 | 7EVE3 | 9 | 0 | 1 | 3 | 1 | 0 | -6 | 6 less units
3 | 71205556 | 8EVE3 | 8 | 1 | 0 | 9 | 0 | 1 | 1 | one additional unit
3 | 71205556 | 9EVE3 | 0 | 0 | 0 | 8 | 1 | 0 | 8 | New additional kiosk
3 | 71205556 | 10EVE3 | 0 | 0 | 0 | 7 | 1 | 0 | 7 | New additional kiosk
3 | 71205556 | 11EVE3 | 0 | 0 | 0 | 8 | 1 | 0 | 8 | New additional kiosk
|  |  | 190 | 12 | 12 | 190 | 18 | 8
|  |  |  | 24 |  |  | 26

## Temp ME162 open and closings
Erf | Section | Meter serial number | Opening readings | Closing Readings | Usage [WBHO]
22 | A | 67573323 | 19375.9 |  | -19375.9
44 | A | 67021362 | 56032.6 |  | -56032.6
53 | A | 67573216 | 17968.5 |  | -17968.5
58 | B | 42607693 | 59659 |  | -59659
60 | B | 42607645 | 97390 |  | -97390
61 | B | 42607493 | 23184 |  | -23184
62 | B | 42607616 | 7889 |  | -7889
63 | B | 42607457 | 27096 |  | -27096
64 | B | 42607809 | 15280 |  | -15280
65 | B | 42607653 | 20310 |  | -20310
66 | B | 42607631 | 24100 |  | -24100
67 | B | 46886910 | 172161.6 |  | -172161.6
68 | B | 42607609 | 11718 | 11718 | 0
69 | B | 47512547 | 38143 | 38145 | 2
70 | B | 47511635 | 35381.2 | 35381.2 | 0
71 | B | 4260700 | 179707 | 179707 | 0
72 | B | 46886909 | 103115.8 | 103121.8 | 6
73 | B | 47369448 | Cant see readings clearly |  | #VALUE!
74 | B | 47511330 | 72558.4 | 72558.4 | 0
75 | B | 42607467 | 12607 | 12608 | 1
87 | B | 67021344 | 30522 |  | -30522
88 | B | 67021354 | 42174 |  | -42174
89 | B | 91546861 | 0 |  | 0
90 | B | 66599353 | 0 |  | 0
91 | B | 87778411 | 0 |  | 0
92 | B | 67573171 | 55276.2 | 55295.6 | 19.4
93 | A | 90007553 | 1076.4 | 1234.5 | 158.1
94 | B | 67573207 | 26813.1 | 26832.8 | 19.7
95 | A | 42607759 | 26313 | 139657 | 113344
96 | B | 67573298 | 16956.2 | 16978.1 | 21.9
97 | A | 67573203 | 36948.8 | Display dead | #VALUE!
98 | B | 67573191 | 43330.5 |  | -43330.5
99 | A | 67572944 | 21735.7 | 21789.1 | 53.4
100 | B | 67573201 | 28815.3 |  | -28815.3
101 | A | 67021339 | 30210.7 | 30259.5 | 48.8
102 | B | 90008040 | 1849.3 | 1881.8 | 32.5
103 | A | 46886935 | 82275 | 82330 | 55
105 | A | 67572955 | 28976.3 | 29012.7 | 36.4
107 | A | 42607429 | 19376 |  | -19376
109 | A | 67021338 | 29281.6 | 29406.1 | 124.5
111 | A | 42607771 | 5509 | 5516 | 7
113 | A | 67573205 | 38016.9 | 38086 | 69.1
115 | A | 67573265 | 71144.2 | 71214.8 | 70.6
117 | A | 66599401 | 63803.5 | 63860.4 | 56.9
119 | A | 67573188 | 29124.2 | 29208.6 | 84.4
121 | A | 84039773 | 9600.1 | 9668.1 | 68
123 | A | 67573376 | 89289.8 | 89352.7 | 62.9
125 | A | 67573196 | 89182.7 | 89225.2 | 42.5
127 | A | 67573307 | 25290.8 | 25372.1 | 81.3
163 | A | 70694930 | 35892.8 |  | -35892.8

## Elec Meters for invoicing
Electricity Meters To be Invoiced
Stand Number | Section | Meter Serial | Parent Meter | Manufacturer | Meter Model | Connection size | Phase connected | Kiosk Number | Meter Commission Date | Opening reading [kWh]
093 | A1 | 14558069796 | 71205556 | Hexing | HXP100DII | 1x80A | W | 5EVE3 | 2026-06-22 | 0.01
095 | A1 | 14558069945 | 71205556 | Hexing | HXP100DII | 1x80A | R | 5EVE3 | 2026-06-22 | 0
097 | A1 | 14558068194 | 71205556 | Hexing | HXP100DII | 1x80A | W | 4EVE3 | 2026-06-22 | 1.09
099 | A1 | 14558068178 | 71205556 | Hexing | HXP100DII | 1x80A | R | 4EVE3 | 2026-06-22 | 1.11
101 | A1 | 14558068160 | 71205556 | Hexing | HXP100DII | 1x80A | B | 4EVE3 | 2026-06-22 | 0.38
103 | A1 | 14558068285 | 71205556 | Hexing | HXP100DII | 1x80A | W | 4EVE3 | 2026-06-22 | 1.37
105 | A1 | 14558068301 | 71205556 | Hexing | HXP100DII | 1x80A | R | 4EVE3 | 2026-06-22 | 1.63
107 | A1 | 14558067899 | 71205556 | Hexing | HXP100DII | 1x80A | W | 3EVE3 | 2026-06-20 | 0.02
109 | A1 | 14558067873 | 71205556 | Hexing | HXP100DII | 1x80A | R | 3EVE3 | 2026-06-20 | 0.04
111 | A1 | 14558067881 | 71205556 | Hexing | HXP100DII | 1x80A | B | 3EVE3 | 2026-06-20 | 0.55
113 | A1 | 14558067907 | 71205556 | Hexing | HXP100DII | 1x80A | W | 3EVE3 | 2026-06-20 | 0.53
115 | A1 | 14558067964 | 71205556 | Hexing | HXP100DII | 1x80A | R | 3EVE3 | 2026-06-20 | 0
117 | A1 | 14558069713 | 71205556 | Hexing | HXP100DII | 1x80A | R | 2EVE3 | 2026-06-20 | 0
119 | A1 | 14558069705 | 71205556 | Hexing | HXP100DII | 1x80A | B | 2EVE3 | 2026-06-20 | 0
121 | A1 | 14558069762 | 71205556 | Hexing | HXP100DII | 1x80A | W | 2EVE3 | 2026-06-20 | 0
123 | A1 | 14558069887 | 71205556 | Hexing | HXP100DII | 1x80A | R | 2EVE3 | 2026-06-20 | 0
125 | A1 | 14558068111 | 71205556 | Hexing | HXP100DII | 1x80A | B | 1EVE3 | 2026-06-20 | 0
127 | A1 | 14558068152 | 71205556 | Hexing | HXP100DII | 1x80A | R | 1EVE3 | 2026-06-20 | 0
Clubhouse | A1 | 98819618 | 82929684 | Iskra | MT174D | 3x100A | RWB |  | 2026-06-09 | 0

## Water Meters for invoicing
Water Meter Invoicing
Stand Number | Section | Meter serial number | Manufacturer | Meter Model | Connection size | Opening readings | Meter Commissioning Date
093 | A1 | 9897995 | Precision | Axioma | 15mm | 0.095 | 2026-05-26
095 | A1 | 10172258 | Precision | Axioma | 15mm | 0.104 | 2026-05-26
097 | A1 | 10172250 | Precision | Axioma | 15mm | 0.099 | 2026-05-26
099 | A1 | 10172261 | Precision | Axioma | 15mm | 0.101 | 2026-05-26
101 | A1 | 9897994 | Precision | Axioma | 15mm | 0.091 | 2026-05-26
103 | A1 | 9897912 | Precision | Axioma | 15mm | 0.073 | 2026-05-26
105 | A1 | 9898003 | Precision | Axioma | 15mm | 0.093 | 2026-05-26
107 | A1 | 9898044 | Precision | Axioma | 15mm | 0.081 | 2026-05-26
109 | A1 | 9898037 | Precision | Axioma | 15mm | 0.071 | 2026-04-30
111 | A1 | 9897906 | Precision | Axioma | 15mm | 0.068 | 2026-04-30
113 | A1 | 9897997 | Precision | Axioma | 15mm | 0.091 | 2026-04-30
115 | A1 | 9898005 | Precision | Axioma | 15mm | 0.093 | 2026-04-30
117 | A1 | 9897913 | Precision | Axioma | 15mm | 0.082 | 2026-04-24
119 | A1 | 9897993 | Precision | Axioma | 15mm | 0.223 | 2026-04-24
121 | A1 | 9897907 | Precision | Axioma | 15mm | 0.08 | 2026-04-24
123 | A1 | 9897911 | Precision | Axioma | 15mm | 0.071 | 2026-05-26
125 | A1 | 9898001 | Precision | Axioma | 15mm | 1.163 | 2026-05-26
127 | A1 | 9897908 | Precision | Axioma | 15mm | 0.076 | 2026-05-26
Lifestyle Cetre Meter 1 | A1 | 10228692 | Precision | Axioma | 25mm | 0.094 | 2026-05-29
Lifestyle Cetre Meter 2 | A1 | 9279142 | Precision | Axioma | 32mm | 0.131 | 2026-04-24